## Migration CSV
Servers
Server Name | Completed (Yes/No) | Pingable | App/Role Review | Notes | Follow up with: | Application/Role | Application | CMDB Status | CMDB Environment | CMDB Subtype | Tester Group | Data from Angel | From Jose V. | Prod/Test/Dev | List from Angel | Domain Joined | Obsolete System | PCI Data | D1 Systems | Historical Systems | Rafeal's List (BigFix) | Decommissioned List per JT | Sales List | ITDG | Business Owners | Application Owners for Testing | Application SME | PowerShell Application Inventory | Faddom App Inventory | Faddom Map | AMR Application | Location | Destination - Cloud, FIS, Onsite | Migration Phase | Migration Group | Migration Method | Machine Type | Powered On | Operating System | vCPU's | vRAM (GB's) | Storage Provisioned (MB's) | Storage Used (MB's) | IP Address | Subnet Mask | Gateway | Tools NAT | New IP Address | New Subnet Mask | New DNS Servers | New Gateway | Private Cloud - Morpheus Cloud | Private Cloud - VMware Datastore | Private Cloud - VMware Port Group | Public Cloud - Azure SKU Family | Public Cloud - Azure SKU | Public Cloud - Azure CPU | Public Cloud - Azure RAM | Public Cloud - Azure Subscription | Public Cloud - Azure Resource Group | Public Cloud - Azure vNet | Public Cloud - Azure Subnet | Public Cloud - Azure Tags | Backup Method | Current Backups in Veeam | Hardware Dependancies
1502-VC01 | Yes |  | x | Decommissioned |  | Vcenter VMWare | Vcenter VMWare | Disposed/Retired | OFF | ESX | N/A | Not Found | Vcenter VMWare | Decommissioned |  | No | Decommissioned |  |  |  | No | 1502-VC01 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M203103GN |  |  | x |  |  | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | No Match | No Match | No Match | N/A | Not Found | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M203103GP |  |  | x |  |  | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | No Match | No Match | No Match | N/A | Not Found | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M203103GS |  |  | x |  |  | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery | No Match | No Match | No Match | N/A | Not Found | HPE Simplivity 380 Gen10-3 Nodes cluster for Disaster Recovery |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZY4 | Yes |  | x | Decommissioned |  | CHS2-ESXI08 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI08 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | No Match | No Match | No Match | N/A | Not Found | CHS2-ESXI08 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZY5 | Yes |  | x | Decommissioned |  | CHS2-ESXI01 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI01 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Disposed/Retired | OFF | ESX | N/A | Not Found | CHS2-ESXI01 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | 2M25210ZY5 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZY6 | Yes |  | x | Decommissioned |  | CHS2-ESXI09 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI09 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | No Match | No Match | No Match | N/A | Not Found | CHS2-ESXI09 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZY7 | Yes |  | x | Decommissioned |  | CHS2-ESXI03 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI03 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Disposed/Retired | OFF | ESX | N/A | Not Found | CHS2-ESXI03 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | 2M25210ZY7 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZY8 | Yes |  | x | Decommissioned |  | CHS2-ESXI12 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI12 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | No Match | No Match | No Match | N/A | Not Found | CHS2-ESXI12 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZYB | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | 2M25210ZYB | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZYC | Yes |  | x | Decommissioned |  | CHS2-ESXI11 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI11 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | No Match | No Match | No Match | N/A | Not Found | CHS2-ESXI11 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
2M25210ZYF | Yes |  | x | Decommissioned |  | CHS2-ESXI10 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | CHS2-ESXI10 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | No Match | No Match | No Match | N/A | Not Found | CHS2-ESXI10 - HP BL460c Gen9 10Gb/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
ADBSPR02 | Yes |  | x | Decommissioned |  | Active Directory | Active Directory | Disposed/Retired | OFF | Security | N/A | Not Found | Active Directory | Decommissioned |  | No | Decommissioned |  |  |  | No | ADBSPR02 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
APPSWEBDEV |  |  | x | Oracle Cloud |  | AppsWebDEV | AppsWeb | Installed | Development | Applications | N/A | Not Found | AppsWebDEV |  |  | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.179.4.194 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
APPSWEBPRD |  |  | x | Oracle Cloud |  | MicroStrategy Web Prod | MicroStrategy Web | Installed | Production | Applications | N/A | Not Found | MicroStrategy Web Prod |  |  | No | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.179.4.124 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
BIHHPSVR1 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  | Decommissioned |  | Yes | TBD |  |  |  | Yes | BIHHPSVR1 | No |  | N/A |  | N/A | BIHHPSVR1 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.202.15
biportal-dev |  |  | x | Oracle Cloud |  | Tutela BiPortal Developments | Tutela BiPortalelopments | Installed | Development | Applications | N/A | Not Found | Tutela BiPortal Developments |  |  | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) |  |  |  |  | 10.179.4.204 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
BRHHPSVR01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | BRHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.21.15
BSDHCP | Yes |  | x | Decommissioned |  | Active Directory | Active Directory | Disposed/Retired | OFF | Security | N/A | Not Found | Active Directory | Decommissioned |  | No | Decommissioned |  |  |  | No | BSDHCP | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
BSINTRASQL |  |  | x | Decommissioned |  |  |  | Disposed/Retired | Migration | Database | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | BSINTRASQL | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
bsprbi-portal |  |  | x | Oracle Cloud |  | TBD | TBD | Installed | Production | Applications | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) |  |  |  |  | 10.179.4.83 | [20 empty] | No
bspr-edp-cube-02 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cube-02 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cucm-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cucm-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cucm-02 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cucm-02 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cucm-03 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cucm-03 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cucn-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cucn-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cups-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cups-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cwms-adm-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cwms-adm-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-cwms-vcenter-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-cwms-vcenter-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-paging-srv | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-paging-srv | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-pcd-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-pcd-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
bspr-edp-uccx-01 | Yes |  | x | Decommissioned |  | PBX Servers | PBX | Disposed/Retired | OFF | Applications | N/A | Not Found | PBX Servers | Decommissioned |  | No | Decommissioned |  |  |  | No | bspr-edp-uccx-01 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
COHHPSVR02 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | COHHPSVR02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.201.15
DCBSPR-ESXI01 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI01 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI01D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI01D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI02 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI02 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI03 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI03 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI03D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI03D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI04 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI04 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI04D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI04D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI05 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI05 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI06D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI06D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI07 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI07 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI07D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI07D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI08 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI08 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI08D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI08D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI09 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI09 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI09D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI09D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI10 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI10 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI10D | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI10D | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCBSPR-ESXI11 | Yes |  | x | Decommissioned |  | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | VMWare ESX Hosts | Disposed/Retired | OFF | ESX | N/A | Not Found | VMWare ESX Hosts - HP BL460c Gen8 E5-v2 10Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DCBSPR-ESXI11 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCHHPSVR02 |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | DCHHPSVR02 | No |  | N/A |  | N/A | DCHHPSVR02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.35
DCPSTG01 |  |  | x | Miami; Out of scope |  |  |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [7 empty] | 10.87.200.32
DCPVMGT01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Database | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCPVMGT01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.200.105
DCVBKUP01 |  |  | x | Miami; Out of scope; updated CMDB status and environment per Angel - jdeltoro 11/10 |  |  |  | Installed | Production | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVBKUP01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.20 | [20 empty] | No
DCVBKUP02 |  |  | x | Miami; Out of scope |  |  |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVBKUP02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2022 10.0.20348.2527 (21H2) |  |  |  |  | 10.87.206.50
DCVBPM |  |  | x | Miami; Out of scope |  |  |  | Installed | Development | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVBPM | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.199.23 | [20 empty] | No
DCVBPM01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVBPM01 | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.26
DC-VC01 | Yes |  | x | Decommissioned |  | SIEM Tenable MEXICO CI0068168009 - HP BL460c Gen8 10/20Gb FLB CTO Blade | SIEM Tenable MEXICO CI0068168009 - HP BL460c Gen8 10/20Gb FLB CTO Blade | Disposed/Retired | OFF | ESX | N/A | Not Found | SIEM Tenable MEXICO CI0068168009 - HP BL460c Gen8 10/20Gb FLB CTO Blade | Decommissioned |  | No | Decommissioned |  |  |  | No | DC-VC01 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
DCVCYAR01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Security | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVCYAR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2022 10.0.20348.2402 (21H2) |  |  |  |  | 10.87.200.32 | [20 empty] | No
DCVDC02 | Yes |  | x | Decommissioned |  | Domain Controller | Domain Controller | Disposed/Retired | Production | Domain Controller | FIS Infra | Not Found | Domain Controller | Decommissioned |  | No | Decommissioned |  |  |  | No | DCVDC02 | Yes |  | Juan Espinoza |  | Edgardo Santiago | [5 empty] | Onsite | N/A | N/A | No Migration
DCVDEPCON01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVDEPCON01 | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.31
DCVDWS01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Utilities | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVDWS01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.240 | [20 empty] | No
DCVEDC01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVEDC01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.206.24 | [20 empty] | No
DCVENCOM01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVENCOM01 | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.27
DCVFILE01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVFILE01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.137 | [20 empty] | No
DCVFOB01 |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | Production | Security | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | DCVFOB01 | No |  | N/A |  | N/A | DCVFOB01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.58
DCVINTRA01 |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | No | DCVINTRA01 | No |  | N/A |  | N/A | DCVINTRA01 | [5 empty] | N/A | N/A | No Migration | [7 empty] | 10.87.200.40
DCVMBD01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Utilities | N/A | Not Found |  |  |  | Yes | Out of Scope |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVMBD01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.11 | [20 empty] | No
DCVMT01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Mitel HQ Phone system | Mitel HQ Phone system | Disposed/Retired | OFF | File Server | N/A | Not Found | Mitel HQ Phone system | Decommissioned |  | Yes | Decommissioned |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  | poweredOff | [5 empty] | 10.87.199.130 | [10 empty] | No CPU/RAM Info Found
DCVMT02 |  |  | x | Miami; Out of scope |  |  |  | Installed | Development | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVMT02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.26 | [20 empty] | No
DCVMTBM01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVMTBM01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.28 | [20 empty] | No
DCVMTDVS01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVMTDVS01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.2061 (1809) |  |  |  |  | 10.87.200.29 | [20 empty] | No
DCVNS01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Security | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVNS01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.54 | [20 empty] | No
DCVRPT01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  |  |  | Disposed/Retired | Production | Database | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVRPT01 | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2019 10.0.17763.5579 (1809) |  |  |  |  | 10.87.199.172
DCVRS01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.145 | [20 empty] | No
DCVSQL01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Database | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVSQL01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.36 | [20 empty] | No
DCVSQN01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Development | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVSQN01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2022 10.0.20348.2527 (21H2) |  |  |  |  | 10.87.200.33 | [20 empty] | No
DCVSTG01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVSTG01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.200.23 | [20 empty] | No
DCVSYN01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Development | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | DCVSYN01 | [5 empty] | N/A | N/A | No Migration | [7 empty] | 10.87.199.50 | [20 empty] | No
DCVTRKIT01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVTRKIT01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.39 | [20 empty] | No
DCVTRKIT02 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVTRKIT02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.40 | [20 empty] | No
DCVWEB01 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  |  |  | Disposed/Retired | OFF | Security | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVWEB01 | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.173
DCVWGOLD01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DCVWGOLD01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.199.200 | [20 empty] | No
DEHHPSVR01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DEHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.205.15
DOHHPSVR01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | DOHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.83.164.15
EZLENDER-IDM-VS |  |  | x | FL; Out of Scope |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | EZLENDER-IDM-VS | No |  | N/A |  | N/A | EZLENDER-IDM-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2008R2 6.1.7601 |  |  |  |  | 10.81.238.49
FB072378 |  |  | x |  |  | VMware ESXi UIP | VMware ESXi UIP | Installed | Production | ESX | N/A | Not Found | VMware ESXi UIP |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.172
FB1000MGR | [5 empty] | FoundStone | FoundStone | Available | OFF | Database | N/A | Not Found | FoundStone | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FB51058 | Yes |  | x | Decommissioned |  | FBINFTECSANT | FBINFTECSANT | Available | OFF | File Server | N/A | Not Found | FBINFTECSANT | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB52851 | Yes |  | x | Decommissioned |  | Budget Planning Server COB (DR) | Budget Planning COB (DR) | Disposed/Retired | OFF | Applications | N/A | Not Found | Budget Planning Server COB (DR) | Decommissioned |  | No | Decommissioned |  |  |  | No | FB52851 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB52954 | Yes |  | x | Decommissioned |  | Sungard Application SQL Server | Sungard Application SQL | Disposed/Retired | OFF | Database | N/A | Not Found | Sungard Application SQL Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FB52954 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB53661 | Yes |  | x | Decommissioned |  | File Server COB | FileCOB | Available | OFF | File Server | N/A | Not Found | File Server COB | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB53916 |  |  | x | No Concerns |  | Domain Controller ¦ SA1519 | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller ¦ SA1519 | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB53916 | fb53916.firstbank.local |  |  | Santurce 1519 | FIS | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 1 | 1024 | 141313 | 141313 | 10.19.137.4 | [20 empty] | No
FB54508 |  |  |  | Included in JT's decommission list |  | Domain Controller 4 ¦ MR1130 | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 4 ¦ MR1130 | Decommissioned |  | Yes | TBD |  |  |  | Yes | FB54508 | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB54508 |  |  |  | MR1130 | FIS | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 295108 | 295108 | 10.30.137.10 | 255.255.255.0 | [19 empty] | No
FB54509 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Domain Controller 5 ¦ MR1130 | Domain Controller | Disposed/Retired | OFF | Domain Controller | FIS Infra | Not Found | Domain Controller 5 ¦ MR1130 | Decommissioned |  | Yes | Decommissioned |  |  |  | No | FB54509 | Yes |  | Juan Espinoza |  | Edgardo Santiago |  |  |  |  | MR1130 | FIS | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 25600 | 304283 | 304283 | 10.30.137.11 | 255.255.255.0
FB54510 |  |  |  | Included in JT's decommission list; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Domain Controller | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | FB54510 | No |  | Juan Espinoza |  | Edgardo Santiago | FB54510 |  |  |  | MR1130 | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 295021 | 295021 | 10.30.137.9 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FB54511 |  |  |  | Included in JT's decommission list; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Domain Controller 1 ¦ MR1130 | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 1 ¦ MR1130 | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | FB54511 | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB54511 |  |  |  | MR1130 | FIS | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 295130 | 295130 | 10.30.137.4 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | [8 empty] | Yes
FB54512 |  |  |  | No Concerns |  | Domain Controller 2 ¦ MR1130 | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 2 ¦ MR1130 | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB54512 |  |  |  | MR1130 | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 295075 | 295075 | 10.30.137.5 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FB55130 |  |  |  | To Be Decommissioned; No Migrate per Omar - Backup Repository Only |  | Guardium - Data Encryption | Guardium - Data Encryption | Installed | UAT | Utilities | N/A | Not Found | Guardium - Data Encryption | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.54 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB55388 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; Follow up with Omar about MIRC and what that is? - jdeltoro 5/9; Per Omar MIRC instance has been decommissioned and this can be grouped with Varonis systems; needs follow up discussion with Doug - jdeltoro 5/13; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Varonis\MIRC SQL Server | Varonis | Installed | Production | Utilities | N/A | Not Found | Varonis\MIRC SQL Server |  |  | Yes | Pending |  |  |  | Yes | FB55388 | Yes |  | Juan Espinoza |  | Luis Arvelo | FB55388 | FB55388.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.130.141 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB55406 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Development - Sharepoint UAT | Sharepoint | Disposed/Retired | OFF | Database | N/A | Not Found | Development - Sharepoint UAT | Decommissioned |  | Yes | Completed |  |  |  | Yes | FB55406 | No |  | Juan Espinoza |  | N/A | FB55406 | No Agent |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server | poweredOff | Win2012, Win2008 |  |  |  |  | 10.30.153.78 | [10 empty] | No CPU/RAM Info Found
FB55408 | [5 empty] | SharePoint UIT\DEV | SharePoint | Installed | Development | Applications | N/A | Not Found | SharePoint UIT\DEV | Dev |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB55408 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.140.6 | [10 empty] | No CPU/RAM Info Found
FB55409 | [5 empty] | ProNet Scanning Server | ProNet Scanning | Installed | Production | Monitoring | N/A | Not Found | ProNet Scanning Server |  |  | Yes | TBD |  |  |  | Yes | FB55409 | Yes |  | N/A |  | N/A | FB55409 | FB55409.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.136.55 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FB55415 | Yes |  | x | Decommissioned |  | IBM Encription Key Manager | IBM Encription Key Manager | Disposed/Retired | OFF | Applications | N/A | Not Found | IBM Encription Key Manager | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55415 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55416 |  |  |  | Changed CMDB values to OFF per Angel - jdeltoro 11/10 |  | IBM Security Guardium | IBM Security Guardium | OFF | OFF | Applications | N/A | Not Found | IBM Security Guardium | Decommissioned |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.161 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB55419 | [5 empty] | SharePoint Web Server - Is a virtual server | SharePoint Web- Is a virtual | Installed | Production | Applications | N/A | Not Found | SharePoint Web Server - Is a virtual server |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB55419 | FB55419.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012 6.2.9200 | 8 | 32760 | 288956 | 256001 | 10.30.137.230 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
fb55420 |  |  |  | Follow up with Omar identifying databases and target destination for database and application - jdeltoro 5/5 |  | SQL Server Cluster Node 2 | SQLCluster Node 2 | Installed | Production | Database | N/A | Not Found | SQL Server Cluster Node 2 |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2003 5.2.3790 |  |  |  |  | 10.30.141.32 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55421 | [5 empty] | SharePoint SQL | SharePoint SQL | Installed | Production | Applications | N/A | Not Found | SharePoint SQL |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB55421 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.130.64 | [10 empty] | No CPU/RAM Info Found
FB55426 | Yes |  | x | Decommissioned; Modified CMDB status and environment to off per Angel - jdeltoro 11/10 |  | On-Base APPL | On-Base APPL | OFF | OFF | Applications | N/A | Not Found | On-Base APPL | Decommissioned |  | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB55431 | [5 empty] | SharePoint ¦ INTRA-SPS-APP01 | SharePoint ¦ INTRA-SPS-APP01 | Installed | Production | Applications | N/A | Not Found | SharePoint ¦ INTRA-SPS-APP01 |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB55431 | FB55431.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.137.231 | [10 empty] | No CPU/RAM Info Found | [9 empty] | Yes
FB55432 | [5 empty] | Sharepoint SQL | Sharepoint SQL | Installed | Production | Applications | N/A | Not Found | Sharepoint SQL |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB55432 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.130.65 | [10 empty] | No CPU/RAM Info Found
FB55433 | Yes |  | x | Decommissioned |  | SharePoint ¦ INT-SPS-WFE02 ¦ DMZ | SharePoint ¦ INT-SPS-WFE02 ¦ DMZ | Disposed/Retired | OFF | Applications | N/A | Not Found | SharePoint ¦ INT-SPS-WFE02 ¦ DMZ | Decommissioned |  | No | Pending |  |  |  | No | FB55433 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB55434 | Yes |  | x | Decommissioned |  | SharePoint ¦ INT-SPS-WFE01 ¦ DMZ | SharePoint ¦ INT-SPS-WFE01 ¦ DMZ | Disposed/Retired | OFF | Applications | N/A | Not Found | SharePoint ¦ INT-SPS-WFE01 ¦ DMZ | Decommissioned |  | No | Pending |  |  |  | No | FB55434 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB55460 |  |  | x | To Be Decommissioned; No Migrate |  | Cell Manager ¦ PHILADELPHIA | Cell Manager ¦ PHILADELPHIA | Disposed/Retired | OFF | Applications | N/A | Not Found | Cell Manager ¦ PHILADELPHIA | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55460 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FB55461 | Yes |  | x | Decommissioned |  | VI Server Spare | VISpare | Available | OFF | Applications | N/A | Not Found | VI Server Spare | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FB55470 | Yes |  | x | Decommissioned |  | IBM Security Guardium Central Manager | IBM Security Guardium Central Manager | Disposed/Retired | OFF | Utilities | N/A | Not Found | IBM Security Guardium Central Manager | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55470 | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.98 | [10 empty] | No CPU/RAM Info Found
FB55473 |  |  |  | Guardium Management |  | IBM Security Guardium Data Encryption DSM Primary Collector | Guardium | Installed | Production | Security | N/A | Not Found | IBM Security Guardium Data Encryption DSM Primary Collector | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 8 | 16384 | 272473 | 272473 | 10.30.130.97 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FB55475 | Yes |  | x | Decommissioned |  | SQL Server VAM & PayPlus (COB) | SQLVAM & PayPlus (COB) | Available | OFF | Database | N/A | Not Found | SQL Server VAM & PayPlus (COB) | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55478 | Yes |  | x | Decommissioned |  | IBM Security Guardium Colector | IBM Security Guardium Colector | Disposed/Retired | OFF | Security | N/A | Not Found | IBM Security Guardium Colector | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55478 | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.100 | [10 empty] | No CPU/RAM Info Found
FB55480 |  |  |  | Guardium Management; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | IBM Security Guardium Data Encryption DSM Secondary Collector | Guardium | Installed | Production | Database | N/A | Not Found | IBM Security Guardium Data Encryption DSM Secondary Collector | Prod |  | No | Pending |  |  |  | No | FB55480 | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 8 | 16384 | 272472 | 272472 | 10.30.130.99 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
FB55632 | Yes |  | x | Decommissioned |  | HP DATA PROTECTOR | HP DATA PROTECTOR | Disposed/Retired | OFF | Utilities | N/A | Not Found | HP DATA PROTECTOR | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55632 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB55801 |  |  |  | Follow up with Dean Hanna or Adam Lucero - jdeltoro 5/7 |  | IBM TEM Server - SQL/APP (BigFix) | BigFix | Installed | Production | Database | N/A | Not Found | IBM TEM Server - SQL/APP |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot | FB55801 | FB55801.firstbank.local |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 49152 | 1790271 | 1198205 | 10.30.130.57 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E8s_v6 | 8 | 64 | [6 empty] | Yes
FB55801-OLD | Yes |  | x | Decommissioned |  | IBM TEM Server - SQL/APP | IBM TEM- SQL/APP | Disposed/Retired | OFF | Database | N/A | Not Found | IBM TEM Server - SQL/APP | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55801-OLD | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FB55977 | Yes |  | x | Decommissioned |  | Xamine ETL COB | Xamine | Disposed/Retired | OFF | Database | TSA/CDO | Not Found | Xamine ETL COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55977 | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | [5 empty] | FIS | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.134.242 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55978 | [5 empty] | Xamine | Xamine | Installed | Development | Database | TSA/CDO | Not Found | Xamine |  |  | No | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  | FB55978 |  | MR1130 | FIS | Milestone 3 |  | TBD | Physical Server |  | Linux Red Hat Enterprise 8.9 (4.18.0-513.5.1.el8_9.x86_64) |  |  |  |  | 10.30.140.166 | 255.255.255.0 |  |  | 10.100.140.166 | [6 empty] | TBD | TBD
FB55979 | [5 empty] | Xamine Oracle Server | Xamine | Installed | UAT | Database | TSA/CDO | Not Found | Xamine Oracle Server |  |  | No | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  | FB55979 |  | MR1130 | FIS | Milestone 3 |  | TBD | Physical Server |  | Linux Red Hat Enterprise 8.9 (4.18.0-477.21.1.el8_8.x86_64) |  |  |  |  | 10.30.140.162 | 255.255.255.0 |  |  | 10.100.140.162 | [6 empty] | TBD | TBD
FB55980 |  |  | x | Validate No Migrate |  | XAMINE Oracle Server Contingency | Xamine | Installed | Contingency | Database | TSA/CDO | Not Found | XAMINE Oracle Server Contingency |  |  | No | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  |  |  | Arterial | FIS | Milestone 3 |  | TBD | Physical Server |  | Linux Red Hat Enterprise 8.4 (4.18.0-305.el8.x86_64) |  |  |  |  | 10.20.102.12 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB55981 | [5 empty] | XAMINE Report Server Prod | Xamine | Available | OFF | Database | TSA/CDO | Not Found | XAMINE Report Server Prod |  |  | No | Completed |  |  |  | No |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | [7 empty] | 10.30.134.241 | 255.255.255.0 |  |  | 10.100.134.241 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55982 | Yes |  | x | Decommissioned |  | XAMINE Report Server Prod | Xamine | Available | OFF | Database | TSA/CDO | Not Found | XAMINE Report Server Prod | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | [5 empty] | FIS | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB55983 | Yes |  | x | Decommissioned |  | VMware ESXi COB | VMware ESXi COB | Available | OFF | ESX | N/A | Not Found | VMware ESXi COB | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55984 |  |  | x | To Be Decommissioned; No Migrate |  | VMware ESXi Sungard | VMware ESXi Sungard | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Sungard | Decommissioned |  | No | Decommissioned |  |  |  | No | FB55984 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
fb55985 |  |  | x | To Be Decommissioned; No Migrate |  | VMware ESXi Sungard | VMware ESXi Sungard | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Sungard | Decommissioned |  | No | Decommissioned |  |  |  | No | fb55985 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB55986 | [5 empty] | Encompass Database - MSSQL | Encompass | Installed | STAGING | Database | Mortgage Sysytems | Not Found | Encompass Database - MSSQL |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Luzmarie Velez |  | Waldemar Velez | FB55986 |  |  | Encompass | MR1130 | Cloud | Milestone 2 | Group 3 | TBD | Physical Server |  | Win2019 10.0.17763.5329 (1809) |  |  |  |  | 10.30.130.177 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB55987 | [5 empty] | ESXI Host | ESXI Host | Installed | SIT | Applications | N/A | Not Found | POC - Unknown at this time |  |  | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.15 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6
FB55988 | Yes |  | x | Decommissioned |  | VMware ESXi Linux | VMware ESXi | Available | OFF | ESX | N/A | Not Found | VMware ESXi Linux | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55989 | Yes |  | x | Decommissioned |  | VMware ESXi Linux | VMware ESXi | Available | OFF | ESX | N/A | Not Found | VMware ESXi Linux | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55990 | Yes |  | x | Decommissioned |  | VMware ESXi Linux | VMware ESXi | Available | OFF | ESX | N/A | Not Found | VMware ESXi Linux | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55991 | Yes |  | x | Decommissioned |  | VMware ESXi Linux | VMware ESXi | Available | OFF | ESX | N/A | Not Found | VMware ESXi Linux | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB55992 | Yes |  | x | Decommissioned |  | VMware ESXi Linux | VMware ESXi | Available | OFF | ESX | N/A | Not Found | VMware ESXi Linux | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6
fb56000 |  |  | x | Validate No Migrate |  | Bancware LIBOR ALM Compute DR | Bancware | Installed | Contingency | Applications | Financial Planning | Not Found | LIBOR ALM Compute DR |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | fb56000 |  |  | Bancware | Santurce 1519 | Cloud | Milestone 2 | Group 3 | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.19.137.32 | [10 empty] | No CPU/RAM Info Found
FB56002 | Yes |  | x | Decommissioned |  | VMware ESXi UIP COB | VMware ESXi UIP COB | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi UIP COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB56002 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.142.22 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB56003 | Yes |  | x | Decommissioned |  | VMware ESXi UIP COB | VMware ESXi UIP COB | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi UIP COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB56003 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.36 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB56004 | Yes |  | x | Decommissioned |  | VMware ESXi UIP COB | VMware ESXi UIP COB | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi UIP COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB56004 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.34 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB56228 |  |  | x |  |  | VMware ESX 5.1.0 For E3 | VMware ESX 5.1.0 For E3 | Installed | Production | ESX | N/A | Not Found | VMware ESX 5.1.0 For E3 |  |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.67 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB56229 | [5 empty] | SharePoint SQL UAT | SharePoint SQL | Installed | UAT | Applications | N/A | Not Found | SharePoint SQL UAT |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB56229 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.140.194 | [10 empty] | No CPU/RAM Info Found
FB56230 | Yes |  | x | Decommissioned |  | SQL UAT Proyecto SQL 2012 Migration Staging | SQL Proyecto SQL 2012 Migration Staging | Disposed/Retired | OFF | Database | N/A | Not Found | SQL UAT Proyecto SQL 2012 Migration Staging | Decommissioned |  | No | Decommissioned |  |  |  | No | FB56230 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
fb56231 |  |  |  | Shared Oracle database with multiple applications. Shares with D1 systems. |  | Digital One - Xpress Development Database Server, TPSS - Oracle Server | Xpress | Installed | UIT | Database | TSA | Not Found | Digital One - Xpress Development Database Server - Oracle | Dev |  | No | TBD |  | Yes |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  | FB56231 - D1 | Xpress, TPSS | MR1130 | FIS | Milestone 2 | Group 6 | D1 | Physical Server |  | Linux Oracle Enterprise Server 7.9 (4.1.12-124.68.3.el7uek.x86_64) |  |  |  |  | 10.30.140.160 | 255.255.255.0 |  |  | 10.100.140.160 | [6 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6
FB56232 | Yes |  | x | Decommissioned |  | VMware ESXi COB | VMware ESXi COB | Available | OFF | ESX | N/A | Not Found | VMware ESXi COB | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6
FB57483 | Yes |  | x | Decommissioned |  | Oracle Xamine Database | Xamine | Disposed/Retired | OFF | Database | TSA/CDO | Not Found | Oracle Xamine Database | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57483 | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | [5 empty] | FIS | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB57484 | Yes |  | x | Decommissioned |  | Sharepoint ¦ INT-SQL-SPS01 ¦ DMZ | Sharepoint ¦ INT-SQL-SPS01 ¦ DMZ | Disposed/Retired | OFF | Applications | N/A | Not Found | Sharepoint ¦ INT-SQL-SPS01 ¦ DMZ | Decommissioned |  | No | Pending |  |  |  | No | FB57484 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB57487 | Yes |  | x | Decommissioned |  | SQL Cluster | SQL Cluster | Disposed/Retired | OFF | Database | N/A | Not Found | SQL Cluster | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57487 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6
FB57490 | Yes |  |  | Server appears to be decommissioned; |  | Xamine Business Object UAT | Xamine | Disposed/Retired | OFF | Database | TSA/CDO | Not Found | Xamine Business Object UAT | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57490 | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  | fb57490.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.140.133 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FB57492 | Yes |  | x | Decommissioned |  | IBM Security Guardium Colector | IBM Security Guardium Colector | Disposed/Retired | OFF | Utilities | N/A | Not Found | IBM Security Guardium Colector | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57492 | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.147.11 | [10 empty] | No CPU/RAM Info Found
FB57493 | Yes |  | x | Decommissioned per Angel - jdeltoro 5/7 |  | Oracle Xamine Database | Xamine | Disposed/Retired | OFF | Database | TSA/CDO | Not Found | Oracle Xamine Database | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57493 | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | [5 empty] | FIS | N/A | N/A | No Migration
FB57494 | Yes |  | x | Decommissioned |  | VMware ESXi Dev | VMware ESXi | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Dev | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57494 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB57766 | Yes |  | x | Decommissioned |  | VMware ESXi Dev | VMware ESXi | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Dev | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57766 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB57767 | Yes |  | x | Decommissioned |  | VMware ESXi Dev | VMware ESXi | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Dev | Decommissioned |  | No | Decommissioned |  |  |  | No | FB57767 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB57768 | [5 empty] | On Base / Pay by Phone / IIS Consolidation / CD Rates | Onbase | Installed | Production | Applications | TSA | Not Found | On Base / Pay by Phone / IIS Consolidation |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FB57768 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Physical Server |  | Win2008R2 6.1.7601 |  |  |  |  | 10.30.137.101 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB57769 | [5 empty] | On Base / Pay by Phone / IIS Consolidation / CD Rates | Onbase | Installed | Production | Applications | TSA | Not Found | On Base / Pay by Phone / IIS Consolidation |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FB57769 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Physical Server |  | Win2008R2 6.1.7601 |  |  |  |  | 10.30.137.102 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB57773 | Yes |  | x | Decommissioned |  | IP Security | IP Security | Available | OFF | Security | N/A | Not Found | IP Security | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB57881 | Yes |  | x | Decommissioned |  | IP Security MR876 | IP Security MR876 | Available | OFF | Security | N/A | Not Found | IP Security MR876 | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB58088 |  |  | x | To Be Decommissioned; No Migrate |  | VMware ESXi Sungard | VMware ESXi Sungard | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi Sungard | Decommissioned |  | No | Decommissioned |  |  |  | No | FB58088 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB58089 |  |  | x | Decommissioned per ticket CH25000182766 in CMC meeting - jdeltoro 9/18 |  | XPRESS Oracle Server COB | XPRESS OracleCOB | Installed | Contingency | Database | N/A | Not Found | XPRESS Oracle Server COB | Decommissioned |  | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOff | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.92.1.0.1.el7.x86_64) |  |  |  |  | 10.19.130.74
FB58260 | Yes |  | x | Decommissioned |  | Bancware ALM Compute Server | Bancware ALM | Available | OFF | Monitoring | N/A | Not Found | ALM Compute Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB58261 | Yes |  | x | Decommissioned |  | Bancware ALM Compute Server | Bancware ALM | Available | OFF | Monitoring | N/A | Not Found | ALM Compute Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB58262 | Yes |  | x | Decommissioned |  | Bancware ALM Compute Server | Bancware ALM | Available | OFF | Monitoring | N/A | Not Found | ALM Compute Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB58263 | Yes |  | x | Decommissioned |  | Analytical and Data Intergration Server | Analytical and Data Intergration | Available | OFF | Utilities | N/A | Not Found | Analytical and Data Intergration Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB58267 | Yes |  | x | Decommissioned |  | Bancware ALM Compute Server | Bancware ALM | Available | OFF | Monitoring | N/A | Not Found | ALM Compute Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB58268 | Yes |  | x | Decommissioned |  | Analytical and Data Intergration Server | Analytical and Data Intergration | Available | OFF | Utilities | N/A | Not Found | Analytical and Data Intergration Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB58269 | Yes |  | x | Decommissioned |  | Varonis Database | Varonis Database | Available | OFF | Database | N/A | Not Found | Varonis Database | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Luis Arvelo | [6 empty] | N/A | N/A | No Migration
FB58270 | Yes |  | x | Decommissioned |  | Bancware ALM Compute Server | Bancware ALM | Available | OFF | Monitoring | N/A | Not Found | ALM Compute Server | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB59110 | [5 empty] | Xamine ETL Server Prod | Xamine | Installed | Production | Applications | TSA/CDO | Not Found | Xamine ETL Server Prod |  |  | No | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  | FB59110 |  | MR1130 | FIS | Milestone 3 |  | TBD | Physical Server |  | Linux Red Hat Enterprise 8.9 (4.18.0-513.5.1.el8_9.x86_64) |  |  |  |  | 10.30.134.123 | 255.255.255.0 |  |  | 10.100.134.123
FB59111 | [5 empty] | Xamine Oracle DB Server Prod | Xamine | Installed | Production | Database | TSA/CDO | Not Found | Xamine Oracle DB Server Prod |  |  | No | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  | FB59111 |  | MR1130 | FIS | Milestone 3 |  | TBD | Physical Server |  | Linux Red Hat Enterprise 8.9 (4.18.0-425.19.2.el8_7.x86_64) |  |  |  |  | 10.30.130.73 | 255.255.255.0 |  |  | 10.100.130.73
FB60572 | Yes |  | x | Decommissioned |  | HP PROLIANT DL320E GEN8 HOT PLUG 4LFF CTO SERVER (Replacement MOEX Branches) | HP PROLIANT DL320E GEN8 HOT PLUG 4LFF CTO(Replacement MOEX Branches) | Disposed/Retired | OFF | Database | N/A | Not Found | HP PROLIANT DL320E GEN8 HOT PLUG 4LFF CTO SERVER (Replacement MOEX Branches) | Decommissioned |  | No | Decommissioned |  |  |  | No | FB60572 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB60581 | Yes |  | x | Decommissioned |  | HP | HP | Disposed/Retired | OFF | File Server | N/A | Not Found | HP | Decommissioned |  | No | Decommissioned |  |  |  | No | FB60581 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB62511 |  |  |  | Follow up with Omar identifying databases and target destination for database and application - jdeltoro 5/5 |  | SQL Cluster | SQL Cluster | Installed | Production | Database | N/A | Not Found | SQL Cluster |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB62511 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.184 | 255.255.255.0
FB62512 | Yes |  | x | Decommissioned |  | SQL Cluster 2008 R2 | SQL Cluster 2008 R2 | Disposed/Retired | OFF | Database | N/A | Not Found | SQL Cluster 2008 R2 | Decommissioned |  | No | Decommissioned |  |  |  | No | FB62512 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB62519 |  |  |  | Follow up with Omar need to determine databases and related applications- jdeltoro 5/7 |  | SQL Cluster Server NODE1 | SQL ClusterNODE1 | Installed | Production | Database | N/A | Not Found | SQL Cluster Server NODE1 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB62519 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.6614 (1607) |  |  |  |  | 10.30.130.235 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB62618 | [5 empty] | BARR - TEST / UAT / BARRNJE | BARR | Available | OFF | Utilities | N/A | Not Found | BARR - TEST / UAT / BARRNJE |  |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB62618 |  |  |  |  | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.133.59
FB62640 |  |  |  | Follow up with Omar on masking question with Doug - jdeltoro 5/7 |  | IBM Optim Information Analyzer (DB Classification and Masking) | IBM Optim | Installed | Production | Monitoring | N/A | Not Found | IBM Optim Information Analyzer (DB Classification and Masking) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | Omar Ramos / Luis Charti | FB62640 |  |  | IBM Optim | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.150 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB62641 |  |  |  | Currently version 11.5; Sends to Central Manager |  | IBM Security Guardium Colector | Guardium | Installed | Production | Monitoring | N/A | Not Found | IBM Security Guardium Colector | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.151 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB63350 |  |  | x | Check back after ASP Migration |  | SNA server | SNA | Available | OFF | Utilities | N/A | Not Found | SNA server | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63350 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.133.19 | 255.255.255.0
FB63351 |  |  | x | Check back after ASP Migration |  | SNA server | SNA | Available | OFF | Utilities | N/A | Not Found | SNA server | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63351 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.133.14 | 255.255.255.0
FB63352 |  |  | x | Check back after ASP Migration |  | BARR SNA Philadelphia | BARR | Available | OFF | Utilities | N/A | Not Found | BARR SNA Philadelphia |  |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63352 |  |  |  | Philladelphia | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.0.151.19
FB63353 | Yes |  | x | Decommissioned |  | BARR SNA COB | BARR | Available | OFF | Utilities | N/A | Not Found | BARR SNA COB | Decommissioned |  | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.20.105.14
FB63367 |  |  | x | To Be Decommissioned; No Migrate |  | SQL - DR Contingency Site | SQL - DR Contingency Site | Installed | Contingency | Applications | N/A | Not Found | SQL - DR Contingency Site |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63367 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.6897 (1607) |  |  |  |  | 10.0.151.114 | [10 empty] | No CPU/RAM Info Found
FB63368 |  |  | x |  |  | VMware ESXi (LAB) | VMware ESXi (LAB) | Installed | Development | ESX | N/A | Not Found | VMware ESXi (LAB) |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.171
FB63369 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.137
FB63370 | [5 empty] | New File Server cluster Node 1 (FBA01016) | File Server | Installed | Production | Applications | N/A | Not Found | New File Server cluster Node 1 (FBA01016) | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63370 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.193 | 255.255.255.0 | 10.30.137.1 | N/A | [7 empty] | No CPU/RAM Info Found
FB63371 |  |  |  | Follow up with Omar need to determine databases and related applications- jdeltoro 5/7 |  | SQL Cluster Server NODE2 | SQL ClusterNODE2 | Installed | Production | Database | N/A | Not Found | SQL Cluster Server NODE2 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63371 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.6981 (1607) |  |  |  |  | 10.30.130.236 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB63372 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.101
FB63373 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.103
FB63374 |  |  |  | Needs analysis post OneDrive project |  | File Server cluster Node 2 (FBA01016 - Cluster Name) - Home Directories, Dept Shares, etc. | File Server | Installed | Production | Applications | N/A | Not Found | File Server cluster Test Node 2 (FBA01016) | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63374 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.194 | 255.255.255.0 | 10.30.137.1 | N/A | [7 empty] | No CPU/RAM Info Found
FB63375 | Yes |  | x | Decommissioned |  | Cell Manager ¦ COB | Cell Manager ¦ COB | Disposed/Retired | OFF | Applications | N/A | Not Found | Cell Manager ¦ COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB63375 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB63376 | Yes |  | x | Decommissioned |  | DataProtector New 2 | DataProtector New 2 | Disposed/Retired | OFF | Utilities | N/A | Not Found | DataProtector New 2 | Decommissioned |  | No | Decommissioned |  |  |  | No | FB63376 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB63377 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.119
FB63434 | Yes |  | x | Decommissioned |  | HP DL320e Gen8 Hot Plug 4LFF CTO Server | HP DL320e Gen8 Hot Plug 4LFF CTO | Disposed/Retired | OFF | Domain Controller | N/A | Not Found | HP DL320e Gen8 Hot Plug 4LFF CTO Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FB63434 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB63435 | Yes |  | x | Decommissioned |  | HP DL320e Gen8 Hot Plug 4LFF CTO Server | HP DL320e Gen8 Hot Plug 4LFF CTO | Disposed/Retired | OFF | Domain Controller | N/A | Not Found | HP DL320e Gen8 Hot Plug 4LFF CTO Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FB63435 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB63911 | Yes |  | x | Repurposed to be new node in file server cluster per ticket CH25000182444 - jdeltoro 9/18; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | File Server Cluster Node 3 - FBA01016 | File Server | Installed | Production | Utilities | N/A | Not Found | Enterprise Vault - (NEW) | Prod |  | No | Pending |  |  |  | No | FB63911 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.197 | 255.255.255.0 | 10.30.137.1 | N/A
FB63939 |  |  | x | Validate No Migrate |  | VMware ESXi PCI COB | VMware ESXi COB | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi PCI COB |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.149.4
FB63940 |  |  |  | Follow up with Omar on databases and related applications - jdeltoro 5/8; appro, debt manager, d1, onesumx, etc. |  | PCI SQL Cluster | SQL Cluster | Installed | Production | Database | N/A | Not Found | PCI SQL Cluster |  |  | Yes | TBD | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63940 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.147.4 | [10 empty] | No CPU/RAM Info Found
FB63941 |  |  | x | Validate No Migrate |  | VMware ESXi PCI | VMware ESXi | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi PCI |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.142.40
FB63942 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | COB PCI SQL Cluster | COB SQL Cluster | Installed | Contingency | Database | N/A | Not Found | COB PCI SQL Cluster |  |  | Yes | Completed | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63942 |  |  |  | Santurce 1519 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.19.147.4 | [10 empty] | No CPU/RAM Info Found
FB63944 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | PCI SQL Reporting Services | SQL Reporting Services | Installed | Production | Database | N/A | Not Found | PCI SQL Reporting Services |  |  | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.147.6 | [10 empty] | No CPU/RAM Info Found
FB63945 |  |  | x |  |  | VMware ESXi PCI | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi PCI |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.149.6
FB63946 |  |  | x |  |  | VMware ESXi PCI | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi PCI |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.149.5
FB63960 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | PCI SQL Cluster | SQL Cluster | Installed | Production | Database | N/A | Not Found | PCI SQL Cluster |  |  | Yes | TBD | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.147.5 | [10 empty] | No CPU/RAM Info Found
FB63961 |  |  | x | Validate No Migrate |  | VMware ESXi PCI COB | VMware ESXi COB | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi PCI COB |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.142.42
FB63962 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | COB PCI SQL Cluster | COB SQL Cluster | Installed | Contingency | Database | N/A | Not Found | COB PCI SQL Cluster |  |  | Yes | TBD | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63962 |  |  |  | Santurce 1519 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.19.147.5 | [10 empty] | No CPU/RAM Info Found
FB63963 |  |  | x | Validate No Migrate |  | VMware ESXi PCI COB | VMware ESXi COB | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi PCI COB |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.149.6
FB63964 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | COB PCI SQL Reporting Services | COB SQL Reporting Services | Installed | Contingency | Database | N/A | Not Found | COB PCI SQL Reporting Services |  |  | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FB63964 |  |  |  | Santurce 1519 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2012R2 6.3.9600 |  |  |  |  | 10.19.147.6 | [10 empty] | No CPU/RAM Info Found
FB64006 |  |  |  | Reviewed with Omar - no concerns;Digital Banking team didn't recognize this SQL Cluster; Edgardo verifyed that he is seeing SQL Instances related to Digital Banking |  | Digital Banking - MSSQL Cluster Node 1 | Digital Banking | Installed | Production | Database | N/A | Not Found | Digital Banking - SQL Cluster Node 1 |  |  | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB64006 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.130.103 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB64007 |  |  |  | Reviewed with Omar - no concerns;Digital Banking team didn't recognize this SQL Cluster |  | Digital Banking - MSSQL Cluster Node 2 | Digital Banking | Installed | Production | Database | N/A | Not Found | Digital Banking - SQL Cluster Node 2 |  |  | Yes | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB64007 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Physical Server |  | Win2012 6.2.9200 |  |  |  |  | 10.30.130.104 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB64018 |  |  |  | Per Omar and Edgardo no migrate - jdeltoro 5/13 |  | Encompass DB COB | Encompass DB COB | Available | OFF | Database | N/A | Not Found | Encompass DB COB | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | [7 empty] | 10.19.130.133
FB64108 |  |  | x |  |  | VMware ESXi IC & Intranet Prod | VMware ESXi IC & Intranet | Available | OFF | ESX | N/A | Not Found | VMware ESXi IC & Intranet Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB64109 |  |  | x |  |  | VMware ESXi IC & Intranet Prod | VMware ESXi IC & Intranet | Available | OFF | ESX | N/A | Not Found | VMware ESXi IC & Intranet Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB64110 |  |  | x |  |  | VMware ESXi IC & Intranet Prod | VMware ESXi IC & Intranet | Available | OFF | ESX | N/A | Not Found | VMware ESXi IC & Intranet Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB64111 |  |  | x | Validate No Migrate |  | VMware ESXi IC & Intranet UAT\UIT | VMware ESXi IC & Intranet | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi IC & Intranet UAT\UIT |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.27
FB64112 |  |  | x | Validate No Migrate |  | VMware ESXi IC & Intranet UAT\UIT | VMware ESXi IC & Intranet | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi IC & Intranet UAT\UIT |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.29
fb64136 |  |  |  | Requires 6 CPU cores for Oracle Licensing |  | TPSS Database (LINUX) - Oracle Rack 12c | TPSS | Installed | Production | Database | TSA | Not Found | TPSS Database (LINUX) |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  | FB64136 - D1 | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Physical Server |  | Linux Red Hat Enterpise 7 |  |  |  |  | 10.30.130.190 | 255.255.255.0 |  |  | 10.100.130.190
fb64137 |  |  |  | Requires 6 CPU cores for Oracle Licensing |  | TPSS Database (LINUX) - Oracle Rack 12c | TPSS | Installed | Production | Database | TSA | Not Found | TPSS Database (LINUX) |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  | FB64137 - D1 | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Physical Server |  | Linux Red Hat Enterpise 7 |  |  |  |  | 10.30.130.191 | 255.255.255.0 |  |  | 10.100.130.191
FB64193 |  |  |  | Currently version 11.5; Sends to Central Manager |  | IBM Security Guardium Colector | Guardium | Installed | Production | Utilities | N/A | Not Found | IBM Security Guardium Colector | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.211 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB64274 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.143
FB64275 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.145
FB64276 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.147
FB64277 |  |  | x |  |  | VMware ESXi PCI | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi PCI |  |  | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.149.13
FB64632 | Yes |  | x | Decommissioned; follow up |  | Cell Manager ¦ MR1130 | Cell Manager ¦ MR1130 | Disposed/Retired | OFF | Applications | N/A | Not Found | Cell Manager ¦ MR1130 | Decommissioned |  | No | Decommissioned |  |  |  | No | FB64632 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB64633 | [5 empty] | Digital One SIT Branch Server | Digital One SIT Branch | Disposed/Retired | OFF | Applications | N/A | Not Found | Digital One SIT Branch Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FB64633 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FB64634 |  |  |  | Included in JT's decommission list |  | Digital One UAT Branch Server | Digital One Branch | Disposed/Retired | OFF | Applications | N/A | Not Found | Digital One UAT Branch Server | Decommissioned |  | No | Decommissioned |  | Yes |  | No | FB64634 | Yes |  | N/A |  | N/A |  |  | Not in Faddom |  |  |  | N/A | N/A | No Migration
FB64672 |  |  | x | Not in use |  | VMware ESXi UAT\DEV | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi UAT\DEV |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.184
FB64673 |  |  | x | Not in use |  | VMware ESXi UAT\DEV | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi UAT\DEV |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.186
FB64674 |  |  | x | Not in use |  | VMware ESXi Linux | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Linux |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.188
FB64725 |  |  | x | Marked as VMware ESXi - Needs confirmation; Probably no migrate |  | VMware ESXi Digital One Production | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Digital One Production |  |  | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | Marked as ESXi |  | MR1130 |  | N/A | N/A | No Migration | Physical Server |  | VMware? |  |  |  |  | 10.30.149.15
FB64726 |  |  | x | Marked as VMware ESXi - Needs confirmation; Probably no migrate |  | VMware ESXi Digital One Production | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Digital One Production |  |  | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | Marked as ESXi |  | MR1130 |  | N/A | N/A | No Migration | Physical Server |  | VMware? |  |  |  |  | 10.30.149.17
FB64727 |  |  | x | Marked as VMware ESXi - Needs confirmation; Probably no migrate |  | VMware ESXi Digital One Production | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Digital One Production |  |  | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | Marked as ESXi |  | MR1130 |  | N/A | N/A | No Migration | Physical Server |  | VMware? |  |  |  |  | 10.30.149.19
FB64787 |  |  | x | Marked as VMware ESXi - Needs confirmation; Probably no migrate |  | VMware ESXi D1 | VMware ESXi | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi D1 |  |  | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | Marked as ESXi |  |  |  | N/A | N/A | No Migration | Physical Server |  | VMware? |  |  |  |  | 10.20.114.10
FB64788 |  |  | x | Marked as VMware ESXi - Needs confirmation; Probably no migrate |  | VMware ESXi D1 | VMware ESXi | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi D1 |  |  | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | Marked as ESXi |  |  |  | N/A | N/A | No Migration | Physical Server |  | VMware? |  |  |  |  | 10.20.114.12
FB64866 | [5 empty] | Microsoft Deployment Toolkit 2013 (MDT) | Microsoft Deployment Toolkit 2013 (MDT) | Installed | Production | Applications | N/A | Not Found | Microsoft Deployment Toolkit 2013 (MDT) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB64866 |  |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.8.164 | [10 empty] | No CPU/RAM Info Found
FB65030 | [5 empty] | SQL 2016 UAT (BDI) Bancware | MSSQL, Bancware, ITDG | Installed | UAT | Database | Financial Planning | Not Found | SQL 2016 UAT (BDI) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB65030 |  |  | Bancware |  | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.147 | [10 empty] | No CPU/RAM Info Found
FB65031 |  |  |  | Majority of UIT Databases are located on this server - check if on the obsolete system and if a new SQL server has already been built that needs to be migrated. Follow up with Omar - jdeltoro 5/7 |  | SQL UIT\Dev Environment (Proyecto SQL 2018) | MSSQL Environment (Proyecto SQL 2018), ITDG | Installed | Development | Database | N/A | Not Found | SQL UIT\Dev Environment (Proyecto SQL 2018) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB65031 |  |  |  |  | Onsite | Shared Infrastructure |  | No Migration; New Build Replacement | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.140.251
FB65052 |  |  | x | To Be Decommissioned; No Migrate |  | VMware ESXi Sungard | VMware ESXi Sungard | Installed | Contingency | ESX | N/A | Not Found | VMware ESXi Sungard |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.0.151.120
FB65075 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.220
FB65076 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.221
FB65077 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.222
FB65078 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.223
FB65367 |  |  |  | Dependent on obsolete IIS server apps being moved to new IIS servers; good to keep in milestone 2; Mike M. to follow up with Derek - jdeltoro 5/13 |  | IIS Consolidated Prod (2016) | IIS Consolidated | Installed | Production | Web | TSA & others (Definir cuales son los aplicativos) | Not Found | IIS Consolidated Prod (2016) |  |  | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Juan Espinoza |  | Eric Lopez | FB65367 |  |  | TBD | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.146 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB65368 |  |  |  | Dependent on obsolete IIS server apps being moved to new IIS servers; good to keep in milestone 2; Mike M. to follow up with Derek - jdeltoro 5/13 |  | IIS Consolidated (2016) | IIS Consolidated | Installed | Production | Web | TSA & others (Definir cuales son los aplicativos) | Not Found | IIS Consolidated (2016) |  |  | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Juan Espinoza |  | Eric Lopez | FB65368 |  |  | TBD | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.147 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB65381 |  |  | x |  |  | VMware ESXi COB | VMware ESXi COB | Disposed/Retired | OFF | ESX | N/A | Not Found | VMware ESXi COB | Decommissioned |  | No | Decommissioned |  |  |  | No | FB65381 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FB65383 | [5 empty] | SQL 2016 Profitability & BDI Node 1 - Bancware | Bancware | Installed | Production | Database | Financial Planning | Not Found | SQL 2016 Profitability & BDI Node 1 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB65383 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.137 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB65384 | [5 empty] | SQL 2016 Profitability & BDI Node 2 - Bancware | Bancware | Installed | Production | Database | Financial Planning | Not Found | SQL 2016 Profitability & BDI Node 2 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB65384 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.138 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB65979 |  |  | x | Not in scope; No Migrate |  | Video Surveillance - Directory | Video Surveillance - Directory | Installed | Production | Security | N/A | Not Found | Video Surveillance - Directory |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB65979 |  |  |  |  | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.66.216
FB65980 | [5 empty] | Video Surveillance - Archiver | Video Surveillance - Archiver | Installed | Production | Security | N/A | Not Found | Video Surveillance - Archiver |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB65980 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.66.235
fb66339 |  |  | x |  |  | VMware ESXi Prod | VMware ESXi | Installed | Production | ESX | N/A | Not Found | VMware ESXi Prod |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.149
fb66340 |  |  | x |  |  | VMware ESXi | VMware ESXi | Installed | UAT | ESX | N/A | Not Found | VMware ESXi |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.151
FB69753 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | Domain Controller | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FB69753 | [5 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 2048 | 126459 | 126459 | 10.87.199.252
FB69754 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | Domain Controller | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FB69754 | [5 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 2048 | 126459 | 126459 | 10.81.238.53
FB69756 |  |  |  | Existing DC's remain; Lab VM's were deleted per Angel on 3/28 - jdeltoro |  | Domain Controller 1 - ECR Site | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 1 - ECR Site - Lab VM's - Likely not in scope of migration | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB69756 |  |  |  | Waterfront | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 7168 | 131579 | 131579 | 10.15.1.219 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud |  | N/A
FB69757 |  |  |  | Existing DC's remain; Lab VM's were deleted per Angel on 3/28 - jdeltoro |  | Domain Controller 2 - ECR Site | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 2 - ECR Site - Lab VM's - Likely not in scope of migration | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB69757 |  |  |  | FB Plaza V.I. | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 7168 | 131579 | 131579 | 10.1.152.219 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud |  | N/A
FB69758 |  |  | x |  |  | DHCP Server - ECR | DHCP- ECR | Installed | Production | Applications | N/A | Not Found | DHCP Server - ECR |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB69758 |  |  |  |  | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.15.1.221 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6
FB69759 |  |  |  | Existing DC's remain; Lab VM's were deleted per Angel on 3/28 - jdeltoro |  | Domain Controller 1 - MR876 Site | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 1 - MR876 Site - Lab VM's - Likely not in scope of migration | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB69759 |  |  |  | MR876 | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 1 | 6144 | 130535 | 130535 | 10.18.137.4 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud |  | N/A
FB69760 |  |  |  | Existing DC's remain; Lab VM's were deleted per Angel on 3/28 - jdeltoro |  | Domain Controller 2 - MR876 Site | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Not Found | Domain Controller 2 - MR876 Site - Lab VM's - Likely not in scope of migration | Prod |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB69760 |  |  |  | MR876 | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 3072 | 127483 | 127483 | 10.18.137.5 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud |  | N/A
FB69761 |  |  | x |  |  | DHCP Server - MR876 | DHCP- MR876 | Installed | Production | Applications | N/A | Not Found | DHCP Server - MR876 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB69761 |  |  |  |  | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.18.137.7 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FB69761-New |  |  | x |  |  | DHCP Server - MR876- temporaty server | DHCP- MR876- temporaty | Disposed/Retired | OFF | Applications | N/A | Not Found | DHCP Server - MR876- temporaty server | Decommissioned |  | No | Decommissioned |  |  |  | No | FB69761-New | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72378 | [5 empty] | HPE Solution Server Proliant DL360 G10 | HPE SolutionProliant DL360 G10 | No Match | No Match | No Match | N/A | Not Found | HPE Solution Server Proliant DL360 G10 | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FB72379 |  |  | x |  |  | VMware ESXi UIP | VMware ESXi UIP | Installed | Production | ESX | N/A | Not Found | VMware ESXi UIP |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.174 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72380 |  |  | x |  |  | VMware ESXi UIP | VMware ESXi UIP | Installed | Production | ESX | N/A | Not Found | VMware ESXi UIP |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.176 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72381 |  |  | x |  |  | VMware ESXi UIP | VMware ESXi UIP | Installed | Production | ESX | N/A | Not Found | VMware ESXi UIP |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.178 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72388 |  |  | x | To Be Decommissioned; No Migrate |  |  |  | Installed | STAGING | Database | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FB72388 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.0.151.142 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB72390 | [5 empty] | Veeam Proxy #3 | Veeam Proxy #3 | Installed | Production | Applications | N/A | Not Found | Veeam Proxy #3 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB72390 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.129.233 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FB72391 |  |  |  | Currently version 11.5; Sends to Central Manager |  | IBM Guardium Collector1 MC | Guardium | Installed | Production | Database | N/A | Not Found | IBM Guardium Collector1 MC | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.153 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB72392 |  |  |  | Need to determine plan for physical to virtual migration or new build - jdeltoro 6/24 |  | Monarch Server | Monarch | Installed | Production | Applications | N/A | Not Found | Monarch Server |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FB72392 |  |  | Monarch | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.25 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB72393 |  |  |  | Currently version 11.5; Sends to Central Manager |  | IBM Guardium Collector3 MC | Guardium | Installed | Production | Database | N/A | Not Found | IBM Guardium Collector3 MC | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.155 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB72394 | [5 empty] | Veeam Orchestrator (MR1130) | Veeam Orchestrator (MR1130) | Installed | Production | Database | N/A | Not Found | Veeam Orchestrator (MR1130) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB72394 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.129.232 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FB72397 | [5 empty] | Internal Web Server OnBase | MIT Zabbix Server | Disposed/Retired | OFF | Web | N/A | Not Found | Internal Web Server OnBase | Decommissioned |  | No | Decommissioned |  |  |  | No | FB72397 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FB72399 |  |  |  | Repurposed from Pay By Phone OnBase; Now is Apply Pay physical server - jdeltoro 10/15; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Apple Pay Prod | Apple Pay | Installed | STAGING | Applications | N/A | N/A - Server Renamed | N/A - Server Renamed | Prod | N/A - Server Renamed | N/A - Server Renamed | TBD |  |  |  | N/A - Server Renamed | N/A - Server Renamed | N/A - Server Renamed |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | TBD |  |  |  |  | 10.30.150.140 | 255.255.255.0 | 10.30.150.1 | [8 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FB72400 |  |  |  | Currently version 11.5; Sends to Central Manager |  | IBM Guardium Collector2 MC | Guardium | Installed | Production | Database | N/A | Not Found | IBM Guardium Collector2 MC | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.154 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB72401 |  |  | x | Validate No Migrate |  | Veeam Orchestrator (Arterial) |  | Installed | Production | Applications | N/A | Not Found | Veeam Orchestrator (Arterial) |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB72401 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.20.101.33 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72407 |  |  |  | Needs to be upgraded version 12 from 11.5 |  | IBM Guardium Central Manager MC1 | Guardium | Installed | Production | Database | N/A | Not Found | IBM Guardium Central Manager MC1 | Prod |  | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Physical Server | [6 empty] | 10.30.130.152 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FB72409 |  |  |  | Repurposed from D1 Onbase App; Now is Apple Pay physical server - jdeltoro 10/17; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Apple Pay Prod | Apple Pay | Installed | STAGING | Applications | TSA | N/A - Server Renamed | N/A - Server Renamed | Prod | N/A - Server Renamed | N/A - Server Renamed | TBD |  |  |  | N/A - Server Renamed | N/A - Server Renamed | N/A - Server Renamed |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | TBD |  |  |  |  | 10.30.150.141 | 255.255.255.0 | 10.30.150.1 | [8 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FB72410 | [5 empty] | ASP Test File Server | ASP File | Installed | STAGING | File Server | N/A | Not Found | ASP Test File Server |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB72410 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.140.219 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FB72412 | [5 empty] | Cold Onbase APP | Cold Onbase APP | Disposed/Retired | OFF | Database | N/A | Not Found | Cold Onbase APP | Decommissioned |  | No | Decommissioned |  |  |  | No | FB72412 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
fb72740 |  |  | x |  |  | VMware ESX | VMware ESX | Installed | STAGING | ESX | N/A | Not Found | VMware ESX |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.6 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
fb72776 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.228 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
fb72777 |  |  | x |  |  | VMware ESXi HPE Simplivity 380 G10 VDI | VMware ESXi HPE Simplivity 380 G10 VDI | Installed | Production | ESX | N/A | Not Found | VMware ESXi HPE Simplivity 380 G10 VDI |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.180.229 | [10 empty] | TBD
FB72778 |  |  | x | Validate No Migrate |  | VDI ESXI Hosts | VDI ESXI Hosts | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.180.220 | [10 empty] | TBD
FB72779 |  |  | x | Validate No Migrate |  | VDI ESXI Hosts | VDI ESXI Hosts | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.19.180.221 | [10 empty] | Standard Dlsv6 Family vCPUs
FB72780 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host VDI | DR ESXi Host VDI | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.180.222 | [10 empty] | Standard Dlsv6 Family vCPUs
FB73553 |  |  |  | Edgardo Santiago to follow up on whether this can be included in milestone 2 - jdeltoro 5/13; also related to GFT/Swift |  | Swift (Serv-U) SFTP/File Server - DEV | Serv-U | Installed | STAGING | File Server | TSA | Not Found | Swift (Serv-U) SFTP/File Server - PROD |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB73553 |  |  | Serv-U, Swift | MR1130 | Cloud | Milestone 2 | Group 6 | No Migration; New Build Replacement | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.140.66 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB73554 |  |  |  | Edgardo Santiago to follow up on whether this can be included in milestone 2 - jdeltoro 5/13; also related to GFT/Swift |  | Swift (Serv-U) SFTP/File Server - PROD | Serv-U | Installed | STAGING | File Server | TSA | Not Found | Swift (Serv-U) SFTP/File Server - COB |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FB73554 |  |  | Serv-U, Swift | MR1130 | Cloud | Milestone 2 | Group 6 | No Migration; New Build Replacement | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.220 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB73810 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.200 | [10 empty] | Standard Dlsv6 Family vCPUs
FB73811 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.202 | [10 empty] | Standard Dlsv6 Family vCPUs
FB73812 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.204 | [10 empty] | Standard Esv6 Family vCPUs
FB73813 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.205 | [10 empty] | Standard Esv6 Family vCPUs
FB73814 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.208 | [10 empty] | Standard Dlsv6 Family vCPUs
FB73815 |  |  | x |  |  | VMware ESX 7.0.3 | VMware ESX | Installed | Production | ESX | N/A | Not Found | VMware ESX 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.210 | [10 empty] | Standard Dlsv6 Family vCPUs
FB74855 | [5 empty] | Bancware ALM6 UAT Application Server | Bancware | Installed | UAT | Applications | Financial Planning | Not Found | Bancware ALM6 UAT Application Server |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB74855 |  |  | Bancware |  | Cloud | Milestone 2 | Group 3 | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.140.127 | [10 empty] | No CPU/RAM Info Found
FB74856 | [5 empty] | Bancware ALM6 Application | Bancware | Installed | Production | Applications | Financial Planning | Not Found | Bancware ALM6 Application |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB74856 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.137.251 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB74857 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | LIBOR DR SQL | LIBOR | Installed | Contingency | Database | N/A | Not Found | LIBOR DR SQL |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB74857 |  |  |  | Santurce 1519 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.19.130.17 | [10 empty] | No CPU/RAM Info Found
FB74858 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | LIBOR SQL Prod Server Node 2 | LIBOR | Installed | Production | Database | N/A | Not Found | LIBOR SQL Prod Server Node 2 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB74858 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.130.158 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB74859 |  |  |  | Needs discussion on AVD; Active/Passive Cluster; Would move with ALM app; NOT RESPONDING TO PING |  | LIBOR SQL UAT Server - Bancware/BDI | Bancware | Installed | UAT | Database | Financial Planning | Not Found | LIBOR SQL UAT Server |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FB74859 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 3 | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.130.156 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB74860 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | LIBOR SQL Prod Server Node 1 | LIBOR | Installed | Production | Database | N/A | Not Found | LIBOR SQL Prod Server Node 1 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB74860 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.130.157 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FB75076 | [5 empty] | VEEAM Proxy 01 | VEEAM Proxy 01 | Installed | Production | Utilities | N/A | Not Found | VEEAM Proxy 01 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75076 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.129.230 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs
FB75077 | [5 empty] | VEEAM Proxy 02 | VEEAM Proxy 02 | Installed | Production | Utilities | N/A | Not Found | VEEAM Proxy 02 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75077 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.129.231 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs
FB75078 |  |  | x | Validate No Migrate |  | VEEAM Proxy COB | VEEAM Proxy COB | Installed | Production | Applications | N/A | Not Found | VEEAM Proxy COB |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75078 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.20.101.229 | [10 empty] | Standard Dlsv6 Family vCPUs
FB75079 |  |  | x | Validate No Migrate |  | VEEAM Proxy Aretrial | VEEAM Proxy Aretrial | Installed | Production | Security | N/A | Not Found | VEEAM Proxy Aretrial |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75079 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.20.101.230 | [10 empty] | Standard Dlsv6 Family vCPUs
FB75086 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | SQL Server Nodo 1 - Arterial | SQLNodo 1 - Arterial | Installed | Contingency | Database | N/A | Not Found | SQL Server Nodo 1 - Arterial |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.20.119.17 | [10 empty] | No CPU/RAM Info Found
FB75087 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | SQL Server Nodo 2 - Arterial | SQLNodo 2 - Arterial | Installed | Contingency | Database | N/A | Not Found | SQL Server Nodo 2 - Arterial |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75087 |  |  |  | Arterial | Cloud | Shared Infrastructure |  | TBD | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.20.102.107 | [10 empty] | No CPU/RAM Info Found
FB75089 | [5 empty] | Sharepoint SQL Node 1 | Sharepoint SQL Node 1 | Installed | Production | Database | N/A | Not Found | Sharepoint SQL Node 1 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FB75089 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.221 | [10 empty] | No CPU/RAM Info Found
FB75090 | [5 empty] | Sharepoint SQL Node 2 | Sharepoint SQL Node 2 | Installed | Production | Database | N/A | Not Found | Sharepoint SQL Node 2 |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FB75090 |  |  |  |  | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.130.222 | [10 empty] | No CPU/RAM Info Found
FB75716 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Available | OFF | ESX | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | Powered Off | [5 empty] | 10.20.114.31 | [10 empty] | Standard Dlsv6 Family vCPUs
fb75794 |  |  | x |  |  | VMware ESXi 7.0.3 | VMware ESXi 7.0.3 | Installed | Production | ESX | N/A | Not Found | VMware ESXi 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.212 | [10 empty] | Standard Dsv6 Family vCPUs
fb75795 |  |  | x |  |  | VMware ESXi 7.0.3 | VMware ESXi 7.0.3 | Installed | Production | ESX | N/A | Not Found | VMware ESXi 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.214 | [10 empty] | Standard Dlsv6 Family vCPUs
fb75796 |  |  | x |  |  | VMware ESXi 7.0.3 | VMware ESXi 7.0.3 | Installed | Production | ESX | N/A | Not Found | VMware ESXi 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.216
fb75797 |  |  | x |  |  | VMware ESXi 7.0.3 | VMware ESXi 7.0.3 | Installed | Production | ESX | N/A | Not Found | VMware ESXi 7.0.3 |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.142.218
FB75998 |  |  |  | Part of Backup infrastructure System |  | Apollo Storage System | Apollo Storage System | Installed | Production | Applications | N/A | Not Found | Apollo Storage System |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Linux Red Hat Enterprise 9.3 (5.14.0-362.8.1.el9_3.x86_64) |  |  |  |  | 10.30.129.64
FB75999 |  |  |  | Part of Backup infrastructure System |  | Apollo Storage System | Apollo Storage System | Installed | Production | Applications | N/A | Not Found | Apollo Storage System |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Linux Red Hat Enterprise 9.3 (5.14.0-362.8.1.el9_3.x86_64) |  |  |  |  | 10.30.129.65
FB76000 |  |  |  | Part of Backup infrastructure System |  | Apollo Storage System | Apollo Storage System | Installed | Production | Applications | N/A | Not Found | Apollo Storage System |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Linux Red Hat Enterprise 9.3 (5.14.0-362.8.1.el9_3.x86_64) |  |  |  |  | 10.30.129.66
FB76001 |  |  |  | Part of Backup infrastructure System |  | Apollo Storage System | Apollo Storage System | Installed | Production | Applications | N/A | Not Found | Apollo Storage System |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Linux Red Hat Enterprise 9.3 (5.14.0-362.18.1.el9_3.x86_64) |  |  |  |  | 10.30.129.67
FB78080 |  |  | x | Validate No Migrate |  | ESX 3 Arterial | ESX 3 Arterial | Installed | Contingency | ESX | N/A | Not Found | ESX 3 Arterial |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.15
FB78081 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.16
FB78082 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.18
FB78083 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Available | OFF | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.20
FB78084 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.22
FB78085 |  |  | x | Validate No Migrate - Arterial |  | DR ESXi Host | DR ESXi Host | Installed | Contingency | ESX | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.20.114.24
FBA00003 |  |  | x |  |  | AD Migration Tool | AD Migration Tool | Installed | Production | Security | N/A | AD Migration Tool | AD Migration Tool | Decommissioned | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA00003 | FBA00003.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 4 | 8192 | 213090 | 213090 | 10.30.137.47 | 255.255.255.0 | [19 empty] | Yes
FBA00006 |  |  | x | Validate No Migrate |  | Domain Controller 2 - SA1519 Site | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Domain Controller 2 - SA1519 Site | Domain Controller 2 - SA1519 Site | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | FBA00006 | fba00006.firstbank.local |  |  | Santurce 1519 | Cloud | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 1 | 4096 | 143359 | 143359 | 10.19.137.5 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA00007 |  |  | x | Validate No Migrate |  | DHCP Server - SA1519 | DHCP- SA1519 | Installed | Production | Applications | N/A | DHCP Server - SA1519 | DHCP Server - SA1519 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA00007 | FBA00007.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 176466 | 69627 | 10.19.137.7 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | [8 empty] | No
FBA00008 |  |  | x |  |  | DHCP Server - MR1130 | DHCP- MR1130 | Installed | Production | Applications | N/A | DHCP Server - MR1130 | DHCP Server - MR1130 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA00008 | FBA00008.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 176394 | 176394 | 10.30.137.23 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA00010 | [5 empty] | Domain Controller | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Domain Controller MR1130 | Domain Controller | Prod | Production | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Edgardo Santiago | FBA00010 |  |  |  | MR1130 | FIS | Milestone 1 | New Build | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 272481 | 272481 | 10.30.137.11 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | [8 empty] | No
FBA00011 |  |  | x | Validate No Migrate |  | Domain Controller Alterial | Domain Controller | Installed | Production | Domain Controller | FIS Infra | Domain Controller Alterial |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Edgardo Santiago | FBA00011 | [5 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 12288 | 268685 | 268685 | 10.20.109.11 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
fba01002 |  |  |  | Needs review of file shares due to dependency with TPSS; all stored in a single directory; file server targeted to go to azure and tpss is going to FIS; needs full review of all data shares; will likely be moved sepearately and original server decommissioned - jdeltoro 5/5 |  | File Server VM | File Server | Installed | Production | File Server | N/A | File Server Cluster | File Server VM | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba01002 | fba01002.firstbank.local |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 24 | 55296 | 38222651 | 34427015 | 10.30.137.12 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D32ls_v6 | 32 | 64 | [6 empty] | Yes
FBA01004 |  |  | x |  |  | Print Server | Print Server | Installed | Production | Utilities | N/A | Print Server | Print Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA01004 | FBA01004.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 282736 | 168594 | 10.30.137.15 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA01008 | [5 empty] | PCI File Server | File | Installed | Production | File Server | N/A | PCI File Server | PCI File Server |  | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA01008 |  |  |  |  | Cloud | Milestone 4 |  | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 151742 | 151742 | 10.30.148.4 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA01010 | [5 empty] | APPRO File Server - PCI CDE | APPRO | Installed | Production | File Server | TSA | APPRO File Server - PCI CDE | APPRO File Server - PCI CDE | Prod | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA01010 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 2 | 10240 | 1189132 | 1189132 | 10.30.148.234 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | [6 empty] | Yes
FBA01013 | [5 empty] | PCI File Server - Non Structured Data | File Server | Installed | Production | File Server | N/A | PCI File Server - Non Structured Data | PCI File Server - Non Structured Data | Prod | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA01013 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 24576 | 23373221 | 23184195 | 10.30.148.8 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
fba01014 |  |  | x | To Be Decommissioned; No Migrate |  | Sungard file server | Sungard file | Installed | Contingency | File Server | N/A | Sungard file server | Sungard file server |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba01014 | fba01014.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 4096 | 1196586 | 575731 | 10.0.151.82 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA01015 | [5 empty] | New File Server Cluster virtual ip | New FileCluster virtual ip | No Match | No Match | No Match | N/A | Not Found | New File Server Cluster virtual ip |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA01015 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | [7 empty] | 10.30.137.195 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FBA01017 |  |  |  | Potential Transformation to Azure File Shares - Needs review of OS to validate other apps, scripts, etc. |  | APPRO File Server - UAT\TEST | APPRO | Installed | UAT | File Server | TSA | APPRO File Server - UAT\TEST | APPRO File Server - UAT\TEST | UAT | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA01017 | FBA01017.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 10 | 1024 | 973915 | 362293 | 10.30.140.208 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA01019 |  |  | x |  |  | BUILDINGS PRINT SERVER | BUILDINGS PRINT SERVER | Installed | Production | Applications | N/A | BUILDINGS PRINT SERVER (New Ricoh) | BUILDINGS PRINT SERVER |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA01019 | FBA01019.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 12288 | 473185 | 473185 | 10.30.137.202 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | [8 empty] | No
FBA01020 | [5 empty] | Onbase File Server 1 | Onbase | Installed | Production | File Server | TSA | Onbase File Server 1 | Onbase File Server 1 | Prod | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA01020 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 4 | 16384 | 95956367 | 95956367 | 10.30.148.42 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA01021 |  |  | x | Validate No Migrate |  | Onbase Fileserver 2 | Onbase | Installed | Production | File Server | TSA | Onbase Fileserver 2 | Onbase Fileserver 2 | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA01021 | FBA01021.firstbank.local |  |  | Arterial | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.6529 (1607) | 8 | 16384 | 90272014 | 90139296 | 10.20.120.43 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
FBA01022 |  |  | x |  |  | BRANCHES PRINT SERVER | BRANCHES PRINT Server | Installed | Production | Applications | N/A | BRANCHES PRINT SERVER | BRANCHES PRINT SERVER |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA01022 | FBA01022.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 417893 | 417893 | 10.30.137.183 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA01023 |  |  | x |  |  | MONEY EXPRESS PRINT SERVER | MONEY EXPRESS PRINT | Installed | Production | Applications | MOEX | MONEY EXPRESS PRINT SERVER | MONEY EXPRESS PRINT SERVER |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago (FIS) | FBA01023 | FBA01023.firstbank.local |  |  |  | Onsite | Milestone 3 |  | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 417878 | 417878 | 10.30.137.184 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA01024 |  |  | x | No Migrate per Juan Luis - jdeltoro 5/9 |  | File Server - Eureka | File- Eureka | Installed | STAGING | File Server | N/A | EUREKA FILE SERVER | File Server | Staging | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA01024 | FBA01024.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 3451432 | 2184682 | 10.30.137.34 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA01025 |  |  |  | Added to Milestone 1; Group 1 per Angel on 4/14 - jdeltoro; no migrate per Lizzie and Juan Luis - jdeltoro 11/18 | N/A | Money Express PLIS | Money Express PLIS | Installed | Development | File Server | Felipe Ramos/Alfredo Mercado | PLIS MOEX File Server DEV | Money Express PLIS | Dev | Development | Yes | TBD |  |  |  | Yes |  | No |  | Felipe Ramos |  | Ysabel Asencio | FBA01025 | FBA01025.firstbank.local |  |  | MR1130 | Cloud |  |  | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 8192 | 1237107 | 743778 | 10.30.140.28 | 255.255.255.0 | 10.30.140.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA01026 | [5 empty] | ITOMO File Server | ITOMO File | Installed | Production | File Server | N/A | ITOMO File Server | ITOMO File Server | Prod | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA01026 | FBA01026.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 4 | 8192 | 8026241 | 7908604 | 10.30.137.222 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | [8 empty] | Yes
FBA01027 |  |  | x | ON |  | B2B File Server Prod | IBM B2Bi | Installed | Production | File Server | TSA | B2B File Server Prod | B2B File Server Prod | Prod | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.1.el8uek.x86_64) | 2 | 8192 | 725101 | 648884 | 10.30.134.81 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | Yes
FBA01028 |  |  | x | Decommissioned |  |  |  | Installed | STAGING | File Server | N/A | Not Found | 0 | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  | 10.20.120.48 |  |  |  |  | N/A | N/A | No Migration |  |  | Win2022 10.0.20348.2527 (21H2) |  |  |  |  | 10.20.120.48 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02001 |  |  | x | Reviewed with Omar - no concerns; Reviewed and no further concerns - jdeltoro 5/16 | N/A | HP Service Manager - Prod | HP Service Manager | Installed | Production | Applications | TSA | HP Service Manager - Prod | HP Service Manager - Prod | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Alejandro Alvear | FBA02001 | FBA02001.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 120939 | 120939 | 10.30.137.41 |  |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02014 | Yes |  | x | Decommissioned |  | Radius Server | Radius Server | Disposed/Retired | OFF | Monitoring | N/A | Radius Server | Radius Server | Decommissioned | OFF | No | Completed |  |  |  | Yes | FBA02014 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Win2008 6.0.6003 |  |  |  |  | 10.30.137.32 | [10 empty] | No CPU/RAM Info Found
FBA02028 | [5 empty] | ADManager | ADManager | Installed | Production | Security | N/A | ADManager 7.2 | ADManager | Prod | Production | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02028 | FBA02028.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 4096 | 260183 | 260183 | 10.30.137.110 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8 | [6 empty] | No
FBA02031 | [5 empty] | OnBase File Transfer Report Appl Server | Onbase | Installed | Production | Applications | TSA | OnBase File Transfer Report Appl Server | OnBase File Transfer Report Appl Server | Prod | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02031 |  |  |  | MR1130 | Cloud | Milestone 3 |  | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 10240 | 1546402 | 826788 | 10.30.148.200 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02031-New | [5 empty] | OnBase File Transfer Report Appl Server - replacement for FBA02031 | Onbase | No Match | No Match | No Match | TSA | Not Found | OnBase File Transfer Report Appl Server - replacement for FBA02031 | Decommissioned |  | No | Decommissioned |  |  |  | No |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | [5 empty] | Cloud | Milestone 3 |  | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02037 | [5 empty] | Credit Card Portfolio Acquisition Tsys APPRO Inter | Credit Card Portfolio Acquisition Tsys APPRO Inter | Installed | Production | Applications | TSA | Credit Card Portfolio Acquisition Tsys APPRO Inter (Tsys Splitter and ADM service) | Credit Card Portfolio Acquisition Tsys APPRO Inter | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Alejandro Baer |  | Suzzane Seda/Eric Lopez | FBA02037 | FBA02037.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2008R2 6.1.7601 | 4 | 4096 | 239705 | 200969 | 10.30.137.85 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02040 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | New JIRA UAT | New JIRA | Disposed/Retired | OFF | Applications | N/A | New JIRA UAT | New JIRA UAT | Decommissioned | UAT | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 4 | 6144 | 88148 | 86888 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8
FBA02041 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 2048 | 43089 | 37018 | [11 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FBA02045 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 4096 | 65616 | 65616 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA02046 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | Xpress server - UIT | Xpress | Installed | Development | Utilities | TSA | Xpress server - UIT | Xpress server - UIT | Dev | Development | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn |  | 2 | 16384 | 67666 | 63637 | 10.30.140.136 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.136 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_001 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02047 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | Xpress 4.2 Server DEV - Used for TPSS Training | Xpress | Installed | UIT | Database | TSA | Xpress 4.2 Server DEV | Xpress 4.2 Server DEV | UIT | UIT | No | Completed |  |  |  | Yes |  | No |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 1 | 16384 | 57438 | 56499 | 10.30.140.137 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.137 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_002 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG | Standard Dsv6 Family vCPUs | Standard D4s_v6 |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02048 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | Xpress 4.2 Server, TPSS DEV | Xpress | Installed | Development | Database | TSA | Xpress 4.2 Server DEV | Xpress 4.2 Server DEV | Dev | Development | No | In Progress |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn |  | 3 | 24576 | 157779 | 151910 | 10.30.140.138 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.138 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_001 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02049 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | TPSS UAT | TPSS | Installed | UAT | Database | TSA | Xpress 4.2 Server UAT | Xpress 4.2 Server UAT | UAT | UAT | No | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 1 | 1024 | 42065 | 41450 | 10.30.140.139 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.139 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_002 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02050 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | Xpress 4.2 Server UAT | Xpress | Installed | UAT | Database | TSA | Xpress 4.2 Server UAT | Xpress 4.2 Server UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.315.5.el8uek.x86_64) | 4 | 4096 | 157797 | 81768 | 10.30.140.132 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.132 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_001 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02051 | [5 empty] | TIM Production Server | TIMuction | Disposed/Retired | OFF | Monitoring | N/A | TIM Production Server | TIM Production Server | Decommissioned | OFF | No | Completed |  |  |  | No | FBA02051 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02052 | [5 empty] | Xpress 4.2 Server | Xpress | Installed | Production | Database | TSA | Xpress 4.2 Server | Xpress 4.2 Server | Prod | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 4096 | 249946 | 122102 | 10.30.134.240 | 255.255.255.0 |  |  | 10.100.134.240 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02052temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBA02052temp | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) |  |  |  |  | 10.30.134.139 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA02053 | [5 empty] | Xpress 4.2 Server | Xpress | Installed | Production | Database | TSA | Xpress 4.2 Server | Xpress 4.2 Server | Prod | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 4096 | 249948 | 122604 | 10.30.134.239 | 255.255.255.0 |  |  | 10.100.134.239 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA02053temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBA02053temp | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) |  |  |  |  | 10.30.134.140 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FBA02057 | [5 empty] | Xena Server RedHat Enterprice 6.2 | XenaRedHat Enterprice 6.2 | Disposed/Retired | OFF | Applications | N/A | Xena Server RedHat Enterprice 6.2 | Xena Server RedHat Enterprice 6.2 | Decommissioned | OFF | No | Completed |  |  |  | No | FBA02057 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02058 | [5 empty] | E3 Application | E3 Application | Installed | Production | Applications | N/A | E3 Application Server PROD | E3 Application |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02058 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.135 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02059 | [5 empty] | E3 Doc Server Prod | E3 Doc | Installed | Production | Applications | N/A | E3 Doc Server PROD (Win2008R2 6.1.7601) | E3 Doc Server Prod |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02059 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.137 | [20 empty] | No
FBA02061 | [5 empty] | Data Center & Inf Sec Sharepoint | Data Center & Inf Sec Sharepoint | Installed | Production | Applications | N/A | Data Center & Inf Sec Sharepoint | Data Center & Inf Sec Sharepoint |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA02061 | fba02061.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012 6.2.9200 | 6 | 8192 | 213117 | 213117 | 10.30.137.94 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02063 | [5 empty] | TPSS Server | TPSS | Installed | Production | Applications | TSA | TPSS Server | TPSS Server | Prod | Production | No | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  |  | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 16384 | 57428 | 57428 | 10.30.134.151 | 255.255.255.0 |  |  | 10.100.134.151 | [16 empty] | Yes
FBA02064 | [5 empty] | TPSS Server | TPSS | Installed | Production | Applications | TSA | TPSS Server | TPSS Server | Prod | Production | No | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  |  | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 16384 | 57428 | 57428 | 10.30.134.152 | 255.255.255.0 |  |  | 10.100.134.152 | [16 empty] | Yes
FBA02065 | [5 empty] | Linux NTP Server | Linux NTP | Disposed/Retired | OFF | Security | N/A | Linux NTP Server | Linux NTP Server | Decommissioned | Production | No | Decommissioned |  |  |  | No | FBA02065 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 67672 | 67672 | [21 empty] | Yes
FBA02068 |  |  |  | Confirmed with Rafi that this will be in Milestone 3? - jdeltoro 5/9 |  | Remote Desktop Licencing Server | Remote Desktop Licencing | Installed | Production | Utilities | N/A | Remote Desktop Licencing Server | Remote Desktop Licencing Server | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago (FIS) | FBA02068 | FBA02068.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 4096 | 106599 | 106599 | 10.30.137.98 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02069 |  |  |  | To be decommissioned per Edgardo - jdeltoro 5/13 |  | CA Authority Server Lic. Server | CA Authority Lic. | Installed | OFF | Utilities | N/A | CA Authority Server Lic. Server | CA Authority Server Lic. Server |  | OFF | No | Pending |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 106625 | 106625 | 10.30.137.99 | 255.255.255.0 | [19 empty] | Yes
FBA02073-NEW | [5 empty] | TRANE Application - New Server | TRANE Application - New | Installed | Production | Applications | N/A | TRANE Application - New Server | TRANE Application - New Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02073-NEW | FBA02073-NEW.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 127076 | 127076 | 10.30.137.185 | [20 empty] | Yes
FBA02075 |  |  | x | Follow up |  | E3 Application Server UAT | E3 Application | Disposed/Retired | OFF | Applications | N/A | E3 Application Server UAT | E3 Application Server UAT | Decommissioned | OFF | Yes | Decommissioned |  |  |  | No | FBA02075 | No |  | N/A |  | N/A |  | FBA08119.firstbank.local |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.140.152
FBA02076 |  |  | x | Follow up |  | E3 Doc Server UAT | E3 Doc | Disposed/Retired | OFF | Applications | N/A | E3 Doc Server UAT | E3 Doc Server UAT | Decommissioned | OFF | Yes | Decommissioned |  |  |  | No | FBA02076 | No |  | N/A |  | N/A |  | FBA02377.firstbank.local |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.140.154
FBA02080 |  |  | x | Follow up - Historical Data |  | Mortgageware | Mortgageware | Installed | Production | Applications | Waldemar Velez | Mortgage Ware | Mortageware | Prod | Production | Yes | Pending |  |  |  | Yes |  | No |  | Luzmarie Velez |  | Waldemar Velez |  |  |  | Mortgageware | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2008 6.0.6003 | 1 | 2048 | 150609 | 150609 | 10.30.141.97 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02091 |  |  |  | Follow up with Lucy, Shela and Vendor - C & R Software (used to be FICO); no concerns - jdeltoro 5/16; updated CMDB status and environment per Angel - jdeltoro 11/10 | N/A | DebtManager Test | DebtManager | Installed | UIT | Applications | Sheila Ponte | DebtManager Test | DebtManager Test | UIT | UIT | Yes | TBD |  |  |  | Yes | FBA02091 | Yes |  | Santitos Rivas |  | Geraldo Reyes | FBA02091 | FBA02091.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 408757 | 119783 | 10.30.140.75 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02097 | [5 empty] | ABIS Workstation - Human Resources - Win 7 | ABIS Workstation - Human Resources - Win 7 | Disposed/Retired | OFF | Applications | N/A | ABIS Workstation - Human Resources - Win 7 | ABIS Workstation - Human Resources - Win 7 | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02097 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8
FBA02106 |  |  | x | Per Omar no migrate - jdeltoro 5/13 |  | Oracle OCI Agent 1 | Oracle OCI Agent 1 | Installed | UAT | Applications | N/A | Oracle OCI Agent 1 | Oracle OCI Agent 1 | UAT | UAT | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208999 | 27599 | 10.30.140.87 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8 | [6 empty] | No
FBA02107 |  |  | x | Per Omar no migrate - jdeltoro 5/13 |  | Oracle OCI Agent 1 | Oracle OCI Agent 1 | Installed | UAT | Applications | N/A | Oracle OCI Agent 2 | Oracle OCI Agent 1 | UAT | UAT | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208981 | 28894 | 10.30.140.88 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8 | [6 empty] | No
FBA02111 |  |  |  | Reviewed with Omar and updated database information. No concerns - jdeltoro 5/22 | N/A | Service Manager UAT | HP Service Manager | Installed | UAT | Applications | TSA | HP Service Manager UAT | Service Manager UAT | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Alejandro Alvear | FBA02111 | FBA02111.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 1 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 106602 | 95864 | 10.30.140.35 | 255.255.255.0 | 10.30.140.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
fba02113 |  |  |  | Will be decommissioned - replaced by FBA02408 |  | B2Bi Development Server | B2Bielopment | Disposed/Retired | OFF | Applications | Miguel Mejias/Luis Arvelo | B2Bi Development Server | B2Bi Development Server | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA02113 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 6144 | 313449 | 212449 | 10.30.140.74 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
fba02114 |  |  |  | Will be decommissioned - replaced by FBA02407 |  | B2Bi Sterling Control Center Development Server | B2Bi Sterling Control Centerelopment | Disposed/Retired | OFF | Applications | Miguel Mejias/Luis Arvelo | B2Bi Sterling Control Center Development Server | B2Bi Sterling Control Center Development Server | Decommissioned | UAT | No | Decommissioned |  |  |  | Yes | FBA02114 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.79.2.el7uek.x86_64) | 2 | 8192 | 110760 | 58942 | 10.30.140.73 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
fba02115 |  |  |  | Will be decommissioned - replaced by FBA02406 |  | Sterling Control Center Development Server (LINUX) PROD | Sterling Control Center | Installed | Production | Applications | TSA | Sterling Control Center Development Server (LINUX) PROD | Sterling Control Center Development Server (LINUX) PROD | Prod | Production | No | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 | TBD | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.105.1.0.1.el7.x86_64) | 4 | 10240 | 855196 | 855196 | 10.30.134.15 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
fba02116 |  |  |  | Decommissioned per Rafi - jdeltoro 5/9 |  | Sterling Control Center B2Bi (PROD(LINUX) PROD | Sterling Control Center B2Bi ((LINUX) | Disposed/Retired | OFF | Applications | N/A | Sterling Control Center B2Bi (PROD(LINUX) PROD | Sterling Control Center B2Bi (PROD(LINUX) PROD | Decommissioned | Production | No | Decommissioned |  |  |  | Yes | FBA02116 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.31.1.el7.x86_64) | 2 | 16384 | 118891 | 60583 | 10.30.134.16 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16
FBA02117 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | B2Bi Development Server (LINUX)COB | B2Bielopment(LINUX)COB | Disposed/Retired | OFF | Applications | Miguel Mejias/Luis Arvelo | B2Bi Development Server (LINUX)COB | B2Bi Development Server (LINUX)COB | Decommissioned | Contingency | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  | poweredOff | [16 empty] | No CPU/RAM Info Found
fba02118 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Sterling Control Center Development Server (LINUX) COB | Sterling Control Centerelopment(LINUX) COB | Disposed/Retired | OFF | Applications | N/A | Sterling Control Center Development Server (LINUX) COB | Sterling Control Center Development Server (LINUX) COB | Decommissioned | Contingency | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.105.1.0.1.el7.x86_64) | 2 | 8192 | 263607 | 75911 | 10.19.137.18 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
FBA02120 | [5 empty] | Intranet SharePoint - APPL | Intranet SharePoint - APPL | Installed | Production | Applications | N/A | Intranet SharePoint - APPL | Intranet SharePoint - APPL |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA02120 | FBA02120.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 12288 | 370797 | 370797 | 10.30.137.75 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02121 | [5 empty] | APPRO - Doc Manager - PCI CDE | APPRO | Installed | Production | Applications | TSA | APPRO - Doc Manager - PCI CDE | APPRO - Doc Manager - PCI CDE | Prod | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02121 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 90575 | 90575 | 10.30.148.82 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02122 | [5 empty] | APPRO - ALEX - PCI - PCI-CDE | APPRO | Installed | Production | Applications | TSA | APPRO - ALEX - PCI - PCI-CDE | APPRO - ALEX - PCI - PCI-CDE | Prod | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02122 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 2 | 8192 | 146735 | 146735 | 10.30.148.79 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | Yes
FBA02123 | [5 empty] | APPRO - RISK - PCI | APPRO | Installed | Production | Applications | TSA | APPRO - RISK - PCI | APPRO - RISK - PCI | Prod | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02123 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 95575 | 95575 | 10.30.148.80 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02124 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Encompass 360 | Encompass | Disposed/Retired | OFF | Applications | Mortgage Sysytems | Encompass 360 | Encompass 360 | Decommissioned | OFF | No | Pending |  |  |  | No | FBA02124 | Yes |  | Luzmarie Velez |  | Waldemar Velez |  |  |  | Encompass |  | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02126 | Yes |  |  |  |  | Intranet SharePoint APPS UAT | Intranet SharePoint APPS | Available | OFF | Applications | N/A | Intranet SharePoint APPS UAT | Intranet SharePoint APPS UAT |  | OFF | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA02127 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Intranet SharePoint APPL UAT | Intranet SharePoint APPL | Disposed/Retired | OFF | Applications | N/A | Intranet SharePoint APPL UAT | Intranet SharePoint APPL UAT | Decommissioned | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA02127 | FBA02127.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2012R2 6.3.9600 | 4 | 8192 | 284793 | 284793 | 10.30.140.244 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8
FBA02128 | Yes |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | HPE Testing Management System | HPEing Management System | Disposed/Retired | OFF | Monitoring | N/A | HPE Testing Management System | HPE Testing Management System | Decommissioned | OFF | No | Pending |  |  |  | No | FBA02128 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02129 | [5 empty] | Digital Banking - Application - UIT | Digital Banking | Installed | Development | Applications | N/A | Digital Banking - Application - UIT | Digital Banking - Application - UIT | Dev | Development | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02129 | FBA02129.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 4 | 16384 | 221347 | 155712 | 10.30.140.53 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02130 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; jdeltoro 5/9 |  | VARONIS PROBE DP SERVER | Varonis | Installed | Production | Utilities | N/A | VARONIS PROBE DP SERVER | VARONIS PROBE DP SERVER | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo | FBA02130 | FBA02130.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 1210723 | 1210723 | 10.30.137.42 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02131 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; jdeltoro 5/9 |  | VARONIS COLLECTOR 01 | Varonis | Installed | Production | Utilities | N/A | VARONIS COLLECTOR 01 | VARONIS COLLECTOR 01 | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo | FBA02131 | FBA02131.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 344340 | 344340 | 10.30.137.43 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02132 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; jdeltoro 5/9 |  | VARONIS COLLECTOR 02 | Varonis | Installed | Production | Utilities | N/A | VARONIS COLLECTOR 02 | VARONIS COLLECTOR 02 | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo | FBA02132 | FBA02132.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 344183 | 344183 | 10.30.137.44 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02133 | [5 empty] | Digital Banking - Source Code Escrow | Digital Banking | Installed | Development | Applications | N/A | Digital Banking - Source Code Escrow | Digital Banking - Source Code Escrow | Dev | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02133 |  |  | Digital Banking Source Code Escrow | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213101 | 213101 | 10.30.140.78 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02134 | [5 empty] | Digital Banking - Application Server - UAT | Digital Banking | Installed | UAT | Applications | N/A | Digital Banking - Application Server - UAT | Digital Banking - Application Server - UAT | UAT | UAT | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02134 | FBA02134.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221333 | 186767 | 10.30.140.19 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02135 |  |  |  | Follow up with Omar; UIT and UAT DB's are on Shared Physical SQL Server FB65030 and FB65031; Gustavo Rodriguez - jdeltoro 5/8 |  | Data Provisioning - Reporting Services | Data Provisioning | Installed | Production | Applications | CDO | Data Provisioning - Reporting Services | Data Provisioning - Reporting Services | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez | FBA02135 | FBA02135.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 311387 | 311387 | 10.30.137.199 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02136 |  |  |  | Follow up with Omar; UIT and UAT DB's are on Shared Physical SQL Server FB65030 and FB65031; Gustavo Rodriguez - jdeltoro 5/8 |  | Data Provisioning - Analysis Services | Data Provisioning | Installed | Production | Applications | CDO | Data Provisioning - Analysis Services | Data Provisioning - Analysis Services | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez | FBA02136 | FBA02136.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 311389 | 311389 | 10.30.137.200 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02137 |  |  |  | Follow up with Omar; UIT and UAT DB's are on Shared Physical SQL Server FB65030 and FB65031; Gustavo Rodriguez - jdeltoro 5/8 |  | Data Provisioning - Integration Services | Data Provisioning | Installed | Production | Applications | CDO | Data Provisioning - Integration Services | Data Provisioning - Integration Services | Prod | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez | FBA02137 | FBA02137.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 362587 | 362587 | 10.30.137.201 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02138 |  |  | x | Follow up with Rafi - jdeltoro 5/9 |  | Ricoh Hard Drive Encryption | Ricoh Hard Drive Encryption | Installed | Production | Security | N/A | Ricoh Hard Drive Encryption | Ricoh Hard Drive Encryption | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02138 | FBA02138.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 4096 | 157793 | 157793 | 10.30.137.59 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02139 | [5 empty] | EUDA Lifetime Server Outsystem | OutSystem | Installed | Production | Applications | Multiple EUDA Users | EUDA Lifetime Server | EUDA Lifetime Server | Prod | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Alberto Jimenez |  | Guillermo Hernandez | FBA02139 | FBA02139.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 8192 | 595653 | 256972 | 10.30.137.19 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | Yes
FBA02140 |  |  |  | FBA03085 is a database dependency |  | Outsystem (EUDA) Test Server | Outsystem | Installed | UAT | Applications | Multiple EUDA Users | Outsystem (EUDA) Test Server | Outsystem (EUDA) Test Server | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Alberto Jimenez |  | Guillermo Hernandez | FBA02140 | FBA02140.firstbank.local |  | Outsystem EUDA | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 4 | 8192 | 562132 | 393158 | 10.30.140.46 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02141 |  |  |  | FBA03085 is a database dependency |  | Outsystem (EUDA) DEV Server | Outsystem | Installed | Development | Applications | Multiple EUDA Users | Outsystem (EUDA) DEV Server | Outsystem (EUDA) DEV Server | Dev | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Alberto Jimenez |  | Guillermo Hernandez | FBA02141 | FBA02141.firstbank.local |  | Outsystem EUDA | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 4 | 32768 | 399649 | 241257 | 10.30.140.47 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | No
FBA02142 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS AQM Server UAT | FEIS | Installed | UAT | Applications | N/A | FEIS AQM Server UAT | FEIS AQM Server UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.72.2.el7uek.x86_64) | 2 | 8192 | 59547 | 59547 | 10.30.140.90 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02143 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 1 UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Application Server 1 UAT | FEIS Application Server 1 UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.60.1.el7uek.x86_64) | 4 | 16384 | 88296 | 88296 | 10.30.140.91 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02144 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 2 UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Application Server 2 UAT | FEIS Application Server 2 UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.314.6.2.el7uek.x86_64) | 4 | 16384 | 88272 | 88272 | 10.30.140.92 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02145 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 3 UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Application Server 3 UAT | FEIS Application Server 3 UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.314.6.2.el7uek.x86_64) | 4 | 16384 | 88273 | 88273 | 10.30.140.93 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02146 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 4 UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Application Server 4 UAT | FEIS Application Server 4 UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.88.1.0.1.el7.x86_64) | 4 | 16384 | 88282 | 88282 | 10.30.140.97 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02147 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Log Server UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Log Server UAT | FEIS Log Server UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.302.7.2.2.el7uek.x86_64) | 2 | 8192 | 100471 | 100471 | 10.30.140.98 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02148 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Management Server UAT | FEIS | Installed | UAT | Applications | N/A | FEIS Management Server UAT | FEIS Management Server UAT | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.54.6.el7uek.x86_64) | 2 | 4096 | 55396 | 55396 | 10.30.140.99 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02149 |  |  | x |  |  | FEIS AMQ Server PROD | FEIS | Installed | Production | Applications | N/A | FEIS AMQ Server PROD | FEIS AMQ Server PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02149 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.330.7.1.el7uek.x86_64) | 6 | 8192 | 90239 | 90239 | 10.30.134.181 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02150 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 1 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 1 PROD | FEIS Application Server 1 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02150 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.330.7.1.el7uek.x86_64) | 4 | 65536 | 157953 | 157953 | 10.30.134.113 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02151 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 2 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 2 PROD | FEIS Application Server 2 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02151 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.324.5.3.el7uek.x86_64) | 4 | 65536 | 158462 | 158462 | 10.30.134.164 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02152 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 3 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 3 PROD | FEIS Application Server 3 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02152 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.84.2.el7uek.x86_64) | 4 | 65536 | 158367 | 158367 | 10.30.134.165 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02153 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 4 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 4 PROD | FEIS Application Server 4 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02153 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.84.2.el7uek.x86_64) | 4 | 65536 | 158481 | 158481 | 10.30.134.166 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02154 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 5 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 5 PROD | FEIS Application Server 5 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02154 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.330.7.1.el7uek.x86_64) | 4 | 65536 | 209651 | 164818 | 10.30.134.167 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02155 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Application Server 6 PROD | FEIS | Installed | Production | Applications | N/A | FEIS Application Server 6 PROD | FEIS Application Server 6 PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02155 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.53.5.2.el7uek.x86_64) | 4 | 65536 | 218013 | 169032 | 10.30.134.168 | [10 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | Yes
FBA02156 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Log server PROD | FEIS | Installed | Production | Applications | N/A | FEIS Log server PROD | FEIS Log server PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02156 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.84.2.el7uek.x86_64) | 4 | 16384 | 139533 | 139533 | 10.30.134.169 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02157 |  |  | x | OpenShift, SpringBoot, Kubernetes |  | FEIS Management Server PROD | FEIS | Installed | Production | Applications | N/A | FEIS Management Server PROD | FEIS Management Server PROD |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02157 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.330.7.1.el7uek.x86_64) | 4 | 8192 | 39067 | 39067 | 10.30.134.170 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02159 |  |  |  | FBA03089 is a database dependency |  | EUDA Production Server Outsystem | OutSystem | Installed | Production | Applications | Multiple EUDA Users | EUDA Production Server | EUDA Production Server |  | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | Alberto Jimenez |  | Guillermo Hernandez | FBA02159 |  | FBA02160 |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 470983 | 237095 | 10.30.148.20 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02160 | [5 empty] | CUC Application Server - UIT | D1 | Installed | UIT | Applications | TSA | CUC Application Server - UIT | CUC Application Server - UIT |  | UIT | No | Completed |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  | FBA02160 |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 12288 | 114880 | 114880 | 10.30.140.124 |  |  |  | 10.100.140.124 | [16 empty] | No
FBA02161 | [5 empty] | CUG Application Server - UIT | D1 | Installed | UIT | Applications | TSA | CUG Application Server - UIT | CUG Application Server - UIT |  | UIT | No | Completed |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  | FBA02161 |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.332.5.2.el7uek.x86_64) | 4 | 8192 | 110699 | 110699 | 10.30.140.125 |  |  |  | 10.100.140.125 | [16 empty] | No
FBA02162 | [5 empty] | Xpress Application Server - UIT | Xpress | Installed | UIT | Applications | TSA | Xpress Application Server - UIT | Xpress Application Server - UIT |  | UIT | No | TBD |  | Yes |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  | FBA02162 |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.321.4.el8uek.x86_64) | 4 | 8192 | 254064 | 107487 | 10.30.140.126 |  |  |  | 10.100.140.126 | [16 empty] | No
FBA02167 | [5 empty] | Xpress Development Application Server - UIT | Xpress | Installed | Development | Applications | TSA | Xpress Development Application Server - UIT | Xpress Development Application Server - UIT |  | Development | No | TBD |  | Yes |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  | FBA02167 |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) | 4 | 4096 | 249960 | 120316 | 10.30.140.147 |  |  |  | 10.100.140.147 | [16 empty] | No
FBA02168 | [5 empty] | Xpress CUC development Application Server - UIT | Xpress | Installed | Development | Applications | TSA | Xpress CUC development Application Server - UIT | Xpress CUC development Application Server - UIT |  | Development | No | TBD |  | Yes |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  | FBA02168 |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.321.4.el8uek.x86_64) | 4 | 8192 | 254096 | 106934 | 10.30.140.148 |  |  |  | 10.100.140.148 | [16 empty] | No
FBA02169 | [5 empty] | FEIS Development Server (Digital ONE) - UIT | FEIS | Installed | Development | Applications | N/A | FEIS Development Server (Digital ONE) - UIT | FEIS Development Server (Digital ONE) - UIT |  | Development | No | TBD |  | Yes |  | No |  | Yes |  | N/A |  | N/A |  |  | FBA02169 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn |  | 4 | 16384 | 77961 | 77961 | 10.30.140.229 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02170 | [5 empty] | FEIS Development Server (Digital ONE) | FEIS | Installed | Development | Applications | N/A | FEIS Development Server (Digital ONE) | FEIS Development Server (Digital ONE) |  | STAGING | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02170 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.323.8.1.el7uek.x86_64) | 4 | 16384 | 78056 | 78056 | 10.30.140.9 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02171 | [5 empty] | FEIS Development Server (Digital ONE) - UIT | FEIS | Installed | UIT | Applications | N/A | FEIS Development Server (Digital ONE) - UIT | FEIS Development Server (Digital ONE) - UIT |  | UIT | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02171 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.78.4.1.el7uek.x86_64) | 4 | 16384 | 77967 | 77967 | 10.30.140.13 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02172 | [5 empty] | FEIS Development Server (Digital ONE) | FEIS | Installed | Development | Applications | N/A | FEIS Development Server (Digital ONE) | FEIS Development Server (Digital ONE) |  | STAGING | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02172 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.50.2.el7uek.x86_64) | 4 | 16384 | 78096 | 78096 | 10.30.140.22 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02173 | [5 empty] | Digital One Branch Server (CUC,CUG,SQL) | Digital One Branch(CUC,CUG,SQL) | Installed | UAT | Applications | N/A | Digital One Branch Server (CUC,CUG,SQL) | Digital One Branch Server (CUC,CUG,SQL) |  | UAT | Yes | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | FBA02173 | fba02173.firstbank.local | FBA02173 |  | MR1130 | FIS | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 631005 | 94459 | 10.30.140.180 | [20 empty] | No
FBA02174 | [5 empty] | SIT CUG Application Server - UIT | D1 | Installed | UIT | Applications | TSA | SIT CUG Application Server - UIT | SIT CUG Application Server - UIT |  | UIT | No | Completed |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.332.5.2.el7uek.x86_64) | 4 | 8192 | 110692 | 110692 | 10.30.140.163 |  |  |  | 10.100.140.163 | [16 empty] | No
FBA02175 | [5 empty] | SIT CUC Application Server - UIT | D1 | Installed | UIT | Applications | TSA | SIT CUC Application Server - UIT | SIT CUC Application Server - UIT |  | UIT | No | Completed |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.332.5.2.el7uek.x86_64) | 4 | 12288 | 114771 | 114771 | 10.30.140.168 |  |  |  | 10.100.140.168 | [16 empty] | No
FBA02176 | [5 empty] | Digital Banking - Application 1 - PROD | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 1 - Pilot | Digital Banking - Application 1 - PROD |  | Production | Yes | In Progress |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | FBA02176 | FBA02176.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221336 | 153206 | 10.30.137.172 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02177 | [5 empty] | Digital Banking - Application 2 - PROD | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 2 - Pilot | Digital Banking - Application 2 - PROD |  | Production | Yes | In Progress |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | FBA02177 | FBA02177.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221346 | 145472 | 10.30.137.173 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02178 | [5 empty] | Digital Banking - Application 3 - PROD | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 3 - Pilot | Digital Banking - Application 3 - PROD |  | Production | Yes | In Progress |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | FBA02178 | FBA02178.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 351135 | 163285 | 10.30.137.174 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02180 | [5 empty] | Xpress SIT Application Server (D1) - UIT | Xpress | Installed | UIT | Applications | TSA | Xpress SIT Application Server (D1) - UIT | Xpress SIT Application Server (D1) - UIT |  | UIT | No | TBD |  | Yes |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.320.7.el8uek.x86_64) | 2 | 8192 | 254094 | 106704 | 10.30.140.76 |  |  |  | 10.100.140.76 | [16 empty] | No
FBA02181 | [5 empty] | FEIS Development Server | FEIS | Installed | Development | Applications | N/A | FEIS Development Server | FEIS Development Server |  | Development | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02181 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.313.6.el7uek.x86_64) | 4 | 16384 | 78007 | 78007 | 10.30.140.72 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02183 | [5 empty] | BSNEE - Branch Digital Screens Server | BSNEE | Installed | Production | Applications | Marketing | BSNEE - Branch Digital Screens Server | BSNEE - Branch Digital Screens Server |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Cristina Rodriguez |  | Cristina Rodriguez /Felix Otero (felix@sbtechpr.com) / Tais Laborde |  |  |  | BSNEE | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 16384 | 1218657 | 1218657 | 10.30.163.11 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02194 |  |  |  | Eric reported back that FBA02194 was replaced by FBA02378 |  | Xamine Dev Server - Zena Scheduler | Xamine | Installed | Development | Applications | TSA/CDO | Xamine Dev Server | Xamine Dev Server |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | FBA02194 | FBA02194.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 334217 | 147010 | 10.30.140.38 | 255.255.255.0 | [19 empty] | No
fba02195 |  |  | x | Follow up with Milton/MSS |  | Tenable Nessus Security Center | Tenable Nessus Security Center | Installed | Production | Applications | CSO | Tenable Nessus Security Center | Tenable Nessus Security Center |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.331.7.el7uek.x86_64) | 4 | 16384 | 979072 | 930904 | 10.30.136.252 | 255.255.255.0 | [19 empty] | No
FBA02196 |  |  | x | Follow up with Milton/MSS |  | Nexpose Scan Engine | Nexpose Scan Engine | Installed | Production | Applications | N/A | Nexpose Scan Engine | Nexpose Scan Engine |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02196 | FBA02196.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 135435 | 135435 | 10.30.136.57 | 255.255.255.0 | [19 empty] | No
FBA02197 | [5 empty] | D1 SPE/PROD - Application (Java Server #1) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Java Server #1) | D1 SPE/PROD - Application (Java Server #1) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 4 | 12288 | 191788 | 191788 | 10.30.148.21 |  |  |  | 10.100.148.21 | [16 empty] | No
FBA02197temp |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.329.3.1.el7uek.x86_64) |  |  |  |  | 10.30.134.235
FBA02198 | [5 empty] | D1 SPE/PROD - Application (Java Server #2) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Java Server #2) | D1 SPE/PROD - Application (Java Server #2) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 4 | 12288 | 191719 | 191719 | 10.30.148.22 |  |  |  | 10.100.148.22 | [16 empty] | No
FBA02199 | [5 empty] | D1 SPE/PROD - Application (Java Server #3) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Java Server #3) | D1 SPE/PROD - Application (Java Server #3) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 4 | 12288 | 191688 | 191688 | 10.30.148.23 |  |  |  | 10.100.148.23 | [16 empty] | No
FBA02200 | [5 empty] | D1 SPE/PROD - Application (Java Server #4) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Java Server #4) | D1 SPE/PROD - Application (Java Server #4) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 12288 | 217254 | 217254 | 10.30.148.24 |  |  |  | 10.100.148.24 | [16 empty] | No
FBA02201 | [5 empty] | D1 SPE/PROD - Application (JBoss Server #1) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (JBoss Server #1) | D1 SPE/PROD - Application (JBoss Server #1) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 8 | 16384 | 241955 | 241955 | 10.30.148.25 |  |  |  | 10.100.148.25 | [16 empty] | No
FBA02202 | [5 empty] | D1 SPE/PROD - Application (JBoss Server #2) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (JBoss Server #2) | D1 SPE/PROD - Application (JBoss Server #2) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 8 | 16384 | 190661 | 190661 | 10.30.148.26 |  |  |  | 10.100.148.26 | [16 empty] | No
FBA02202temp |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 8 | 16384 | 191058 | 86336 | 10.30.134.236
FBA02203 | [5 empty] | D1 SPE/PROD - Application (JBoss Server #3) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (JBoss Server #3) | D1 SPE/PROD - Application (JBoss Server #3) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 8 | 16384 | 190821 | 190821 | 10.30.148.27 |  |  |  | 10.100.148.27 | [16 empty] | No
FBA02204 | [5 empty] | D1 SPE/PROD - Application (JBoss Server #4) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (JBoss Server #4) | D1 SPE/PROD - Application (JBoss Server #4) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.325.5.el7uek.x86_64) | 8 | 16384 | 190742 | 190742 | 10.30.148.28 |  |  |  | 10.100.148.28 | [16 empty] | No
fba02205 | [5 empty] | D1 SPE/PROD - Application (JBoss Server #5) | D1 | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (JBoss Server #5) | D1 SPE/PROD - Application (JBoss Server #5) |  | Production | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 16 | 32768 | 207063 | 122956 | 10.30.148.29 |  |  |  | 10.100.148.29 | [16 empty] | Yes
FBA02206 | [5 empty] | D1 SPE/PROD - Application (Xpress Server #1) | D1 SPE/ - Application (Xpress#1) | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Xpress Server #1) | D1 SPE/PROD - Application (Xpress Server #1) |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.330.7.1.el8uek.x86_64) | 4 | 16384 | 358091 | 189511 | 10.30.148.30 |  |  |  | 10.100.148.30 | [16 empty] | No
FBA02207 |  |  | x | Follow up on D1 |  | SAS | SAS | Installed | Production | Applications | N/A | SAS | SAS |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Edgardo Santiago | FBA02207 | FBA02207.firstbank.local |  | SAS | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 6 | 32768 | 1081864 | 1081864 | 10.30.137.161 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02208 |  |  | x | Used by more than D1 |  | D1 SIT CheckPartner App Server | D1 | Installed | UAT | Applications | TSA | D1 SIT CheckPartner App Server | D1 SIT CheckPartner App Server |  | UAT | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02208 | FBA02208.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 157801 | 94474 | 10.30.140.116 | 255.255.255.0 | [19 empty] | No
FBA02209 |  |  |  | updated CMDB status and environment per Angel - jdeltoro 11/10 |  | D1 SPE/PROD - Application (Xpress Server #2) | D1 SPE/ - Application (Xpress#2) | Installed | Production | Disposed\Retired | TSA | D1 SPE/PROD - Application (Xpress Server #2) | D1 SPE/PROD - Application (Xpress Server #2) |  | Production | No | TBD |  | Yes |  | Yes | FBA02209 | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.330.7.1.el8uek.x86_64) | 4 | 16384 | 262384 | 139534 | 10.30.148.31 |  |  |  | 10.100.148.31 | [16 empty] | No
FBA02210 |  |  |  | updated CMDB status and environment per Angel - jdeltoro 11/10 |  | D1 SPE/PROD - Application (Xpress Server #3) | D1 SPE/ - Application (Xpress#3) | Installed | Production | Disposed\Retired | TSA | D1 SPE/PROD - Application (Xpress Server #3) | D1 SPE/PROD - Application (Xpress Server #3) |  | Production | No | TBD |  | Yes |  | Yes | FBA02210 | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.330.7.1.el8uek.x86_64) | 4 | 16384 | 262369 | 139143 | 10.30.148.32 |  |  |  | 10.100.148.32 | [16 empty] | No
FBA02212 | [5 empty] | D1 SPE/PROD - Application (Xpress Server #4) | D1 SPE/ - Application (Xpress#4) | Installed | Production | Applications | TSA | D1 SPE/PROD - Application (Xpress Server #4) | D1 SPE/PROD - Application (Xpress Server #4) |  | Production | No | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.331.7.el8uek.x86_64) | 4 | 16384 | 262383 | 127065 | 10.30.148.33 |  |  |  | 10.100.148.33 | [16 empty] | No
fba02213 | [5 empty] | REDIS PROD App Server 1 - Digital Banking | Digital Banking | Installed | Production | Applications | N/A | REDIS PROD App Server 1 | REDIS PROD App Server 1 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.330.7.1.el8uek.x86_64) | 4 | 4096 | 208980 | 128253 | 10.30.134.94 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
fba02214 | [5 empty] | REDIS PROD App Server 2 - Digital Banking | Digital Banking | Installed | Production | Applications | N/A | REDIS PROD App Server 2 | REDIS PROD App Server 2 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208980 | 127988 | 10.30.134.95 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
fba02215 | [5 empty] | REDIS PROD App Server 3 - Digital Banking | Digital Banking | Installed | Production | Applications | N/A | REDIS PROD App Server 3 | REDIS PROD App Server 3 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba02215 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208981 | 127847 | 10.30.134.96 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02216 | [5 empty] | D1 SPE\PROD - Application (Item analyze #1) | D1 | Installed | Production | Applications | TSA | D1 SPE\PROD - Application (Item analyze #1) | D1 SPE\PROD - Application (Item analyze #1) |  | Production | Yes | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02216 |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 16384 | 118982 | 118982 | 10.30.148.34 |  |  |  | 10.100.148.34 | [16 empty] | Yes
FBA02217 | [5 empty] | D1 SPE\PROD - Application (Item analyze #2) | D1 | Installed | Production | Applications | TSA | D1 SPE\PROD - Application (Item analyze #2) | D1 SPE\PROD - Application (Item analyze #2) |  | Production | Yes | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02217 |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 16384 | 119456 | 119456 | 10.30.148.35 |  |  |  | 10.100.148.35 | [16 empty] | Yes
FBA02218 | [5 empty] | D1 SPE FEIS (DEV Server) | FEIS | Installed | Development | Applications | N/A | D1 SPE FEIS (DEV Server) | D1 SPE FEIS (DEV Server) |  | Development | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  | FBA02218 |  | MR1130 | Cloud | Milestone 4 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.332.5.2.el7uek.x86_64) | 4 | 8192 | 49241 | 30893 | 10.30.134.100 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02220 | [5 empty] | Profitability & BDI Production File Server - Bancware | Bancware | Installed | Production | Applications | Financial Planning | Profitability & BDI Production Server | Profitability & BDI Production Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA02220 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 12 | 65536 | 741681 | 741681 | 10.30.137.82 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D16s_v6 | 16 | 64 | [6 empty] | Yes
FBA02221 |  |  |  | Per Edgardo this is decommissioned - jdeltoro 5/13 |  | MQ Java Application #1 | MQ Java Application #1 | Disposed/Retired | OFF | Applications | N/A | MQ Java Application #1 | MQ Java Application #1 | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02221 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02222 |  |  |  | Follow up with Eric per Edgardo - jdeltoro 5/13 |  | MQ Java Application #2 | MQ | Installed | Development | Applications | FIS / Open System | MQ Java Application #2 | MQ Java Application #2 |  | Development | No | Pending |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Ana Cruz |  |  |  | TBD | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 8192 | 49238 | 22658 | 10.30.140.23 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02223 |  |  |  | Per Edgardo this is decommissioned - jdeltoro 5/13 |  | MQ IBM Websphere | MQ IBM Websphere | Disposed/Retired | STAGING | Applications | N/A | MQ IBM Websphere | MQ IBM Websphere | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA02223 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [7 empty] | 10.30.140.49 | [10 empty] | No CPU/RAM Info Found
FBA02224 | [5 empty] | Profitability & BDI UAT Server - Bancware | Bancware | Installed | UAT | Applications | Financial Planning | Profitability & BDI UAT Server | Profitability & BDI UAT Server |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA02224 | FBA02224.firstbank.local |  | Bancware |  | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7159 (1607) | 2 | 3072 | 515160 | 464267 | 10.30.140.56 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02226 | [5 empty] | D1 GTS Remote Desktop | D1 | Installed | STAGING | Applications | TSA | D1 GTS Remote Desktop | D1 GTS Remote Desktop |  | STAGING | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02226 | FBA02226.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 90225 | 74818 | 10.30.137.71 |  |  |  | 10.100.137.71 | [16 empty] | No
FBA02227 | Yes |  |  | Decommissioned |  | CLCS APPL UAT Server | CLCS APPL | Disposed/Retired | OFF | Applications | Irma Ramos | CLCS APPL UAT Server | CLCS APPL UAT Server | Decommissioned | OFF | Yes | Decommissioned |  |  |  | Yes | FBA02227 | Yes |  | Sharon Gutierrez |  | Irma Ramos | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 1 | 2048 | 462930 | 115607 | 10.30.140.143 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA02228 | [5 empty] | CLCS APPL ROD Server | CLCS APPL ROD | Disposed/Retired | OFF | Applications | Irma Ramos | CLCS APPL ROD Server | CLCS APPL ROD Server | Decommissioned | OFF | Yes | Decommissioned |  |  |  | Yes | FBA02228 | Yes |  | Sharon Gutierrez |  | Irma Ramos |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.5717 (1607) | 8 | 65536 | 680940 | 680940 | 10.30.137.93 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E8s_v6 | 8 | 64
FBA02229 |  |  | x | Follow up with Milton/MSS |  | Tenable Virtual Appliance 4.8.0 (Nesus) MR1130 | Tenable Virtual Appliance 4.8.0 (Nesus) | Installed | Production | Applications | CSO | Tenable Virtual Appliance 4.8.0 (Nesus) MR1130 | Tenable Virtual Appliance 4.8.0 (Nesus) MR1130 |  | Production | No | Pending |  |  |  | No |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 49265 | 49265 | 10.30.136.6 | 255.255.255.0 | [19 empty] | No
FBA02230 | Yes |  |  |  |  | EUDA Lifetime Outsystems Temp and no longer used | EUDA | No Match | No Match | No Match | N/A | Not Found | EUDA Lifetime |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FBA02231 | Yes |  |  |  |  | EUDA - Outsystems UAT Temp and no longer used | EUDA | No Match | No Match | No Match | N/A | Not Found | EUDA - Outsystems UAT |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FBA02232 | Yes |  |  |  |  | EUDA - Outsystems Development Temp and no longer used | EUDA | No Match | No Match | No Match | N/A | Not Found | EUDA - Outsystems Development |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
FBA02233 | Yes |  |  |  |  | EUDA - Outsystems Production Temp and no longer used | EUDA | No Match | No Match | No Match | N/A | Not Found | EUDA - Outsystems Production |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA02235 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | D1 Onbase WKSOBDocComp 1 | Onbase | Disposed/Retired | OFF | Applications | TSA | D1 Onbase WKSOBDocComp 1 | D1 Onbase WKSOBDocComp 1 | Decommissioned | Production | Yes | Decommissioned |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02235 | FBA02235.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 340286 | 340286 | 10.30.137.22 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32
FBA02236 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | D1 Onbase WKSOBDocComp 2 | Onbase | Disposed/Retired | OFF | Applications | TSA | D1 Onbase Appserver 2 | D1 Onbase WKSOBDocComp 2 | Decommissioned | Production | Yes | Decommissioned |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02236 | FBA02236.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 340283 | 340283 | 10.30.137.73 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32
FBA02237 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | D1 Onbase WKSOBDocComp 1 | Onbase | Disposed/Retired | OFF | Applications | TSA | D1 Onbase WKSOBDocComp 1 | D1 Onbase WKSOBDocComp 1 | Decommissioned | Production | Yes | Decommissioned |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02237 | FBA02237.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 223350 | 223350 | 10.30.137.86 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA02238 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | D1 Onbase AppServer 2 | Onbase | Disposed/Retired | OFF | Applications | TSA | D1 Onbase AppServer 2 | D1 Onbase AppServer 2 | Decommissioned | Production | Yes | Decommissioned |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02238 | FBA02238.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 213111 | 213111 | 10.30.137.95 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA02239 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Report Web PCI | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Report Web Server Prod 1 | Onbase Report Web PCI | Decommissioned | Production | Yes | Decommissioned | Yes |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02239 |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 4 | 32768 | 289124 | 289124 | 10.30.148.50 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32
FBA02240 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Report Web PCI | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Report Web Server Prod 2 | Onbase Report Web PCI | Decommissioned | Production | Yes | Decommissioned | Yes |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02240 |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 4 | 32768 | 289168 | 289168 | 10.30.148.51 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32
FBA02241 |  |  |  | Moved to Vendor Cloud |  | Fimo Jira UAT | Fimo Jira | Installed | UAT | Applications | N/A | Fimo Jira UAT | Fimo Jira UAT |  | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.85.1.el7uek.x86_64) | 4 | 8192 | 622710 | 622710 | 10.30.140.106 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02242 | [5 empty] | FIMO Jira Prod | FIMO Jira | Installed | Production | Applications | N/A | FIMO Jira Prod | FIMO Jira Prod |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.71.3.el7uek.x86_64) | 4 | 16384 | 1116267 | 1116267 | 10.30.134.44 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02245 |  |  | x | Follow up with Milton/MSS |  | Tenable Virtual Appliance 4.8.0 (Nexus) PCI | Tenable Virtual Appliance 4.8.0 (Nexus) | Installed | Production | Monitoring | CSO | Tenable Virtual Appliance 4.8.0 (Nexus) PCI | Tenable Virtual Appliance 4.8.0 (Nexus) PCI |  | Production | No | Pending | Yes |  |  | No |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 49287 | 49287 | 10.30.151.6 | [20 empty] | No
FBA02247 |  |  | x | Follow up with Milton/MSS |  | Tenable Virtual Appliance 4.8.0 (Nexus) COB | Tenable Virtual Appliance 4.8.0 (Nexus) | Installed | STAGING | Monitoring | CSO | D1 Performance monitoring 1 | Tenable Virtual Appliance 4.8.0 (Nexus) COB | UIT | UIT | No | Pending |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 1 | 8192 | 49445 | 49445 | 10.19.137.6 | [20 empty] | No
FBA02248 |  |  | x | Follow up with Milton/MSS |  | Tenable Virtual Appliance 4.8.0 (Nexus) MR1130 | Tenable Virtual Appliance 4.8.0 (Nexus) | Installed | Production | Monitoring | CSO | Tenable Virtual Appliance 4.8.0 (Nexus) MR1130 | Tenable Virtual Appliance 4.8.0 (Nexus) MR1130 |  | Production | No | Pending |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.332.5.2.el7uek.x86_64) | 4 | 16384 | 57665 | 57665 | 10.30.136.7 | 255.255.255.0 | [19 empty] | No
FBA02249 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found | 0 | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 49404 | 49404 | 10.19.151.6
FBA02250 |  |  | x | Follow up with Milton/MSS |  | Tenable Windows 2016 Image | Tenable Windows 2016 Image | Installed | Development | Utilities | CSO | Tenable Windows 2016 Image | Tenable Windows 2016 Image |  | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A | FBA02250 | FBA02250.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 106590 | 106590 | 10.30.140.250 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02252 |  |  | x | Decommissioned per ticket CH25000179097 in CMC meeting - jdeltoro 7/30 |  | Tenable Windows 2012 Image (Tenable Template Hardening Testing Server) | Tenable Windows 2012 Image (Tenable Template Hardeninging ) | Disposed/Retired | OFF | Applications | CSO | Tenable Windows 2012 Image (Tenable Template Hardening Testing Server) | Tenable Windows 2012 Image (Tenable Template Hardening Testing Server) | Decommissioned | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A | FBA02252 | FBA02252.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 161911 | 57928 | 10.30.140.25
FBA02253 |  |  | x | Used by more than D1 |  | D1 Checkpartner Enterprise Prod (CPE) | D1 | Installed | Production | Applications | TSA | D1 Checkpartner Enterprise Prod (CPE) | D1 Checkpartner Enterprise Prod (CPE) |  | Production | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02253 | FBA02253.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 110759 | 110759 | 10.30.137.48 | 255.255.255.0 |  |  | 10.100.137.48 | [16 empty] | Yes
FBA02256 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Xamine Operator Machine (FB56220 Clone) | Xamine | Disposed/Retired | OFF | Applications | TSA/CDO | Xamine Operator Machine (FB56220 Clone) | Xamine Operator Machine (FB56220 Clone) | Decommissioned | OFF | No | Decommissioned |  |  |  | Yes | FBA02256 | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez |  |  |  |  | MR1130 | FIS | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.115 | 255.255.255.0 |  |  | 10.100.137.115
FBA02257 |  |  |  | Databases do require encryption; no concerns for moving in group 4 currently; need to review with vendor |  | APPRO - Doc Manager - UAT\TEST | APPRO | Installed | UAT | Applications | TSA | APPRO - Doc Manager - UAT\TEST | APPRO - Doc Manager - UAT\TEST |  | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02257 | fba02257.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 90315 | 35917 | 10.30.140.155 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02258 |  |  |  | Databases do require encryption; no concerns for moving in group 4 currently; need to review with vendor |  | APPRO - RISK - UAT\TEST | APPRO | Installed | UAT | Applications | TSA | APPRO - RISK - UAT\TEST | APPRO - RISK - UAT\TEST |  | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02258 | FBA02258.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 1 | 1024 | 88148 | 35009 | 10.30.140.156 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02259 |  |  |  | Databases do require encryption; no concerns for moving in group 4 currently; need to review with vendor |  | APPRO - ALEX - UAT\TEST | APPRO | Installed | UAT | Applications | TSA | APPRO - ALEX - UAT\TEST | APPRO - ALEX - UAT\TEST |  | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA02259 | FBA02259.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 1 | 1024 | 118867 | 58441 | 10.30.140.157 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02263 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | UAT Xpress Server 1 - Websphere | Xpress | Installed | UAT | Applications | TSA | Eloan UAT Xpress Server 1 | Eloan UAT Xpress Server 1 | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.327.2.el8uek.x86_64) | 4 | 4096 | 249942 | 143540 | 10.30.140.131 | 255.255.255.0 | 10.30.140.1 | N/A | 10.100.140.131 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | JAX_FBPR_12121_CORE_002 | FBPR-12121¦CORE_AP¦NON-PROD-10.100.140.0_24_EPG |  |  |  |  | N/A | N/A | N/A | N/A | N/A | VADP | No | N/A
FBA02264 |  |  |  | Reviewed with Omar and Eric on 5/22 and no issues. Dependency with FEIS and would require WAN emulation testing to confirm. - jdeltoro 5/22 |  | UAT Xpress Server 2 - Websphere | Xpress | Installed | UAT | Applications | TSA | Eloan UAT Xpress Server 2 | Eloan UAT Xpress Server 2 | UAT | UAT | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | FIS | TBD | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.328.3.el8uek.x86_64) | 4 | 4096 | 249951 | 105435 | 10.30.140.142 | 255.255.255.0 |  |  | 10.100.140.142 | 255.255.255.0 | 100.119.252.194, 100.119.252.195 | 10.100.140.1 | JAX_PROD_Cloud | [12 empty] | No
FBA02265 | [5 empty] | Xamine Operator Machine (FB56218 Clone) | Xamine | Installed | Production | Applications | TSA/CDO | Xamine Operator Machine (FB56218 Clone) | Xamine Operator Machine (FB56218 Clone) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | FBA02265 | FBA02265.firstbank.local |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4644 | 194421 | 194421 | 10.30.137.29 | 255.255.255.0 |  |  | 10.100.137.29 | [16 empty] | Yes
FBA02266 | [5 empty] | Xamine Operator Machine (fb56219 Clone) | Xamine | Installed | Production | Applications | TSA/CDO | Xamine Operator Machine (fb56219 Clone) | Xamine Operator Machine (fb56219 Clone) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | FBA02266 | FBA02266.firstbank.local |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 213132 | 213132 | 10.30.137.33 | 255.255.255.0 |  |  | 10.100.137.33 | [16 empty] | Yes
FBA02267 | [5 empty] | SIT Item Analysis Server ( IAS ) | D1 | Installed | Development | Applications | TSA | SIT Item Analysis Server ( IAS ) | SIT Item Analysis Server ( IAS ) |  | Development | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02267 | FBA02267.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | D1 | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 16384 | 119008 | 54856 | 10.30.140.42 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02269 |  |  | x | Used by more than D1 |  | D1 Checkpartner Enterprise Server (CPE) 2 | D1 | Installed | Production | Applications | TSA | D1 Checkpartner Enterprise Server (CPE) 2 | D1 Checkpartner Enterprise Server (CPE) 2 |  | Production | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA02269 | FBA02269.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 110684 | 110684 | 10.30.137.78 | 255.255.255.0 |  |  | 10.100.137.78 | [16 empty] | Yes
FBA02270 | [5 empty] | D1 Training Xpress | D1 | Installed | UAT | Applications | TSA | D1 Training Xpress | D1 Training Xpress |  | UAT | No | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.320.7.el8uek.x86_64) | 2 | 16384 | 262347 | 117052 | 10.30.140.16 |  |  |  | 10.100.140.16 | [16 empty] | No
FBA02272 | [5 empty] | D1 Training Glass | D1 | Installed | UAT | Applications | TSA | D1 Training Glass | D1 Training Glass |  | UAT | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.92.1.0.1.el7.x86_64) | 4 | 8192 | 151644 | 151644 | 10.30.140.242 |  |  |  | 10.100.140.242 | [16 empty] | No
FBA02273 | [5 empty] | D1 Traning Connect | D1 | Installed | UAT | Applications | TSA | D1 Traning Connect | D1 Traning Connect |  | UAT | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 8 | 16384 | 170195 | 170195 | 10.30.140.243 |  |  |  | 10.100.140.243 | [16 empty] | No
FBA02274 |  |  |  | Server is obsolete and decommissioned per Gilberto - jdeltoro 11/13 |  | PCI CDO SANDBOX - SSIS ETL Framework | CDO SANDBOX - SSIS ETL Framework | Installed | Production | Applications | CDO | PCI CDO SANBOX - SSIS ETL Framework | PCI CDO SANBOX - SSIS ETL Framework | Decommissioned | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez | FBA02274 |  |  |  | MR1130 | Cloud |  |  | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 528702 | 528702 | 10.30.148.10 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
fba02275 | [5 empty] | D1 Orbograph License Server SIT | D1 | Installed | Development | Applications | TSA | D1 Orbograph License Server SIT | D1 Orbograph License Server SIT |  | Development | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | fba02275 | FBA02275.firstbank.local |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 161914 | 51652 | 10.30.140.29 |  |  |  | 10.100.140.29 | [16 empty] | No
fba02276 |  |  |  | Follow up on working session Tuesday 5/13 with Omar and Eric to log into this server and review applications - jdeltoro 5/9; Eric to follow up on this with his team to do deep dive of applications jdeltoro 5/13 | Eric | IIS Consolidated UIT/DEV - (FB57768 - FB57769 - FBA06006 upgrade) | IIS Consolidated | Installed | Development | Applications | TSA & others (Definir cuales son los aplicativos) | IIS Consolidated UIT/DEV - (FB57768 - FB57769 - FBA06006 upgrade) | IIS Consolidated UIT/DEV - (FB57768 - FB57769 - FBA06006 upgrade) | UIT | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | fba02276 | FBA02276.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 157783 | 126726 | 10.30.140.30 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
fba02277 | [5 empty] | D1 Orbograph License Server 1 PROD | D1 | Installed | Production | Applications | TSA | D1 Orbograph License Server 1 PROD | D1 Orbograph License Server 1 PROD |  | Production | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | fba02277 |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 170827 | 170827 | 10.30.148.44 |  |  |  | 10.100.148.44 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8 | [6 empty] | Yes
fba02278 |  |  |  | Related to D1 - No Migrate (Development team jumpbox) |  | Windows 2016 Development Server | Windows 2016 | Installed | Development | Applications | N/A | Windows 2016 Development Server | Windows 2016 Development Server |  | Development | Yes | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | fba02278 | FBA02278.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7159 (1607) | 4 | 4096 | 75860 | 60728 | 10.30.140.62 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02279 |  |  |  | No Migrate - Part of D1 Migration |  | Linux 7 Development Server | Linux 7 | Installed | Development | Applications | N/A | Linux 7 Development Server | Linux 7 Development Server |  | Development | No | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 4096 | 45140 | 28562 | 10.30.140.63 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 2 | 8 | [6 empty] | No
FBA02281 |  |  | x | No migration per Coralia - jdeltoro 10/17 | N/A | Mortgageware | Mortgageware | Installed | STAGING | Applications | Waldemar Velez | MortgageWare | Mortgageware | Staging | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Luzmarie Velez |  | Waldemar Velez | FBA02281 | FBA02281.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 157787 | 157787 | 10.30.137.165 | 255.255.255.0 |  | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02282 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; jdeltoro 5/9 |  | Varonis Server SOLR - APP | Varonis | Installed | Production | Utilities | N/A | Varonis Server SOLR - APP | Varonis Server SOLR - APP |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo | FBA02282 | FBA02282.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 1868001 | 1868001 | 10.30.137.221 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02283 |  |  |  | Requires follow up discussion during AMR on whether this will be need in Azure. Also what would be done for shares in FIS.; jdeltoro 5/9 |  | VARONIS COLLECTOR 04 | Varonis | Installed | Production | Utilities | N/A | VARONIS COLLECTOR 04 | VARONIS COLLECTOR 04 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo | FBA02283 | FBA02283.firstbank.local |  | Varonis | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 344324 | 344324 | 10.30.137.132 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
FBA02284 |  |  |  | Reviewed databases with Omar and no concerns. Reviewed dependency with APPRO and determined that this needs to move in Milestone 3; also has a dependency on Load Balancer for FEIS - jdeltoro 5/22 |  | ITDG APPL UIT | ITDG | Installed | UIT | Applications | TSA | ITDG APPL UIT | ITDG APPL UIT |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02284 | FBA02284.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 157784 | 96194 | 10.30.140.32 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02289 |  |  |  | Reviewed databases with Omar and no concerns. Reviewed dependency with APPRO and determined that this needs to move in Milestone 3; also has a dependency on Load Balancer for FEIS - jdeltoro 5/22 |  | ITDG APPL UAT (E-firstclass/Eloan/OSS/NMS/Imaps | ITDG | Installed | UAT | Applications | TSA | ITDG APPL UAT (Efirstclass/Eloan/OSS/NMS/Imaps | ITDG APPL UAT (Efirstclass/Eloan/OSS/NMS/Imaps |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02289 | FBA02289.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 1 | 2048 | 206931 | 48734 | 10.30.140.33 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02290 |  |  |  | Moved to Milestone 2 - jdeltoro 5/9 |  | ITDG APPL PROD #1 (Eloan/OSS/NMS/Imaps | ITDG | Installed | Production | Applications | TSA | ITDG APPL PROD #1 (Eloan/OSS/NMS/Imaps | ITDG APPL PROD #1 (Eloan/OSS/NMS/Imaps |  | Production | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02290 | FBA02290.firstbank.local |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 221301 | 221301 | 10.30.137.207 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02291 | [5 empty] | ITDG APPL PROD #2 (e-firstclass windows service) | ITDG | Installed | Production | Applications | TSA | ITDG APPL PROD #2 (efirstclass windows service) | ITDG APPL PROD #2 (efirstclass windows service) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02291 | FBA02291.firstbank.local |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 221346 | 221346 | 10.30.137.214 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02292 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | ISIM Adapter Agent 1 | ISIM | Disposed/Retired | OFF | Applications | N/A | ISIM Adapter Agent 1 | ISIM Adapter Agent 1 | Decommissioned | STAGING | Yes | Decommissioned |  |  |  | Yes | fba02292 | Yes |  | N/A |  | N/A | FBA02292 | FBA02292.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 2 | 16384 | 118879 | 118879 | 10.30.137.191 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 2 | 8
FBA02293 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | ISIM Adapter Agent 2 | ISIM | Disposed/Retired | OFF | Applications | N/A | ISIM Adapter Agent 2 | ISIM Adapter Agent 2 | Decommissioned | STAGING | Yes | Decommissioned |  |  |  | Yes | FBA02293 | Yes |  | N/A |  | N/A | FBA02293 | FBA02293.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 2 | 16384 | 118900 | 118900 | 10.30.137.197 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA02294 | [5 empty] | D1 Glass UAT Server | D1 | Installed | UAT | Applications | TSA | D1 Glass UAT Server | D1 Glass UAT Server |  | UAT | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 4096 | 147544 | 147544 | 10.30.140.26 |  |  |  | 10.100.140.26 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02295 | [5 empty] | D1 Connect UAT Server | D1 | Installed | UAT | Applications | TSA | D1 Connect UAT Server | D1 Connect UAT Server |  | UAT | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.327.2.el7uek.x86_64) | 4 | 8192 | 131205 | 131205 | 10.30.140.37 |  |  |  | 10.100.140.37 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA02298 |  |  |  | No Migrate - Powered off |  | On Base E-Contracting Auto / E-Firstclass | On Base E-Contracting Auto / E-Firstclass | Disposed/Retired | OFF | Applications | N/A | On Base E-Contracting Auto / E-Firstclass | On Base E-Contracting Auto / E-Firstclass | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02298 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FBA02299 |  |  |  | No Migrate - Powered off |  | On Base E-Contracting Auto / E-Firstclass | On Base E-Contracting Auto / E-Firstclass | Disposed/Retired | OFF | Applications | N/A | On Base E-Contracting Auto / E-Firstclass | On Base E-Contracting Auto / E-Firstclass | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02299 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FBA02300 |  |  | x | To Be Decommissioned; No Migrate |  | Profitability & BDI Contingency Server - Bancware | Bancware | Installed | Contingency | Applications | Financial Planning | Profitability & BDI Contingency Server | Profitability & BDI Contingency Server |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA02300 | FBA02300.firstbank.local |  | Bancware |  | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 698924 | 529020 | 10.0.151.110 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA02303 | [5 empty] | Ricoh Papercut PCC Server | Ricoh Papercut PCC | Installed | Production | Applications | N/A | Ricoh Papercut PCC Server | Ricoh Papercut PCC Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02303 | FBA02303.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 12288 | 946287 | 518081 | 10.30.137.129 | 255.255.255.0 | [19 empty] | No
FBA02304 | [5 empty] | Ricoh OCR Scanning Server | Ricoh OCR Scanning | Installed | STAGING | Applications | N/A | Ricoh OCR Scanning Server | Ricoh OCR Scanning Server |  | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02304 | FBA02304.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 579700 | 579700 | 10.30.137.130 | 255.255.255.0 | [19 empty] | No
FBA02307 |  |  |  | Confirmed with JT no migration - jdeltoro 5/9 |  | GFT MQ New | GFT | Installed | Production | Applications | N/A | GFT MQ New | GFT MQ New |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02307 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 213074 | 213074 | 10.30.156.111 | [20 empty] | Yes
FBA02307-2022 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | GFT MQ New | GFT | Disposed/Retired | OFF | Applications | N/A | GFT MQ Win2022 MQ 9.4 | GFT MQ New | Decommissioned | UAT | Yes | Decommissioned |  |  |  | No | FBA02307-2022 | No |  | N/A |  | N/A | FBA02307-2022 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 8192 | 477063 | 281870 | 10.30.137.244 | 255.255.255.0
FBA02308 |  |  | x | Confirmed with JT no migration - jdeltoro 5/9 |  | GFT MQ New - COB | GFT | Installed | Contingency | Applications | N/A | GFT MQ New - COB | GFT MQ New - COB |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02308 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 213286 | 213286 | 10.19.156.111 | [20 empty] | No
FBA02308-2022 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | GFT MQ Win2022 MQ 9.4 COB | GFT | Disposed/Retired | OFF | Applications | N/A | GFT MQ Win2022 MQ 9.4 COB |  | Decommissioned | UAT | Yes | Decommissioned |  |  |  | No | FBA02308-2022 | No |  | N/A |  | N/A | FBA02308-2022 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 8192 | 463032 | 258257 | 10.19.137.160
FBA02309 | [5 empty] | GFT Crystal Reports New | GFT | Installed | Production | Applications | N/A | GFT Crystal Reports New | GFT Crystal Reports New |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 315508 | 315508 | 10.30.157.207 | [20 empty] | Yes
FBA02310 |  |  | x | Validate No Migrate |  | GFT Crystal Reports New - COB | GFT | Installed | Contingency | Applications | N/A | GFT Crystal Reports New - COB | GFT Crystal Reports New - COB |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02310 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 315623 | 315623 | 10.19.157.206 | [20 empty] | No
FBA02311 | [5 empty] | D1 Glory HA Device Controller server 1 DEV | D1 | Installed | Development | Applications | TSA | D1 Glory HA Device Controller server 1 DEV | D1 Glory HA Device Controller server 1 DEV |  | Development | No | Pending |  | Yes |  | No |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn |  | 2 | 8192 | 136311 | 136311 | 10.30.140.158 |  |  |  | 10.100.140.158 | [16 empty] | No
FBA02312 | [5 empty] | D1 Glory HA Device Controller server 2 Dev | D1 | Installed | Development | Applications | TSA | D1 Glory HA Device Controller server 2 Dev | D1 Glory HA Device Controller server 2 Dev |  | Development | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.323.8.1.el7uek.x86_64) | 2 | 8192 | 136377 | 136377 | 10.30.140.159 |  |  |  | 10.100.140.159 | [16 empty] | No
FBA02313 | [5 empty] | CA Server 01 | CA | Installed | Production | Security | N/A | Certificate Authority (CA) Server 01 | CA Server 01 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Milton Rojas (CSO) |  | German Ferrer | FBA02313 | FBA02313.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 131197 | 131197 | 10.30.137.236 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02314 | [5 empty] | CA Server 02 | CA | Installed | Production | Security | N/A | Certificate Authority (CA) Server 02 | CA Server 02 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Milton Rojas (CSO) |  | German Ferrer | FBA02314 | FBA02314.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 131191 | 131191 | 10.30.137.237 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02315 | [5 empty] | CA Server 03 | CA | Installed | Production | Security | N/A | Certificate Authority (CA) Server 03 | CA Server 03 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Milton Rojas (CSO) |  | German Ferrer | FBA02315 | FBA02315.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 131229 | 131229 | 10.30.137.238 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02316 | [5 empty] | IBM SKLM 01 | IBM SKLM 01 | Installed | Production | Applications | N/A | IBM SKLM 01 | IBM SKLM 01 |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.5 (4.18.0-305.12.1.el8_4.x86_64) | 4 | 8192 | 213082 | 213082 | 10.30.129.34 | 255.255.255.0 | [19 empty] | Yes
FBA02317 | [5 empty] | IBM SKLM 02 | IBM SKLM 02 | Installed | Production | Applications | N/A | IBM SKLM 02 | IBM SKLM 02 |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.5 (4.18.0-305.12.1.el8_4.x86_64) | 4 | 8192 | 435076 | 232265 | 10.30.129.35 | 255.255.255.0 | [19 empty] | Yes
fba02318 |  |  | x | Validate No Migrate |  | IBM SKLM 03 | IBM SKLM 03 | Installed | Production | Applications | N/A | IBM SKLM 03 | IBM SKLM 03 | Decommissioned | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.5 (4.18.0-348.12.2.el8_5.x86_64) | 4 | 8192 | 436076 | 241921 | 10.20.101.34 | [20 empty] | Yes
fba02319 |  |  | x | Validate No Migrate |  | IBM SKLM 04 | IBM SKLM 04 | Installed | Production | Applications | N/A | IBM SKLM 04 | IBM SKLM 04 | Decommissioned | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.5 (4.18.0-348.12.2.el8_5.x86_64) | 4 | 8192 | 213663 | 213663 | 10.20.101.35 | [20 empty] | Yes
FBA02320 | [5 empty] | VDI RDS License Server | VDI RDS License | Installed | Production | Applications | Multiple VDI Users | VDI RDS License Server | VDI RDS License Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA02320 | FBA02320.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 157788 | 157788 | 10.30.137.119 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02321 | [5 empty] | Radius Server 01 (MFA) | Radius01 (MFA) | Installed | Production | Applications | N/A | Radius Server 01 (MFA) | Radius Server 01 (MFA) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02321 | FBA02321.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 110680 | 110680 | 10.30.137.177 | 255.255.255.0 | [19 empty] | No
FBA02322 | [5 empty] | Radius Server 02 (MFA) | Radius02 (MFA) | Installed | Production | Applications | N/A | Radius Server 02 (MFA) | Radius Server 02 (MFA) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02322 | FBA02322.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 110680 | 110680 | 10.30.137.178 | 255.255.255.0 | [19 empty] | No
FBA02323 | [5 empty] | DRA Global Master (MFA) | NetIQ | Installed | Production | Applications | CSO | DRA Global Master (MFA) | DRA Global Master (MFA) |  | Production | Yes | Pending |  |  |  | No |  | Yes |  | Maria Ripepi |  | Omar Cuadrado |  |  |  | DRA | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn |  | 4 | 12288 | 114809 | 114809 | 10.30.192.104 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02324 | [5 empty] | DRA Slave Server (MFA) | NetIQ | Installed | Production | Applications | CSO | DRA Slave Server (MFA) | DRA Slave Server (MFA) |  | Production | Yes | Pending |  |  |  | No |  | Yes |  | Maria Ripepi |  | Omar Cuadrado |  |  |  | DRA | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn |  | 4 | 12288 | 114780 | 114780 | 10.30.192.105 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02325 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Econtracting Onbase App Server 1 | Onbase | Disposed/Retired | OFF | Applications | TSA | OnBase(Moex) App Server 1 | Econtracting Onbase App Server 1 | Decommissioned | Production | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02325 | FBA02325.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 237774 | 237774 | 10.30.137.243 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02326 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Econtracting Onbase App Server 2 | Onbase | Disposed/Retired | OFF | Applications | TSA | OnBase(Moex) App Server 2 | Econtracting Onbase App Server 2 | Decommissioned | Production | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02326 | FBA02326.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 237808 | 237808 | 10.30.137.250 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32
FBA02327 | [5 empty] | D1 Glory HA Device Controller Prod Server 1 | D1 | Installed | Production | Applications | TSA | D1 Glory HA Device Controller Prod Server 1 | D1 Glory HA Device Controller Prod Server 1 |  | Production | No | Pending |  | Yes |  | No |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn |  | 4 | 8192 | 238719 | 216514 | 10.30.134.115 | 255.255.255.0 |  |  | 10.100.134.115 | [16 empty] | No
FBA02328 | [5 empty] | D1 Glory HA Device Controller Prod Server 2 | D1 | Installed | Production | Applications | TSA | D1 Glory HA Device Controller Prod Server 2 | D1 Glory HA Device Controller Prod Server 2 |  | Production | No | Pending |  | Yes |  | No |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn |  | 4 | 8192 | 238743 | 217350 | 10.30.134.116 | 255.255.255.0 |  |  | 10.100.134.116 | [16 empty] | No
FBA02329 | [5 empty] | Onbase temp Document Conversion Server | Onbase | OFF | OFF | Applications | TSA | Onbase temp Document Conversion Server | Onbase temp Document Conversion Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02329 | FBA02329.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 4 | 16384 | 139459 | 139459 | 10.30.137.232 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02331 | [5 empty] | Datacard CardWizard Issuance Software | Datacard CardWizard | Installed | Production | Applications | N/A | Datacard CardWizard Issuance Software | Datacard CardWizard Issuance Software |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02331 | FBA02331.firstbank.local |  |  | MR1130 | Onsite | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 213107 | 91299 | 10.30.137.109 | 255.255.255.0 | [19 empty] | Yes
FBA02333 | [5 empty] | Feis Application Server 7 Prod | FEIS | Installed | Production | Applications | N/A | Feis Application Server 7 Prod | Feis Application Server 7 Prod |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.330.7.1.el7uek.x86_64) | 4 | 65536 | 168491 | 168491 | 10.30.134.117 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E18-4s_v6 | 4 | 64 | [6 empty] | No
fba02334 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | B2B Perimeter Server – UAT. | B2B Perimeterâ€“. | Disposed/Retired | OFF | Applications | Miguel Mejias/Luis Arvelo | B2B Perimeter Server – UAT. | B2B Perimeter Server – UAT. | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA02334 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 6144 | 164972 | 164972 | 10.30.140.7
FBA02335 |  |  | x | ON |  | Opmanager Central Server | Opmanager Central | Installed | Production | Applications | N/A | Opmanager Central Server | Opmanager Central Server |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02335 | FBA02335.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 545494 | 545494 | 10.30.75.43 | [20 empty] | Yes
FBA02336 |  |  | x | ON |  | Opmanager Central Server | Opmanager Central | Installed | Production | Applications | N/A | Opmanager Probe 1 Server | Opmanager Central Server |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02336 | FBA02336.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 529166 | 529166 | 10.30.75.44 | [20 empty] | Yes
FBA02337 |  |  | x | ON |  | Opmanager Probe 2 Server | Opmanager Probe 2 | Installed | Production | Applications | N/A | Opmanager Probe 2 Server | Opmanager Probe 2 Server |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02337 | FBA02337.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 529148 | 529148 | 10.30.75.42 | [20 empty] | Yes
FBA02338 | [5 empty] | Opmanager Probe 3 Server | Opmanager Probe 3 | Installed | Production | Applications | N/A | Opmanager Probe 3 Server | Opmanager Probe 3 Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02338 | FBA02338.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 529128 | 529128 | 10.30.75.46 | [20 empty] | Yes
fba02339 | [5 empty] | B2Bi Perimeter Server (PROD-DMX) | B2Bi Perimeter(-DMX) | Disposed/Retired | OFF | Applications | Miguel Mejias/Luis Arvelo | B2Bi Perimeter Server (PROD-DMX) | B2Bi Perimeter Server (PROD-DMX) |  | Production | No | Completed |  |  |  | No | FBA02339 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 6144 | 195667 | 195667 | 10.30.192.183
FBA02340 |  |  |  | Review with Omar - DB should be no concern; Dependency on FBA65031 - MSSQL Server; Does interface with FEIS; also has a connection from FBA02239 on port 1688 for ASG Mobius 8; Angel reviewed and no concern; Ana Cruz to follow up with InfoCorp - jdeltoro 5/15; per Ana no connection requirements to FBA02239. Does access a load balancer 10.30.140.215, connects to 140.91, 92,93, and 97 - jdeltoro 5/29 |  | Business eStatement Viewer APP - UIT | Business eStatement | Installed | Development | Applications | TSA | Business eStatement Viewer APP - UIT | Business eStatement Viewer APP - UIT |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA02340 | FBA02340.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221394 | 221394 | 10.30.140.112 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02341 | [5 empty] | Business eStatement Viewer APP 1 - PROD | ITDG | Installed | Production | Applications | TSA | Business eStatement Viewer APP 1 - PROD | Business eStatement Viewer APP 1 - PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02341 | FBA02341.firstbank.local |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 238221 | 238221 | 10.30.137.57 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02342 | [5 empty] | Business eStatement Viewer APP 2 - PROD | ITDG | Installed | Production | Applications | TSA | Business eStatement Viewer APP 2 - PROD | Business eStatement Viewer APP 2 - PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA02342 | FBA02342.firstbank.local |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 238073 | 238073 | 10.30.137.58 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02343 |  |  |  | updated CMDB status and environment per Angel - jdeltoro 11/10 |  | IBM ISIM Appliance | ISIM | Disposed/Retired | STAGING | Security | N/A | IBM ISIM Appliance | IBM ISIM Appliance | Decommissioned | STAGING | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 221268 | 221268 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FBA02344 |  |  | x | Follow up with Milton/MSS |  | Tenable Virtual Appliance 4.8.0 (Nexus) | Tenable Virtual Appliance 4.8.0 (Nexus) | Installed | Production | Security | CSO | Tenable Virtual Appliance 4.8.0 (Nexus) | Tenable Virtual Appliance 4.8.0 (Nexus) |  | Production | No | Pending |  |  |  | No |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 8192 | 49449 | 49449 | 10.30.192.6 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02345 |  |  | x | Decommission |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 16 | 49152 | 704608 | 704608 | 10.30.129.29 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6
FBA02346 | [5 empty] | FortyAthenPOC Test Host | FortyAthen Host | Installed | Development | Utilities | N/A | FortyAthenPOC Test Host | FortyAthenPOC Test Host |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.68.3.1.el7uek.x86_64) | 2 | 4096 | 70768 | 16507 | 10.30.140.89 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02347 |  |  |  | Follow up with Omar - Dependency on FBA65030 - MSSQL Server; Does interface with FEIS; Ana Cruz to follow up with InfoCorp - jdeltoro 5/15; per Ana no connection requirements to FBA02239. needs review of firewall rules for TSYS FXD - jdeltoro 5/29 |  | Business eStatement APP UAT | Business eStatement | Installed | UAT | Applications | TSA | Business eStatement APP UAT | Business eStatement APP UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA02347 | FBA02347.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221486 | 221486 | 10.30.140.120 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02348 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/22 |  | Logs Repositories | Logs Repositories | OFF | OFF | Applications | N/A | Logs Repositories | Logs Repositories | Decommissioned | STAGING | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  | Logs Repositories | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.307.3.1.el7uek.x86_64) | 2 | 8192 | 2312715 | 2312715 | 10.30.134.132 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
fba02349 | [5 empty] | D1 Orbograph License Server 2 Prod | D1 | Installed | Production | Applications | TSA | D1 Orbograph License Server 2 Prod | D1 Orbograph License Server 2 Prod |  | Production | Yes | TBD | Yes | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | fba02349 |  |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 170796 | 170796 | 10.30.148.45 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA02350 | [5 empty] | Datacard CardWizard (DEV) | Datacard CardWizard | Installed | UAT | Applications | N/A | Datacard CardWizard (DEV) | Datacard CardWizard (DEV) |  | UAT | Yes | TBD |  | Yes |  | Yes |  | Yes |  | N/A |  | N/A | FBA02350 | FBA02350.firstbank.local |  |  | MR1130 | Onsite | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 161895 | 58265 | 10.30.140.104 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02351 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6; updated Application name per Angel - jdeltoro 10/21 |  | PR Computer Insurance app for Santander | PR Computer Insurance app for Santander | Installed | Production | Applications | N/A | Pricing | Pricing |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02351 | FBA02351.firstbank.local |  | Pricing | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 208990 | 208990 | 10.30.137.198 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA02352 | [5 empty] | Onbase v20 appServer 1 | Onbase | Installed | Development | Applications | TSA | Onbase v20 appServer 1 | Onbase v20 appServer 1 |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02352 | FBA02352.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 1288303 | 1070946 | 10.30.140.230 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02353 | [5 empty] | Onbase v20 appserver 2 | Onbase | Installed | Development | Applications | TSA | Onbase v20 appserver 2 | Onbase v20 appserver 2 |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02353 | FBA02353.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 2 | 8192 | 192632 | 170980 | 10.30.140.231 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02354 | [5 empty] | Onbase v20 appserver 3 | Onbase | Installed | Development | Applications | TSA | Onbase v20 appserver 3 | Onbase v20 appserver 3 |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02354 | FBA02354.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 161879 | 99809 | 10.30.140.232 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02355 | [5 empty] | ReconFrontier Application Server | ReconFrontier | Installed | Production | Applications | Karina Valentin | ReconFrontier Application Server | ReconFrontier Application Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Norberto Gonzalez |  | Karina Valentin | FBA02355 | FBA02355.firstbank.local |  | ReconFrontier | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 392284 | 392284 | 10.30.137.20 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02356 |  |  |  | Follow up with Norberto Gonzalez, Karina Valentin and Vendor; Follow up with Omar on database on FB65031 - jdeltoro 5/16; Reviewed databases and no concerns; follow up on app info in AMR - jdeltoro 5/29 |  | Fiserv ReconFrontier Application Server UAT | Fiserv ReconFrontier | Installed | UAT | Applications | Karina Valentin | ReconFrontier Application Server UAT | ReconFrontier Application Server UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Norberto Gonzalez |  | Myriam Cintron | FBA02356 | FBA02356.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 392332 | 44928 | 10.30.140.151 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02357 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens - Provisioning Server | Xapiens | Installed | Production |  | TBD |  |  | Prod |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.165.12 | [20 empty] | Yes
FBA02358 | [5 empty] | VeeamOne | VeeamOne | Installed | Production | Applications | N/A | VeeamOne | VeeamOne |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02358 | FBA02358.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 12 | 32768 | 365828 | 365828 | 10.30.129.50 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | [8 empty] | Yes
FBA02360 |  |  |  | Network Review for DMZ; Needs follow up as it it talking to FBA08141 and this appears to be a new server; also FBA02458; has dependency on FB65030; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15; moved to Milestone 3 per Angel - jdeltoro 10/21 | TBD | AUTO UAT Onbase WKSOBDocComp - New Onbase systems | Onbase | Installed | Production | Applications | Gissy Lou | AUTO UAT Onbase WKSOBDocComp |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02360 | fba02360.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 8 | 8192 | 213104 | 198902 | 10.30.140.203 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02361 |  |  |  | Network Review for DMZ; No issues found in Faddom; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15 | TBD | Auto UAT OnBase E-contracting AppServer | Onbase | Installed | Development | Applications | Gissy Lou | Auto UAT OnBase E-contracting AppServer |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02361 | FBA02361.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 213100 | 184038 | 10.30.140.204 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02362 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Econtracting DMZ1 - E-Firstclass | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Econtracting DMZ 1 | Onbase Econtracting DMZ1 | Decommissioned | Production | No | Decommissioned |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 388931 | 207349 | 10.30.192.177 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA02363 | [5 empty] | VEEAM Backup | VEEAM Backup | Installed | Production | Applications | N/A | VEEAM Backup | VEEAM Backup |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02363 | FBA02363.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 20480 | 1034409 | 1034409 | 10.30.129.51 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA02364 | [5 empty] | VEEAM Ent Server | VEEAM Ent | Installed | Production | Applications | N/A | VEEAM Ent Server | VEEAM Ent Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02364 | FBA02364.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 12288 | 985192 | 985192 | 10.30.129.52 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA02366 | [5 empty] | DebtManager APP/Web PROD | DebtManager | Installed | Production | Applications | Sheila Ponte | DebtManager APP/Web PROD | DebtManager APP/Web PROD |  | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | Santitos Rivas |  | Geraldo Reyes | FBA02366 |  |  | DebtManager | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 12 | 16384 | 323845 | 120294 | 10.30.148.90 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA02367 | [5 empty] | HPE 3PAR Service Control | HPE 3PAR Service Control | Installed | Contingency | Utilities | N/A | HPE 3PAR Service Control | HPE 3PAR Service Control |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 528780 | 84861 | 10.20.101.30 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA02368 |  |  |  | Will be decommissioned per Juan Luis - jdeltoro 5/9 |  | Dynatrace ActiveGate UAT (POC) | Dynatrace ActiveGate | Disposed/Retired | OFF | Applications | N/A | Dynatrace ActiveGate UAT (POC) |  | Decommissioned | UAT | No | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | Linux |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.324.5.3.el8uek.x86_64) | 4 | 4096 | 106633 | 106633 | 10.30.140.210 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8
FBA02369 | [5 empty] | New TPSS Oracle 8 Server | TPSS | Installed | Development | Applications | TSA | New TPSS Oracle 8 Server | New TPSS Oracle 8 Server |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  |  | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.324.5.3.el8uek.x86_64) | 4 | 4096 | 157811 | 64870 | 10.30.140.209 | 255.255.255.0 |  |  | 10.100.140.209 | [6 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | [8 empty] | No
FBA02370 | [5 empty] | NEW Xpress oracle 8 server | Xpress | Installed | Development | Applications | TSA | NEW Xpress oracle 8 server | NEW Xpress oracle 8 server |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.324.5.3.el8uek.x86_64) | 4 | 4096 | 249951 | 57953 | 10.30.140.217 | 255.255.255.0 |  |  | 10.100.140.217 | [6 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | [8 empty] | No
FBA02371 |  |  |  | Marked as Milestone 2, but non-prod servers are marked as Group Obsolete - needs follow up with Eric - jdeltoro 5/13 |  | OLS | OLS | Installed | Development | Applications | TSA | NEW OLS oracle 8 server | NEW OLS oracle 8 server |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Eric Lopez |  |  |  | OLS | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.324.5.3.el8uek.x86_64) | 4 | 4096 | 157814 | 21225 | 10.30.140.225 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02372 |  |  |  | Per Eric this is a temporary server and will be decommissioned at a later point in the future - jdeltoro 5/13 |  | NEW Account Resolution oracle 8 server (Account Resolution Portal) | NEW Account Resolution oracle 8(Account Resolution Portal) | Installed | Development | Applications | N/A | NEW Account Resolution oracle 8 server | NEW Account Resolution oracle 8 server |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.330.7.1.el8uek.x86_64) | 4 | 4096 | 173470 | 28550 | 10.30.140.226 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02375 |  |  |  | Decommission per ticket CH25000178847 in CMC - jdeltoro 7/30 |  | Onbase Econtracting app server 1 new | Onbase Econtracting app new | Disposed/Retired | OFF | Applications | N/A | Onbase Econtracting app server 1 new | Onbase Econtracting app server 1 new | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02375 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 106580 | 106580 | 10.30.140.222 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8
FBA02376 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Onbase Econtracting app server 2 new | Onbase Econtracting app new | Disposed/Retired | OFF | Applications | N/A | Onbase Econtracting app server 2 new | Onbase Econtracting app server 2 new | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02376 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA02377 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 |  | Logicity DEV Server PROD | Logicity | Installed | UIT | Applications | N/A | Logicity DEV Server | Logicity DEV Server |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02377 | FBA02377.firstbank.local |  | Logicity | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 8192 | 264286 | 45517 | 10.30.140.154 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02378 |  |  |  | Follow up with JT; Eric reported that this server replaced FBA02194; Follow up on Zena Server location, currently targetted for Cloud and may need to go to FIS; This is a scheduler for ETLs and data warehouse - jdeltoro 1/13/25; This could be expanded to be a scheduler for more than Xamine; This would be something possibly in the future, but moving to FIS should be good. - jdeltoro 5/13 |  | Zena Server Linux * | Zena (Xamine) | Installed | Production | Applications | CDO | Zena Server Linux * | Zena Server Linux * | Prod | Production | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 4 | 4096 | 138793 | 43208 | 10.30.134.124 | 255.255.255.0 |  |  | 10.100.134.124 | [16 empty] | Yes
FBA02379 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Econtracting app server | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Econtracting app server | Onbase Econtracting app server | Decommissioned | Production | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02379 | FBA02379.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 170093 | 112950 | 10.30.137.67 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA02380 |  |  | x | Validate No Migrate |  | VEEAM Backup Arterial | VEEAM Backup Arterial | Installed | Production | Applications | N/A | VEEAM Backup Arterial | VEEAM Backup Arterial |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02380 | FBA02380.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 16 | 32768 | 2286160 | 2286160 | 10.20.101.51 | [20 empty] | Yes
FBA02381 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | VEEAM Backup Santurce | VEEAM Backup Santurce | Disposed/Retired | OFF | Applications | N/A | VEEAM Backup Santurce | VEEAM Backup Santurce | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA02381 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA02382 | [5 empty] | Digital Banking - Application 1 - PROD Upgrade | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 1 - PROD Upgrade | Digital Banking - Application 1 - PROD Upgrade |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02382 | FBA02382.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 24 | 32768 | 237780 | 185450 | 10.30.137.179 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D32ls_v6 | 32 | 64 | [6 empty] | Yes
FBA02383 | [5 empty] | Digital Banking - Application 2 - PROD Upgrade | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 2 - PROD Upgrade | Digital Banking - Application 2 - PROD Upgrade |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02383 | FBA02383.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 16 | 32768 | 237744 | 178133 | 10.30.137.190 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA02384 | [5 empty] | Digital Banking - Application 3 - PROD Upgrade | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - Application 3 - PROD Upgrade | Digital Banking - Application 3 - PROD Upgrade |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02384 | FBA02384.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 16 | 32768 | 237720 | 212988 | 10.30.137.192 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
fba02385 | [5 empty] | SCG VMware Data Domain | SCG VMware Data Domain | Disposed/Retired | OFF | Applications | N/A | SCG VMware Data Domain | SCG VMware Data Domain | Decommissioned | Production | No | Completed |  |  |  | No | FBA02385 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 159848 | 159848 | 10.30.129.40 | 255.255.255.0
fba02387 | [5 empty] | Redis UAT Server - Digital Banking | Digital Banking | Installed | UAT | Applications | N/A | Redis UAT Server | Redis UAT Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208997 | 34015 | 10.30.140.228 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
fba02388 | [5 empty] | REDIS UIT Server - Digital Banking | Digital Banking | Installed | UIT | Applications | N/A | REDIS UIT Server | REDIS UIT Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.6 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 208982 | 63463 | 10.30.140.239 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02389 |  |  | x | Validate No Migrate |  | FEIS Application server Alterial | FEIS | Installed | STAGING | Applications | N/A | FEIS Application server Alterial | FEIS Application server Alterial |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.325.5.el7uek.x86_64) | 4 | 16384 | 88752 | 37869 | 10.20.106.181 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02390 |  |  | x | Validate No Migrate |  | FEIS Application Server | FEIS | Installed | STAGING | Applications | N/A | FEIS Application Server | FEIS Application Server |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.331.7.el7uek.x86_64) | 4 | 32768 | 105181 | 53682 | 10.20.106.170 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | No
FBA02391 |  |  | x | Validate No Migrate |  | FEIS Application Server Alterial | FEIS | Installed | STAGING | Applications | N/A | FEIS Application Server Alterial | FEIS Application Server Alterial |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.331.7.el7uek.x86_64) | 4 | 16384 | 88796 | 36059 | 10.20.106.113 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA02392 | [5 empty] | FASTTRACK_Azure Migration Server_ | FASTTRACK_Azure Migration _ | Installed | Production | Utilities | N/A | FASTTRACK_Azure Migration Server_ | FASTTRACK_Azure Migration Server_ |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02392 | FBA02392.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 323861 | 91441 | 10.30.137.38 | 255.255.255.0 | [19 empty] | No
FBA02393 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens - Provisioning server prod | Xapiens | Installed | Production |  | TBD |  |  | Prod |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.167.4 | [20 empty] | Yes
FBA02394 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | DebtManager 11 UAT - App-Web-ETL | DebtManager | Installed | UAT | Applications | Sheila Ponte |  |  | UAT |  |  | TBD | [7 empty] | Santitos Rivas |  | Geraldo Reyes |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2016 |  |  |  |  | 10.30.140.70 | [20 empty] | No
FBA02395 |  |  | x | To Be Decommissioned; No Migrate |  | VEEAM Backup Sungard | VEEAM Backup Sungard | Installed | Contingency | Applications | N/A | VEEAM Backup Sungard | VEEAM Backup Sungard |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02395 | FBA02395.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 1362448 | 1362448 | 10.0.151.140 | [20 empty] | No
FBA02396 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Econtracting app server new 2 | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Econtracting app server new 2 | Onbase Econtracting app server new 2 | Decommissioned | Production | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02396 | FBA02396.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 170190 | 96832 | 10.30.137.142 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02397 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Onbase Econtracting DMZ1 - E-Firstclass | Onbase | Disposed/Retired | OFF | Applications | TSA | Onbase Econtracting DMZ2 | Onbase Econtracting DMZ1 | Decommissioned | Production | No | Decommissioned |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 221296 | 164037 | 10.30.192.178 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA02398 |  |  |  | Network Review for DMZ; No issues found in Faddom; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15 | TBD | Auto UAT onbase WKSOBDocCOMP 2 | Onbase | Installed | Development | Applications | Gissy Lou | Auto UAT onbase WKSOBDocCOMP 2 |  |  | Development | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | fba02398 | fba02398.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 213101 | 132780 | 10.30.140.10 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02398-old |  |  |  | Follow up with Lucy, Shela and Vendor - C & R Software (used to be FICO); duplicate server name, follow up - jdeltoro 5/16; Decommissioned per Angel, follow up on .70 server and validate the name of that server - jdeltoro 11/18 | TBD | DebtManager 11 UAT - App-Web-ETL | Onbase | Installed | Development | Applications | Gissy Lou | DebtManager 11 UAT - App-Web-ETL | DebtManager 11 UAT - App-Web-ETL |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02394 | FBA02394.firstbank.local |  |  | MR1130 | Cloud |  |  | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 323727 | 104765 | 10.30.140.70 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02399 |  |  | x | ON |  | Auto Econtracting Onbase Econtracting DMZ1 | Onbase | Installed | Production | Applications | TSA | Auto UAT Onbase Econtracting DMZ 1 | Auto Econtracting Onbase Econtracting DMZ1 |  | Development | No | TBD |  |  |  | Yes |  | No | Yes | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 8 | 8192 | 213099 | 135417 | 10.30.192.40 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02400 |  |  | x | ON |  | Auto Econtracting Onbase Econtracting DMZ2 | Onbase | Installed | Development | Applications | TSA | Auto UAT Onbase Econtracting DMZ 2 | Auto Econtracting Onbase Econtracting DMZ2 |  | Development | No | TBD |  |  |  | Yes |  | No | Yes | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 213111 | 124445 | 10.30.192.41 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
FBA02401 |  |  |  | Network Review for DMZ; has dependency on FB65030; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15; Moved to milestone 3 per Angel - jdeltoro 10/21 | TBD | Auto UAT Onbase Econtracting app server 1 - New Onbase systems | Onbase | Installed | Production | Applications | Gissy Lou | Auto UAT Onbase Econtracting app server 1 |  |  | Development | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02401 | FBA02401.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 8 | 8192 | 238108 | 111670 | 10.30.140.11 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02402 |  |  |  | Network Review for DMZ; No issues found in Faddom; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15 | TBD | Auto UAT Onbase Econtracting app server 2 | Onbase | Installed | Development | Applications | Gissy Lou | Auto UAT Onbase Econtracting app server 2 |  |  | Development | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02402 | FBA02402.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 161911 | 78658 | 10.30.140.12 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02403 | Yes |  |  | After ASP migration, the BARR will take reports and pass to OnBase |  | MR1130 BARR NJE (ASP) | BARR | Installed | Production | Applications | N/A | MR1130 BARR NJE (ASP) | MR1130 BARR NJE (ASP) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02403 | FBA02403.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 264285 | 80652 | 10.30.133.17 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA02404 |  |  | x | DR copy of BARR needs to move to Hub 787 |  | ARTERIAL BARR NJE (ASP) | BARR | Installed | Contingency | Applications | N/A | ARTERIAL BARR NJE (ASP) | ARTERIAL BARR NJE (ASP) |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02404 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5820 (1809) | 4 | 8192 | 264627 | 264627 | 10.20.105.17 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA02405 |  |  |  | Replacement for FBA02334; Dependency currently showing for OCI; no concerns -jdeltoro 5/16 | N/A | B2B Perimeter Server DEV | IBM B2Bi | Installed | Development | Applications | TSA | B2B Perimeter Server DEV | B2B Perimeter Server DEV | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.324.5.3.el8uek.x86_64) | 4 | 4096 | 106592 | 27121 | 10.30.140.15 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02406 |  |  |  | New DB2 Server for B2B Application - Replaced FBA03058; no concerns - jdeltoro 5/16 | N/A | B2B DB2 DEV | IBM B2Bi | Installed | Development | Applications | TSA | B2B DB2 DEV | B2B DB2 DEV | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 285797 | 222521 | 10.30.140.102 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02407 |  |  |  | Replacement of FBA02114; dependency on FBA03159 - Added FBA03159 to group 5, no other concerns - jdeltoro 5/16; Reviewed databased with Omar and no further concerns - jdeltoro 5/29 |  | B2B Control Center DEV | IBM B2Bi | Installed | Development | Applications | TSA | B2B Control Center DEV | B2B Control Center DEV | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 106597 | 53586 | 10.30.140.101 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02408 |  |  |  | Replacement of FBA02113; dependency on Oracle systems port 22 possible file transfers, port 10022 from FB65031 and VDI system - jdeltoro 5/16; follow up with Iran Rodriguez | Iran Rodriguez | B2B Integrator DEV | IBM B2Bi | Installed | Development | Applications | TSA | B2B Integrator DEV | B2B Integrator DEV | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 10240 | 1946585 | 1109257 | 10.30.140.100 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02409 |  |  |  | Decommissioned per Angel - 3/25/2025 jdeltoro |  | MOVERE APPL PROD | MOVERE APPL | Disposed/Retired | OFF | Applications | N/A | MOVERE APPL PROD |  | Decommissioned | STAGING | Yes | Decommissioned |  |  |  | Yes | FBA02409 | No |  | N/A |  | N/A | FBA02409 | FBA02409.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213108 | 40159 | 10.30.137.31 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FBA02410 |  |  | x | Validate No Migrate |  | TPSS oracle 8 DB ALTERIAL | TPSS | Installed | STAGING | Database | TSA | TPSS oracle 8 DB ALTERIAL | TPSS oracle 8 DB ALTERIAL |  | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  |  | TPSS | Arterial | FIS | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.8 (5.4.17-2136.309.5.el8uek.x86_64) | 4 | 4096 | 1499522 | 1499522 | 10.20.102.26 |  |  |  | 10.100.102.26 | [6 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | [8 empty] | No
FBA02412 | [5 empty] | Radius Server | Radius Server | Installed | Production | Utilities | N/A | Radius Server | Radius Server |  | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA02412 | FBA02412.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213098 | 213098 | 10.30.137.148 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02413 |  |  | x | Validate No Migrate |  | D1 SPE/PROD - Application (Xpress Server #1) Aretial | D1 SPE/ - Application (Xpress#1) Aretial | Installed | Contingency | Applications | TSA | D1 SPE/PROD - Application (Xpress Server #1) Aretial | D1 SPE/PROD - Application (Xpress Server #1) Aretial |  | Contingency | No | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | Arterial | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 16384 | 262264 | 138168 | 10.20.120.30 |  |  |  | 10.100.120.30 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02414 |  |  | x | Validate No Migrate |  | D1 SPE/PROD - Application (Xpress Server #2) Aretial | D1 SPE/ - Application (Xpress#2) Aretial | Installed | Contingency | Applications | TSA | D1 SPE/PROD - Application (Xpress Server #2) Aretial | D1 SPE/PROD - Application (Xpress Server #2) Aretial |  | Contingency | No | TBD |  | Yes |  | No |  | Yes |  | Sharon Gutierrez |  | John Huertas/Eric Lopez |  |  |  |  | Arterial | FIS | Milestone 3 |  | D1 | Virtual Server | poweredOn |  | 4 | 16384 | 262238 | 138140 | 10.20.120.31 |  |  |  | 10.100.120.31 | [16 empty] | No
FBA02416 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | BSNEE (Branch Digital Screens) Application Server 2019 | BSNEE | Disposed/Retired | OFF | Applications | Marketing | BSNEE (Branch Digital Screens) Application Server 2019 | BSNEE (Branch Digital Screens) Application Server 2019 | Decommissioned | Production | Yes | Decommissioned |  |  |  | Yes | FBA02416 | Yes |  | Cristina Rodriguez |  | Cristina Rodriguez /Felix Otero (felix@sbtechpr.com) / Tais Laborde |  |  |  | BSNEE | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 1218674 | 114289 | 10.30.163.12 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16
FBA02418 |  |  |  | Dependency on OCI, FB65030 - 3GB DB; Follow up on NetIQ DRA, this talks to this server on 445 - jdeltoro 5/15; Dependency also on FBA03109 DB server and FBA01016 file server. Follow up on performance of file transfers. - jdeltoro 5/29 |  | MOEX eLoan Appl UAT | MOEX eLoan | Installed | Development | Applications | TSA | MOEX eLoan Appl UAT | MOEX eLoan Appl UIT |  | STAGING | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Felipe Ramos |  | Ysabel Asencio | FBA02418 | FBA02418.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 208989 | 208989 | 10.30.140.247 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02419 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Teneable POC - Directory Listeners | Teneable - Directory Listeners | Disposed/Retired | OFF | Monitoring | CSO | Teneable POC - Directory Listeners | Teneable POC - Directory Listeners | Decommissioned | STAGING | No | Decommissioned |  |  |  | No |  | Yes |  | Maria Ripepi |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff |  | 4 | 16384 | 170292 | 23280 | [11 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FBA02420 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Teneable POC - Security Engine Nodes | Teneable - Security Engine Nodes | Disposed/Retired | OFF | Monitoring | CSO | Teneable POC - Security Engine Nodes | Teneable POC - Security Engine Nodes | Decommissioned | Development | No | Decommissioned |  |  |  | No |  | Yes |  | Maria Ripepi |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff |  | 4 | 16384 | 170326 | 21987 | [11 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6
FBA02421 |  |  | x | Follow up with Milton/MSS |  | Teneable POC - Storage Manager | Teneable - Storage Manager | Available | OFF | Monitoring | CSO | Teneable POC - Storage Manager | Teneable POC - Storage Manager |  | OFF | No | TBD |  |  |  | No |  | Yes |  | Maria Ripepi |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff |  | 4 | 16384 | 170318 | 23963 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA02422 |  |  |  | Follow up with Rafi - Licensing Requirements - On-Prem vs Cloud Bots; Decommissioned per Angel - jdeltoro 10/21 | Rafi | RPA TEST AUTOMATIONS | RPA | Disposed/Retired | OFF | Applications | Alberto Jimenez | RPA TEST AUTOMATIONS |  | Decommissioned | UAT | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Jesus Sanchez | FBA02422 | FBA02422.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213107 | 67646 | 10.30.140.181 | 255.255.255.0 |  | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02423 |  |  |  | Follow up with Wilson on destination of server and application to stay on-site - jdeltoro 5/8 |  | CyberArk | CyberArk | Installed | Production | Applications | CSO | CyberArk |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Milton Rojas (CSO) |  | Wilson Figueroa/German Ferrar | FBA02423 |  |  | CyberArk | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 16 | 16384 | 221308 | 94078 | 10.30.162.11 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA02424 |  |  |  | Follow up with Wilson on destination of server and application to stay on-site - jdeltoro 5/8 |  | CyberArk 2 | CyberArk | Installed | Production | Applications | CSO | Cyber Ark 2 |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Milton Rojas (CSO) |  | Wilson Figueroa/German Ferrar | FBA02424 |  |  | CyberArk | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 16 | 16384 | 221292 | 70152 | 10.30.162.12 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA02425 |  |  | x | Validate No Migrate |  | CyberArk 3 |  | Installed | Contingency | Applications | N/A | CyberArk 3 |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02425 | CyberArk.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 16 | 16384 | 221280 | 72085 | 10.20.117.11 | [20 empty] | Yes
FBA02426 |  |  | x | ON |  | B2B Integrator Oracle 8 Prod | IBM B2Bi | Installed | Production | Applications | TSA | B2B Integrator oracle 8 prod new | B2B Integrator Oracle 8 Prod |  | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) | 4 | 16384 | 1759910 | 856579 | 10.30.134.212 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02427 |  |  | x | ON |  | B2B Perimeter Server Prod | IBM B2Bi | Installed | Production | Applications | TSA | B2B Perimeter Server oracle 8 Prod New | B2B Perimeter Server Prod |  | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.328.3.el8uek.x86_64) | 4 | 4096 | 144796 | 48591 | 10.30.192.184 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02428 |  |  | x | ON |  | B2B Control Center Oracle 8 | IBM B2Bi | Installed | Production | Database | TSA | B2B Control Center oracle 8 | B2B Control Center Oracle 8 |  | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.1.el8uek.x86_64) | 4 | 12288 | 176207 | 79754 | 10.30.134.214 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
fba02429 |  |  |  | updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Dynatrace ActiveGate PRod | Dynatrace | Installed | Production | Applications | ITOMO | Dynatrace ActiveGate PRod |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Jeanson Portalatin/Harry Gonzalez |  |  |  | Dynatrace | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.325.5.1.el8uek.x86_64) | 4 | 4096 | 208985 | 120533 | 10.30.134.125 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02432 |  |  |  | Follow up with Omar on Database jobs |  | CLCS Server UAT - Commercial Loans | CLCS | Installed | UAT | Applications | Irma Ramos | CLCS Server UAT |  | UAT | UAT | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Irma Ramos | FBA02432 | FBA02432.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 6 | 32768 | 647341 | 398130 | 10.30.140.224 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02433 | [5 empty] | CLCS Server PROD | CLCS | Installed | Production | Applications | Irma Ramos | CLCS Server PROD |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Irma Ramos | FBA02433 | FBA02433.firstbank.local |  | CLCS | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 6 | 32768 | 647586 | 404708 | 10.30.137.144 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02435 | [5 empty] | RDS License Server 2022 | RDS License Server | Installed | Production | Applications | N/A | RDS License Server 2022 |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Edgardo Santiago (FIS) | FBA02435 | FBA02435.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 2 | 4096 | 157778 | 157778 | 10.30.137.14 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA02436 |  |  | x | No concerns; Decommissioned per Angel - jdeltoro 10/21 | N/A | RPA DEV | RPA | Disposed/Retired | OFF | Applications | Alberto Jimenez | RPADEV | RPA DEV | Decommissioned | Development | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Jesus Sanchez | FBA02436 |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 8 | 8192 | 161901 | 44655 | 10.30.140.223 | 255.255.255.0 |  | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02437 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | Flexera | Flexera | Disposed/Retired | OFF | Applications | N/A | Flexera |  | Decommissioned | Development | Yes | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02437 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2022 10.0.20348.2527 (21H2) | 4 | 16384 | 170068 | 57663 | 10.30.140.196 | 255.255.255.0
FBA02438 | [5 empty] | Onbase23_1 | Onbase | Installed | Development | Applications | TSA | Onbase23_1 |  |  | Development | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02438 | fb57490.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 2 | 8192 | 192627 | 179688 | 10.30.140.133 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA02440 |  |  |  | Added to Milestone 1; Group 1 per Angel on 4/14 - jdeltoro | N/A | Informatica Cloud Secure Agent-1 | Informatica | Installed | Development | Applications | TSA/Vallellanes | Informatica Cloud Secure Agent-1 |  | Dev | Development | Yes | TBD |  |  |  | Yes |  | No |  | Lucy Ann Vasquez |  | José Vallellanes | FBA02440 | FBA02440.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 1 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 6 | 32768 | 800911 | 120923 | 10.30.140.220 | 255.255.255.0 | 10.30.140.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02441 |  |  | x | IBM MQ; Will be needed after ASP; Bank needs to check on IBM MQ licensing and if changes are needed; See traffic from FEIS server to this MQ. It will be needed longterm. This also talks with ASP. Per Eric, 6127 and 2441 will both be needed as one is UIT and the other is UAT. Requires ASP connectivity; No concerns no follow needed - jdeltoro 5/9; | N/A | MQ UIT | MQ | Installed | UAT | Applications | FIS / Open System | MQ - Obsolesence UIT | MQ UAT | UIT | UIT | No | TBD |  |  |  | No |  | No |  | Irma Ramos |  | Ana Cruz | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Linux | 4 | 4096 | 106589 | 31076 | 10.30.140.123 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02442 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | MQ Production | MQ | Disposed/Retired | OFF | Applications | FIS / Open System | MQ - Obsolesence PROD | MQ Production | Decommissioned | STAGING | No | Decommissioned |  |  |  | No |  | No |  | Irma Ramos |  | Ana Cruz |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Oracle Linux 8.10 | 4 | 4096 | 106588 | 23913 | 10.30.140.221 | 255.255.255.0
FBA02443 |  |  |  | German and MSS confirmed that these will not migrate - jdeltoro 5/12 |  | Cribl Edge for Sentinel Node 1 | Cribl Edge for Sentinel | Installed | STAGING | Applications | N/A | Cribi Edge for Sentinel Node 1 |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02443 | FBA02443.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 4 | 8192 | 161898 | 37517 | 10.30.136.40 | 255.255.255.0 | [19 empty] | No
FBA02444 |  |  |  | German and MSS confirmed that these will not migrate - jdeltoro 5/12 |  | Cribl Edge for Sentinel Node 2 | Cribl Edge for Sentinel | Installed | STAGING | Applications | N/A | Cribi Edge for Sentinel Node 2 |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA02444 | FBA02444.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 4 | 8192 | 161933 | 37614 | 10.30.136.41 | 255.255.255.0 | [19 empty] | No
FBA02446 | [5 empty] | Encompass 360 | Encompass | Installed | Production | Applications | Mortgage Sysytems | Encompass 360 |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Luzmarie Velez |  | Waldemar Velez | FBA02446 | 10.30.137.225 |  | Encompass | MR1130 | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 264303 | 75846 | 10.30.137.225 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02447 | [5 empty] | D1 Performance monitoring 1 | D1 | Installed | UIT | Applications | TSA | D1 Performance monitoring 1 |  |  | UIT | Yes | TBD |  | Yes |  | Yes |  | No |  | Sharon Gutierrez |  | John Huertas | FBA02447 | FBA02447.firstbank.local |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 315506 | 189885 | 10.30.136.85 | 255.255.255.0 | [19 empty] | Yes
FBA02448 | [5 empty] | D1 Performance monitoring 2 | D1 | Installed | UIT | Applications | TSA | D1 Performance monitoring 2 |  |  | UIT | Yes | TBD |  | Yes |  | Yes |  | No |  | Sharon Gutierrez |  | John Huertas | FBA02448 | FBA02448.firstbank.local |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 315486 | 190375 | 10.30.136.86 | 255.255.255.0 | [19 empty] | No
FBA02449 | [5 empty] | D1 Performance monitoring 3 | D1 | Installed | UIT | Applications | TSA | D1 Performance monitoring 3 |  |  | UIT | Yes | TBD |  | Yes |  | Yes |  | No |  | Sharon Gutierrez |  | John Huertas | FBA02449 | FBA02449.firstbank.local |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 315476 | 189731 | 10.30.136.87 | 255.255.255.0 | [19 empty] | No
FBA02450 | [5 empty] | MOEX eLoan Appl PROD 1 | MOEX eLoan | Installed | Production | Applications | TSA | MOEX eLoan Appl PROD 1 |  |  | Production | Yes | TBD |  |  |  | Yes |  | No | Yes | Felipe Ramos |  | Ysabel Asencio | FBA02450 | FBA02450.firstbank.local |  | Money Express Eloan | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 323734 | 323734 | 10.30.137.88 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02452 | [5 empty] | MOEX eLoan Appl PROD 2 | MOEX eLoan | Installed | Production | Applications | TSA | MOEX eLoan Appl PROD 2 |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Felipe Ramos |  | Ysabel Asencio | FBA02452 | 10.30.137.89 |  | Money Express Eloan | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 323804 | 323804 | 10.30.137.89 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02453 |  |  |  | Decommissioned per Angel - 4/2/2025 jdeltoro |  | Microsoft Purview Information Protection | Microsoft Purview Information Protection | Disposed/Retired | OFF | Applications | N/A | Microsoft Purview Information Protection |  | Decommissioned | Development | Yes | Decommissioned |  |  |  | Yes | FBA02453 | No |  | N/A |  | N/A | FBA02453 | FBBRUATFS.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2022 10.0.20348.2527 (21H2) | 4 | 8192 | 161923 | 49302 | 10.30.140.233 | 255.255.255.0
FBA02454 |  |  |  | Network Review for DMZ; Needs Storage Capacity Review; talks to FBA03116, FB65030 for DB; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15; Connection from Load Balancer to this server. Need to follow up with Hiram.; Server appears to be talking to a production database server (FBA03116) and shouldn't be according to Omar - follow up with Angel Ocasio; need to follow up at a later point due to change this coming weekend - jdeltoro 6/4; Has file server dependencies with FBA02352, FBA01021; has been moved to milestone 3 - jdeltoro 6/12 | Omar, Hiram, Angel Ocasio | Onbase24 UAT 1 - New Onbase systems | Onbase | Installed | Production | Applications | TSA | Onbase24 UAT 1 - New Onbase systems |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02454 | FBA02454.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | <not reported> | 4 | 8192 | 161880 | 35205 | 10.30.140.52 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02455 |  |  |  | Network Review for DMZ; Needs Storage Capacity Review; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15; Moved to milestone 3 per Angel - jdeltoro 10/21 | TBD | Onbase24 UAT 2 - New Onbase systems | Onbase | Installed | Production | Applications | TSA | Onbase24 UAT 2 - New Onbase systems |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02455 | FBA02455.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 161879 | 34337 | 10.30.140.64 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02456 |  |  |  | Network Review for DMZ; Needs Storage Capacity Review; it was also noted that these servers will be re-IP'ed and a clone created to replace these server on June 6th, will follow up over the next week to finalize details - jdeltoro 5/15; Moved to milestone 3 per Angel - jdeltoro 10/21 | TBD | Onbase24 UAT 3 - New Onbase systems | Onbase | Installed | Production | Applications | TSA | Onbase24 UAT 3 - New Onbase systems |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02456 | FBA02456.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 | TBD | Replicate and Re-IP | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 161881 | 33856 | 10.30.140.197 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA02457 | [5 empty] | OnBase Test | OnBase | Installed | Production | Applications | TSA | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02457 | FBA02457.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 161879 | 39574 | 10.30.140.182 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02458 | [5 empty] | Onbase Application new version | Onbase | Installed | Production | Applications | TSA | Onbase Application new version |  |  | UAT | Yes | TBD |  |  |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA02458 | FBA02458.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2582 (21H2) | 4 | 8192 | 161879 | 37980 | 10.30.140.109 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02459 | [5 empty] | FIS Snow Mid Server | FIS Snow Mid | Installed | Production | Applications | ITOMO | FIS Snow Mid Server |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | Edgardo Santiago | FBA02459 | FBA02459.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn |  | 4 | 8192 | 161896 | 40179 | 10.30.136.77 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02460 |  |  | x | ON |  | Zabbix Servers | Zabbix | Installed | Production | Applications | ITOMO | Zabbix Server | Zabbix Servers |  | STAGING | No | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | Edgardo Santiago |  |  |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn |  | 8 | 12288 | 114836 | 34399 | 10.30.136.64 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA02461 | [5 empty] | B2B Integrator 2 | IBM B2Bi | Installed | Production | Applications | TSA | B2B Integrator 2 |  |  | Production | No | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 4 | 16384 | 1760411 | 852644 | 10.30.134.128 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA02462 |  |  | x | ON |  | B2B Perimeter Server 2 | IBM B2Bi | Installed | Production | Applications | TSA | B2B Perimeter 2 | B2B Perimeter Server 2 |  | Production | No | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 4 | 4096 | 144753 | 47270 | 10.30.192.185 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA02464 | [5 empty] | Informatica Cloud Secure Agent Prod | Informatica | Installed | Production | Applications | TSA/Vallellanes | Informatica Cloud Secure Agent Prod |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | Lucy Ann Vasquez |  | José Vallellanes | FBA02464 | FBA02464.firstbank.local |  | Informatica | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 6 | 32768 | 800902 | 102168 | 10.30.137.181 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA02465 |  |  |  | Follow up with Wilson on destination of server and application to stay on-site - jdeltoro 5/8 |  | CyberArk DBA Idera JS | CyberArk | Installed | Production | Applications | CSO | CyberArk DBA Idera JS |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | Milton Rojas (CSO) |  | Wilson Figueroa/German Ferrar | FBA02465 | FBA02465.firstbank.local |  | CyberArk | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 8 | 32768 | 186499 | 79545 | 10.30.137.17 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA02466 |  |  | x | Follow up with Wilson on destination of server and application to stay on-site - jdeltoro 5/8 |  | CyberArk PSMP Server | CyberArk | Installed | Production | Applications | CSO | CyberArk PSMP | CyberArk PSMP Server |  | Production | No | TBD |  |  |  | No |  | No |  | Milton Rojas (CSO) |  | Wilson Figueroa/German Ferrar |  |  |  | CyberArk | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 4 | 4096 | 106612 | 7318 | 10.30.162.14 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA02468 |  |  |  | New VM found in Faddom - jdeltoro 7/22 |  | Onbase DocComposition 2 | Onbase | Installed | Production | Applications | N/A | [5 empty] | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | TBD | TBD |  | TBD | [7 empty] | 10.30.140.176 | 255.255.255.0 | 10.30.140.1 | [18 empty] | Yes
FBA02472 |  |  |  | New VM found in Faddom - jdeltoro 7/22; potential migration to D1 |  | D1 App Server 2 | D1 | Installed | Production | Applications | TSA | [5 empty] | TBD | [7 empty] | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | TBD | TBD |  | TBD | [7 empty] | 10.30.140.170 | [20 empty] | Yes
FBA02473 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | DynaTrace Active Gate (Synthetic Monitors) | DynaTrace | Installed | Production | Applications | ITOMO |  |  | Prod |  |  | TBD | [7 empty] | Juan Espinoza |  | Jeanson Portalatin/Harry Gonzalez |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.134.126 | [20 empty] | No
FBA02474 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | E-contracting\OnBase Web Server 2(DMZ) | OnBase | Installed | Production |  | TBD |  |  | Prod |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.192.178 | [20 empty] | Yes
FBA02475 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Win NDM UAT | IBM NDM | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.200 | [20 empty] | No
FBA02476 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | TPSS Training Server new | TPSS | Installed | STAGING | Applications | TSA |  |  | STAGING |  |  | TBD | [7 empty] | Sharon Gutierrez |  | Angel Nieves |  |  |  |  | MR1130 | FIS | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.196 | [20 empty] | No
FBA02477 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Xpress Dev Server | Xpress | Installed | STAGING | Applications | TSA |  |  | STAGING |  |  | TBD | [7 empty] | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.39 | [20 empty] | No
FBA02478 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Xpress UAT Server | Xpress | Installed | STAGING | Applications | TSA |  |  | STAGING |  |  | TBD | [7 empty] | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.207 | [20 empty] | No
FBA02479 | [5 empty] | Unknown - OLS Dev Server? | OLS | Installed | STAGING | Applications | N/A | [5 empty] | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD |  | Replicate and Re-IP | Virtual Server | poweredOn | Oracle Linux 8 |  |  |  |  | 10.30.140.227 | [20 empty] | No
FBA02480 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | LINUX NDM UAT | IBM NDM | Installed | STAGING | Applications | N/A |  |  | STAGING |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.61 | [20 empty] | No
FBA02481 |  | TBD |  | Added per email from Angel - jdeltoro 10/1; updated CMDB status and environment per Angel - jdeltoro 11/10 | N/A | eFirstClass, Online Sales | ITDG | Installed | Development |  | TBD |  |  | TBD |  |  | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | TBD | Cloud | Milestone 1 | Group 4 | TBD | Virtual Server | poweredOn | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | No CPU/RAM Info Found | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02482 |  | TBD |  | Added per email from Angel - jdeltoro 10/1; updated CMDB status and environment per Angel - jdeltoro 11/10 | N/A | eFirstClass, Online Sales | ITDG | Installed | UAT |  | TBD |  |  | TBD |  |  | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | TBD | Cloud | Milestone 1 | Group 4 | TBD | Virtual Server | poweredOn | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | No CPU/RAM Info Found |  |  |  | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA02483 | [5 empty] | Onbase App Server 1 | Onbase | Installed | UAT | Applications | TSA | [5 empty] | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | Replicate and Re-IP | Virtual Server | poweredOn | [5 empty] | 10.30.140.17 | 255.255.255.0 | 10.30.140.1 | [8 empty] | No CPU/RAM Info Found | [9 empty] | No
fba02484 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | OnBase DocComposition 2 | Onbase | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.176 | [20 empty] | No
FBA02485 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | OnBase Webclient 2 | Onbase | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.177 | [20 empty] | No
FBA02486 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | AUTO App Server 1 | AUTO App | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.11 | [20 empty] | No
FBA02487 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | MOEX App Server 1 | MOEX eLoan | Installed | UAT | Applications | TSA |  |  | UAT |  |  | TBD | [7 empty] | Felipe Ramos |  | Ysabel Asencio |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.182 | [20 empty] | No
FBA02488 |  |  |  | New VM reported by Angel Lopez; potential migraiton to D1 - jdeltoro 7/24 |  | D1 App Server 2 | D1 | Installed | UAT | Applications | TSA |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.170 | [20 empty] | No
FBA02489 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | OnBase Import Processor Server | Onbase | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.197 | [20 empty] | No
FBA02490 |  |  |  | New VM per ticket CH25000178889 in CMC - jdeltoro 7/30 |  | Varonis Hub 1 | Varonis | Installed | STAGING |  | TBD | [5 empty] | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | [5 empty] | TBD | [20 empty] | Yes
FBA02491 |  |  |  | New VM per ticket CH25000178889 in CMC - jdeltoro 7/30 |  | Varonis Hub 2 | Varonis | Installed | STAGING | Applications | N/A | [5 empty] | TBD | [7 empty] | Juan Espinoza |  | Luis Arvelo |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | [5 empty] | 10.30.137.59 | [20 empty] | Yes
FBA02492 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Cribl Edge for Sentinel Node 3 | Cribl Edge | Installed | Production | Monitoring | N/A |  |  | Prod |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.46 | [20 empty] | No
FBA02493 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Cribl Edge for Sentinel Node 4 | Cribl Edge | Installed | Production | Monitoring | N/A |  |  | Prod |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.47 | [20 empty] | No
FBA02494 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Apple Pay UIT | Apple Pay | Installed | UIT | Applications | N/A |  |  | UIT |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.178 | 255.255.255.0 | 10.30.150.1 | [18 empty] | No
FBA02495 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | Apple Pay UAT | Apple Pay | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.179 | 255.255.255.0 | 10.30.150.1 | [18 empty] | No
FBA02496 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | FIS Snow Mid Server 2 | FIS Snow Mid | Installed | STAGING | Monitoring | N/A |  |  | STAGING |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.78 | [20 empty] | Yes
FBA02498 |  |  |  | Part of Apple Pay project - jdeltoro 9/18 |  | TBD | TBD | No Match | No Match |  | TBD |  |  | UAT |  |  | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | Cloud | TBD | TBD | TBD | Virtual Server | poweredOn | TBD | TBD | TBD | TBD | TBD | TBD | [10 empty] | No CPU/RAM Info Found
FBA02499 |  |  |  | Part of Apple Pay project - jdeltoro 9/18 |  | TBD | TBD | No Match | No Match |  | TBD |  |  | UIT |  |  | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | Cloud | TBD | TBD | TBD | Virtual Server | poweredOn | TBD | TBD | TBD | TBD | TBD | TBD | [10 empty] | No CPU/RAM Info Found
FBA03018 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2008 Reporting Services | SQL 2008 Reporting Services | Installed | Production | Database | N/A | SQL 2008 Reporting Services | SQL 2008 Reporting Services |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03018 | FBA03018.firstbank.local |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Virtual Server | poweredOn | Win2008R2 6.1.7601 | 2 | 4096 | 311380 | 311380 | 10.30.137.50 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA03022 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2012 INTRA-SQL-SPCLUSTER | SQL 2012 INTRA-SQL-SPCLUSTER | No Match | No Match | No Match | N/A | SQL 2012 INTRA-SQL-SPCLUSTER |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.66 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03025 | [5 empty] | E3 SQL Production Server (Win2008R2 6.1.7601) | E3 SQLuction(Win2008R2 6.1.7601) | Installed | Production | Database | N/A | E3 SQL Production Server (Win2008R2 6.1.7601) |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA03025 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.5850 (1607) |  |  |  |  | 10.30.130.134 | 255.255.255.0 | [19 empty] | No
FBA03027 | [5 empty] | Xamine & Express Upgrade DB Monitor | Xamine | Installed | Production | Applications | TSA/CDO | Xamine & Express Upgrade DB Monitor | Xamine & Express Upgrade DB Monitor |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez/Eric Lopez | FBA03027 | FBA03027.firstbank.local |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 233578 | 233578 | 10.30.130.49 | 255.255.255.0 |  |  | 10.100.130.49 | [16 empty] | Yes
FBA03031 | [5 empty] | Pervasive DB - SQN | SQN | Installed | Production | Applications | TSA | Pervasive DB - SQN | Pervasive DB - SQN |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Karla de Jesus |  | Nayda Reyes | FBA03031 | FBA03031.firstbank.local |  | SQN | MR1130 | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 362582 | 362582 | 10.30.130.230 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA03031old | [5 empty] | Pervasive DB - SQN | Pervasive DB - SQN | Disposed/Retired | OFF | Database | N/A | Pervasive DB - SQN | Pervasive DB - SQN | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA03031old | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA03054 |  |  |  | Moving to Sharepoint Online - No Migration |  | Sharepoint UAT Reporting Services | Sharepoint Reporting Services | Installed | UAT | Applications | N/A | Sharepoint UAT Reporting Services | Sharepoint UAT Reporting Services |  | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA03054 | FBA03054.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012 6.2.9200 | 4 | 4096 | 311440 | 88205 | 10.30.140.164 | [20 empty] | No
FBA03056 |  |  |  | Moving to Sharepoint Online - No Migration; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | Sharepoint UAT Reporting Services | Sharepoint Reporting Services | OFF | OFF | Applications | N/A | Sharepoint UAT Reporting Services | Sharepoint UAT Reporting Services |  | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA03056 | FBA03056.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012 6.2.9200 | 4 | 8192 | 315494 | 96807 | 10.30.140.165 | [20 empty] | No
FBA03057 | [5 empty] | Sharepoint Prod Internal Reporting Services | Sharepoint Internal Reporting Services | Installed | Production | Applications | N/A | Sharepoint Prod Internal Reporting Services | Sharepoint Prod Internal Reporting Services |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA03057 |  |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 516178 | 516178 | 10.30.130.102 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
fba03058 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | B2Bi DB2 Development Server | B2Bi DB2elopment | Disposed/Retired | OFF | Database | Miguel Mejias/Luis Arvelo | B2Bi DB2 Development Server | B2Bi DB2 Development Server | Decommissioned | UAT | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 6144 | 211068 | 201765 | 10.30.140.8 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
fba03059 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL PCI SQL Cluster Name | SQL SQL Cluster Name | No Match | No Match | No Match | N/A | SQL PCI SQL Cluster Name |  |  | Production | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.147.7 | [10 empty] | No CPU/RAM Info Found
FBA03061 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | PCI SQL DTC | SQL DTC | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.147.9 | [10 empty] | No CPU/RAM Info Found
fba03062 |  |  |  | Follow up with Iran Rodrigez to discuss B2Bi and Sterling - jdeltoro 5/7 |  | B2Bi DB2 Development Server (LINUX)PROD | IBM B2Bi | Installed | Production | Database | TSA | B2Bi DB2 Development Server (LINUX)PROD | B2Bi DB2 Development Server (LINUX)PROD |  | Production | No | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.102.1.0.1.el7.x86_64) | 2 | 6144 | 415850 | 200182 | 10.30.134.17 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | Yes
fba03063 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | B2Bi DB2 Development Server (LINUX)COB | B2Bi DB2elopment(LINUX)COB | Disposed/Retired | OFF | Database | Miguel Mejias/Luis Arvelo | B2Bi DB2 Development Server (LINUX)COB | B2Bi DB2 Development Server (LINUX)COB | Decommissioned | Contingency | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.105.1.0.2.el7.x86_64) | 2 | 8192 | 233878 | 169921 | 10.19.137.63 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
FBA03065 |  |  | x | Follow up with Omar - jdeltoro 5/8 |  | SQL 2008 PCI SQL Cluster COB | SQL 2008 SQL Cluster COB | No Match | No Match | No Match | N/A | SQL 2008 PCI SQL Cluster COB |  |  | Contingency | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A | FBA03065 |  |  |  | Santurce 1519 | Onsite | Shared Infrastructure |  | TBD | [7 empty] | 10.19.147.7
FBA03069 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2012 Cluster Name | SQL 2012 Cluster Name | No Match | No Match | No Match | N/A | SQL 2012 Cluster Name |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03069 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.105 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03072 |  |  |  | Reviewed with Omar - no concerns; |  | SQL Server for APPRO - PCI - Instance Name - Cluster Node with FBA03059 | SQLfor APPRO - Instance Name - Cluster Node with FBA03059 | No Match | No Match | No Match | TSA/Auto | Not Found |  |  |  | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | Lucy Ann Vasquez/Omar Ramos |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | [7 empty] | 10.30.147.12 | [10 empty] | No CPU/RAM Info Found
FBA03073 |  |  | x | Validate No Migrate |  | DR - APPRO MSSQL 2016 | DR - APPRO MSSQL 2016 | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | Lucy Ann Vasquez/Omar Ramos | FBA03073 |  |  |  | Santurce 1519 | Onsite | Milestone 3 |  | No Migration | [7 empty] | 10.19.147.11
FBA03074 |  |  |  | Reviewed with Omar - no concerns; |  | Digital Banking - SQL Data Analyzer - UIT | Digital Banking | Installed | Development | Database | N/A | Digital Banking - SQL Data Analyzer - UIT | Digital Banking - SQL Data Analyzer - UIT |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03074 | FBA03074.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7159 (1607) | 4 | 8192 | 417904 | 417904 | 10.30.140.51 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA03075 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Digital Banking - SQL Database Server - UIT | Digital Banking | Disposed/Retired | OFF | Database | N/A | Digital Banking - SQL Database Server - UIT | Digital Banking - SQL Database Server - UIT | Decommissioned | OFF | No | In Progress |  |  |  | No | FBA03075 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA03079 |  |  |  | Reviewed with Omar - no concerns; |  | Digital Banking - SQL Database Analyzer - UAT | Digital Banking | Installed | UAT | Database | N/A | Digital Banking - SQL Database Analyzer - UAT | Digital Banking - SQL Database Analyzer - UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03079 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 374963 | 374963 | 10.30.140.27 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA03084 |  |  |  | Discovered that this server was missing from workbook by ASP team. Appears to be another physical Oracle server. - jdeltoro 9/18 |  | TPSS Database (LINUX) - Oracle Rack 12c | TPSS | No Match | No Match |  | TBD |  |  | TBD |  |  | TBD | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Physical Server | poweredOn | TBD |  |  |  |  | 10.30.130.192
FBA03085 | [5 empty] | OneSumX DataBase (SIT) Outsystem | OneSumX | Installed | UAT | Applications | Compliance | OneSumX DataBase (SIT) | OneSumX DataBase (SIT) |  | UAT | Yes | In Progress |  |  |  | Yes |  | Yes |  | Luana Santos |  | Dennis Hernandez | FBA03085 | FBA03085.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 16384 | 6543469 | 3641266 | 10.30.140.118 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA03087 | [5 empty] | SQL Data Provisioning | Data Provisioning | Installed | Production | Database | CDO | SQL Data Provisioning | SQL Data Provisioning |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Julio Rivas |  | Gustavo Rodriguez | FBA03087 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.4499 (1809) | 8 | 32768 | 5964078 | 5964078 | 10.30.130.115 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA03089 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | Large Cash Instance - SQL Server Outsystem | Large Cash Instance - SQLOutsystem | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.147.14 | [10 empty] | No CPU/RAM Info Found
FBA03090 |  |  | x | Validate No Migrate |  | DR - OneSumX | DR - OneSumX | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03090 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | [7 empty] | 10.19.147.12
FBA03092 | [5 empty] | CUC DB Server | D1 | Installed | Development | Database | TSA | CUC DB Server | CUC DB Server |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas | FBA03092 | FBA03092.firstbank.local |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 528591 | 162028 | 10.30.140.71 | 255.255.255.0 |  |  | 10.100.140.71 | [16 empty] | No
FBA03095 |  |  |  | Reviewed with Omar - no concerns; |  | Digital Banking - SQL Analyzer - PROD | Digital Banking | Installed | Production | Database | N/A | Digital Banking - SQL Analyzer - PROD | Digital Banking - SQL Analyzer - PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03095 |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 8401358 | 4217319 | 10.30.130.119 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA03096 |  |  |  | Needs discussion on AVD; Interfaces with D1 and OnBase; DB is Pervasive version 14; Needs follow up with D1 SME - port 80 connectivity from D1 related systems - jdeltoro 5/15 | TBD | SQN Sentry Test | SQN | Installed | Development | Applications | TSA | SQN Sentry Test | SQN Sentry Test |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Fernando Rodriguez, Nayda Reyes | FBA03096 | FBA03096.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 362592 | 161737 | 10.30.140.122 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA03099 |  |  |  | Follow up with Ana Cruz; FIS Core |  | GFT Database Test - Upgrade | GFT | Installed | UAT | Database | N/A | GFT Database Test - Legacy | GFT Database Test - Upgrade |  | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03099 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 661627 | 661627 | 10.30.158.186 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA03099-2016 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | GFT DB Test Legacy | GFT | Disposed/Retired | OFF | Applications | N/A |  |  | Decommissioned |  |  | Decommissioned | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | N/A | N/A | No Migration | Virtual Server | poweredOff | Microsoft Windows Server 2016 |  |  |  |  | 10.30.158.186 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6
FBA03099-2022 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Database | N/A | GFT Database Test - ISO2022 |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA03099-2022 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 16384 | 661593 | 661593 | 10.30.140.4 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA03100 | [5 empty] | GFT Database Server PROD - Upgrade | GFT | Installed | Production | Database | N/A | GFT Database Server PROD - Upgrade | GFT Database Server PROD - Upgrade |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 835700 | 370936 | 10.30.157.202 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | Yes
FBA03101 |  |  | x | Validate No Migrate |  | GFT DB Server COB - Upgrade | GFT | Installed | Contingency | Database | N/A | GFT DB Server COB - Upgrade | GFT DB Server COB - Upgrade |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03101 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 913301 | 438451 | 10.19.157.202 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA03101Clone |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Temporary Server for GFT DR Validation | GFT | Disposed/Retired | OFF | Database | N/A | Temporary Server for GFT DR Validation | Temporary Server for GFT DR Validation | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA03101Clone | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff | [16 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6
FBA03102 | [5 empty] | D1 SPE\PROD - SQL 2016 Server Node 1 | D1 | Installed | Production | Database | TSA | D1 SPE\PROD - SQL 2016 Server Node 1 | D1 SPE\PROD - SQL 2016 Server Node 1 |  | Production | Yes | TBD | Yes | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 |  | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 24 | 65536 | 2284911 | 2284911 | 10.30.147.17 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | [8 empty] | No
FBA03103 | [5 empty] | Paragon 6 New | Paragon | Installed | Production | Applications | Treasury Accounting | Paragon 6 New | Paragon 6 New |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Javier Cabrera |  | Neidy Kinney | FBA03103 | FBA03103.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 221305 | 221305 | 10.30.130.70 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA03104 |  |  | x | Validate No Migrate |  | Paragon COB New | Paragon | Installed | Contingency | Applications | Treasury Accounting | Paragon DR | Paragon COB New |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | Javier Cabrera |  | Neidy Kinney | FBA03104 |  |  | Paragon | Arterial | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 323914 | 279213 | 10.20.102.70 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA03105 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL Reporting Services | SQL Reporting Services | Installed | Production | Database | N/A | SQL Reporting Services | SQL Reporting Services |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03105 | FBA03105.firstbank.local |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 438360 | 438360 | 10.30.130.48 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA03106 | [5 empty] | D1 SPE\PROD - SQL 2016 Server Node 2 | D1 | Installed | Production | Database | TSA | D1 SPE\PROD - SQL 2016 Server Node 2 | D1 SPE\PROD - SQL 2016 Server Node 2 |  | Production | Yes | TBD |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 24 | 65536 | 2284699 | 2284699 | 10.0.23.1, 10.30.147.18, 169.254.2.247 |  |  |  | 10.10.23.1, 10.30.147.18, 169.254.2.247 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA03107 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2016 Windows Cluster Name | SQL 2016 Windows Cluster Name | No Match | No Match | No Match | N/A | SQL 2016 Windows Cluster Name |  |  | Production | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.147.19 | [10 empty] | No CPU/RAM Info Found
FBA03109 |  |  |  | No Concerns |  | APPRO 3.5 SQL UAT | APPRO | Installed | UAT | Database | TSA | APPRO 3.5 SQL UAT | APPRO 3.5 SQL UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | Lucy Ann Vasquez | FBA03109 | FBA03109.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 7 | 6144 | 1644633 | 848288 | 10.30.140.41 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA03110 | [5 empty] | D1 Prod Database Instance | D1 | No Match | No Match | No Match | TSA | Not Found |  |  |  | Yes | TBD |  | Yes |  | No |  | No |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 |  | N/A | N/A | D1 | [7 empty] | 10.30.147.20 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA03111 |  |  |  | For SQL 2012; To be decommissioned; No Migrate per Omar |  | IBM Security Guardium V10 Colector | IBM Security Guardium V10 Colector | Installed | Production | Security | N/A | IBM Security Guardium V10 Colector | IBM Security Guardium V10 Colector | Staging | STAGING | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.199 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FBA03112 |  |  |  | For SQL 2005; To be decommissioned; No Migrate per Omar |  | IBM InfoSphere Guardium V9.5 Colector | IBM InfoSphere Guardium V9.5 Colector | Installed | Production | Security | N/A | IBM InfoSphere Guardium V9.5 Colector | IBM InfoSphere Guardium V9.5 Colector | Staging | STAGING | No | Pending |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.30.130.101 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [10 empty] | Physical Server
FBA03113 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2016 Windows Cluster Name | SQL 2016 Windows Cluster Name | No Match | No Match | No Match | N/A | SQL 2016 Windows Cluster Name |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03113 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.237 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03114 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2016 Windows Cluster Name | SQL 2016 Windows Cluster Name | No Match | No Match | No Match | N/A | SQL 2016 Windows Cluster Name |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03114 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.139 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03115 |  |  |  | Reviewed with Omar - no concerns; |  | SQL 2016 - BDI Bancware - PROD | Bancware | No Match | No Match | No Match | Financial Planning | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | Maria Medina |  | Maria Medina | FBA03115 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | [7 empty] | 10.30.130.37 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03116 | [5 empty] | SQL 2016 - CPE_PROD; Onbase; AssistCk DB's | SQL 2016 - CPE_; Onbase; AssistCk DB's | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | Omar Ramos | FBA03116 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | [7 empty] | 10.30.130.142 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03117 |  |  |  | To Be Decommissioned; No Migrate |  | SQL 2016 - BDI Bancware - UAT | Bancware | No Match | No Match | No Match | Financial Planning | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | Maria Medina |  | Maria Medina | FBA03117 |  |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 3 | TBD | [7 empty] | 10.30.130.143 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03119 |  |  |  | No Concerns from Omar - Dependendency for FBA02001 - MSSQL Server |  | SQL 2017 Instance - Prod; contains CardWizard DB, ReconFrontier Plus | SQL 2017 Instance ; contains CardWizard DB, ReconFrontier Plus | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03119 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | Physical Server | [6 empty] | 10.30.130.145 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03125 |  |  |  | No Migrate |  | New BigFix Server | New BigFix | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | Cristina Rodriguez |  | N/A | FBA03125 | [5 empty] | N/A | N/A | No Migration | [7 empty] | 10.30.130.131 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA03126 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | ISIM Database | ISIM | Disposed/Retired | OFF | Database | N/A | ISIM Database | ISIM Database | Decommissioned | STAGING | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03126 | FBA03126.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 221334 | 221334 | 10.30.130.60 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6
FBA03129 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03129 | FBA03129.firstbank.local |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.71.45 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FBA03130 |  |  | x | Validate No Migrate - Arterial - Follow up with Omar per Edgardo - jdeltoro 5/13 |  | DR (Used for SQL database restores) | DR (Used for SQL database restores) | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03130 | FBA03130.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | [7 empty] | 10.20.16.45 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA03131 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03131 | 10.30.71.47 |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.71.47
FBA03132 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03132 | 10.30.71.48 |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.71.48
FBA03133 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03133 | 10.30.71.49 |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.71.49
FBA03134 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03134 | 10.30.71.50 |  |  |  |  | N/A | N/A | No Migration | [7 empty] | 10.30.71.50
FBA03136 | [5 empty] | Roll de DTC para el cluster FBA03113 | Roll de DTC para el cluster FBA03113 | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03136 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | [7 empty] | 10.30.130.238 | 255.255.255.0
fba03140 | [5 empty] | Digital Banking - SQL Server 2017 Production | Digital Banking | Installed | Production | Database | N/A | DigitalBanking - SQL Server 2017 Production | DigitalBanking - SQL Server 2017 Production |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba03140 | fba03140.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 16 | 262144 | 17394353 | 17394353 | 10.30.130.31 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E32-16s_v6 | 16 | 256 | [6 empty] | No
FBA03141 | [5 empty] | Historical Commerical Statements - Tutela; SQL Server; Runs APPROCRA on MSSQL SSI Project |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03141 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | [7 empty] | 10.30.130.175 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03142 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL Windows Server 2019 Cluster | SQL Windows019 Cluster | No Match | No Match | No Match | N/A | SQL Windows Server 2019 Cluster |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03142 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.159 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03145 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens Identity and Access Management (XIAM) - DB Server | Xapiens | Installed | UAT |  | TBD |  |  | UAT |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.165.11 | [20 empty] | Yes
FBA03147 | [5 empty] | DebtManager SQL Integration Services Prod | DebtManager | Installed | Production | Applications | Sheila Ponte | DebtManager SQL Integration Services Prod | DebtManager SQL Integration Services Prod |  | Production | Yes | TBD | Yes |  |  | Yes |  | Yes |  | Santitos Rivas |  | Geraldo Reyes | FBA03147 |  |  | DebtManager | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 12 | 32768 | 805752 | 805752 | 10.30.148.92 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA03148 | [5 empty] | Digital Banking - SQL Server Prod - Upgrade | Digital Banking | Installed | Production | Database | N/A | DigitalBanking - SQL Server - Pilot | DigitalBanking - SQL Server Prod - Upgrade |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03148 | FBA03148.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 32768 | 16604362 | 16456397 | 10.30.130.140 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA03149 |  |  |  | Follow up with Omar - jdeltoro 5/8 |  | SQL 2016 Windows Cluster Name | SQL 2016 Windows Cluster Name | No Match | No Match | No Match | N/A | SQL 2016 Windows Cluster Name |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA03149 |  |  |  | MR1130 | Cloud | Shared Infrastructure |  | TBD | [7 empty] | 10.30.130.223 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA03150 | [5 empty] | Sharepoint SQL Server 2016 - Cluster Node | Sharepoint SQL016 - Cluster Node | No Match | No Match | No Match | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | No |  | No |  | Juan Espinoza |  | N/A | FBA03150 | [5 empty] | N/A | N/A | No Migration | [7 empty] | 10.30.130.224
FBA03151 |  |  |  | Follow up on Guardium discussions; Fernando confirmed the FirstBank team is following up on Monday 5/12 - jdeltoro 5/9 |  | IBM GDE CipherTrust Manager 1 - Appliance - Guardium | Guardium | Installed | STAGING | Database | N/A | IBM GDE CipherTrust Manager 1 - Appliance | IBM GDE CipherTrust Manager 1 - Appliance |  | STAGING | No | TBD |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Onsite | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 4 | 16384 | 118889 | 118889 | 10.30.130.213 | 255.255.255.0 | [19 empty] | No
FBA03152 |  |  |  | Follow up on Guardium discussions; Fernando confirmed the FirstBank team is following up on Monday 5/12 - jdeltoro 5/9 |  | IBM GDE CipherTrust Manager 2 - Appliance - Guardium | Guardium | Installed | STAGING | Database | N/A | IBM GDE CipherTrust Manager 2 - Appliance | IBM GDE CipherTrust Manager 2 - Appliance |  | STAGING | No | TBD |  |  |  | No |  | Yes |  | N/A |  | Omar Ramos / Luis Charti |  |  |  | Guardium | MR1130 | Onsite | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn |  | 4 | 16384 | 118900 | 118900 | 10.30.130.214 | 255.255.255.0 | [19 empty] | No
FBA03153 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens Identity and Access Management (XIAM) - DB Server Prod | Xapiens | Installed | Production |  | TBD |  |  | Prod |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.167.5 | [20 empty] | Yes
FBA03154 |  |  |  | Part of digital banking; this will go away |  | Elastic UAT - Digital Banking | Elastic - Digital Banking | Installed | UAT | Database | N/A | Elastic UAT | Elastic UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03154 | FBA03154.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 16384 | 221340 | 221340 | 10.30.140.236 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | [6 empty] | No
FBA03155 |  |  |  | Part of digital banking; this will go away |  | Elastic PROD - Digital Banking | Elastic - Digital Banking | Installed | Production | Database | N/A | Elastic PROD | Elastic PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03155 | FBA03155.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 32768 | 237957 | 237957 | 10.30.137.35 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | No
FBA03156 |  |  |  | Part of digital banking; this will go away |  | Elastic UIT - Digital Banking | Elastic - Digital Banking | Installed | UIT | Database | N/A | Elastic UIT | Elastic UIT |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA03156 | FBA03156.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 16384 | 221279 | 221279 | 10.30.140.237 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | [6 empty] | No
fba03157 |  |  | x | Oracle Cloud |  | ERP Integration Server Oracle Cloud OCI PROD | ERP IntegrationOracle Cloud OCI | Installed | Production | Database | N/A | ERP Integration Server Oracle Cloud OCI PROD | ERP Integration Server Oracle Cloud OCI PROD |  | Production | No | Pending |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (4.14.35-2047.530.5.1.el7uek.x86_64) |  |  |  |  | 10.179.4.105, 192.168.16.18 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
fba03158 | Yes |  | x | Oracle Cloud |  | ERP Integration Server Oracle Cloud OCI TEST | ERP IntegrationOracle Cloud OCI | Installed | UAT | Database | N/A | ERP Integration Server Oracle Cloud OCI TEST | ERP Integration Server Oracle Cloud OCI TEST |  | UAT | No | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (4.14.35-2047.530.5.1.el7uek.x86_64) |  |  |  |  | 10.179.4.178, 192.168.16.18 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
FBA03159 |  |  |  | New DB2 Server for Control Center Application; Was marked as onsite but doesn't make sense as other B2B are moving to Azure mjm 5/16/25 | N/A | New B2B DB2 Dev Server | IBM B2Bi | Installed | Development | Database | TSA | New B2B DB2 Dev Server | New B2B DB2 Dev Server | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.320.7.1.el8uek.x86_64) | 4 | 4096 | 285790 | 217560 | 10.30.140.81 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
fba03160 |  |  | x | ON |  | B2B Oracle 8 PROD 1 | IBM B2Bi | Installed | Production | Database | TSA | B2B DB2 oracle 8 prod 1 | B2B Oracle 8 PROD 1 |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.328.3.el8uek.x86_64) | 4 | 16384 | 298133 | 236240 | 10.30.130.188 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA03161 | [5 empty] | B2B DB2 oracle 8 prod 2 | IBM B2Bi | Installed | Production | Database | TSA | B2B DB2 oracle 8 prod 2 |  |  | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Luis Arvelo/Iran Rodriguez/ENIAC |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.333.5.el8uek.x86_64) | 4 | 16384 | 298134 | 235884 | 10.30.130.189 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA03163 |  |  |  | New VM reported by Angel Lopez; potential migration to D1 - jdeltoro 7/24 |  | D1 Encryption Test Server | D1 | Installed | UAT | Database | TSA |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | John Huertas |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.134 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | [8 empty] | No
FBA04006 | [5 empty] | DIR-SYNC ¦ Azure AD Microsoft O365 | DIR-SYNC ¦ Azure AD Microsoft O365 | Installed | Production | Database | N/A | DIR-SYNC ¦ Azure AD Microsoft O365 | DIR-SYNC ¦ Azure AD Microsoft O365 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA04006 | FBA04006.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 131189 | 131189 | 10.30.137.37 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA04007 | [5 empty] | Exchange Test 2019 | Exchange 2019 | Installed | Production | Exchange | N/A | Exchange 2019 | Exchange Test 2019 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA04007 | FBA04007.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213092 | 146482 | 10.30.137.26 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | [8 empty] | Yes
FBA04009 |  |  |  | Edgardo to follow up on other applications installed on this server; possibly Azure AD sync - jdeltoro 5/13 |  | eDiscovery (Azure AD/Entra Sync) | eDiscovery (Azure AD/Entra Sync) | Installed | Production | Applications | N/A | eDiscovery | eDiscovery |  | Production | Yes | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA04009 | FBA04009.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 8192 | 315499 | 315499 | 10.30.137.113 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA04014 | [5 empty] | New RightFax Server | New RightFax | Installed | Production | Applications | N/A | New RightFax Server | New RightFax Server |  | Production | Yes | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA04014 | FBA04014.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 161923 | 161923 | 10.30.137.212 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA04015 | [5 empty] | New RightFax | New RightFax | Installed | Production | Applications | N/A | New RightFax | New RightFax |  | Production | Yes | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA04015 | FBA04015.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 161935 | 161935 | 10.30.137.213 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA05046 | [5 empty] | VDI Horizon CS | VDI Horizon CS | Installed | Production | Applications | Multiple VDI Users | VDI Horizon CS | VDI Horizon CS |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05046 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 196462 | 121987 | 10.30.180.20 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA05047 | [5 empty] | VDI Horizon Composer | VDI Horizon Composer | Installed | Production | Applications | Multiple VDI Users | VDI Horizon Composer | VDI Horizon Composer |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05047 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 102422 | 57514 | 10.30.180.21 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA05048 | [5 empty] | VDI Horizon APPVOLUMES-01 | VDI Horizon APPVOLUMES-01 | Installed | Production | Applications | Multiple VDI Users | VDI Horizon APPVOLUMES-01 | VDI Horizon APPVOLUMES-01 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05048 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 102422 | 65130 | 10.30.180.22 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | [8 empty] | Yes
FBA05049 | [5 empty] | VDI Horizon-RDS-01 - Possisble mistake in role | VDI Horizon-RDS-01 - Possisble mistake in role | Installed | Production | Applications | Multiple VDI Users | VDI Horizon-RDS-01 | VDI Horizon-RDS-01 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05049 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 249656 | 185198 | 10.30.82.12 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | [8 empty] | No
FBA05056 | [5 empty] | VDI- Horizon-RDS-APPRO | VDI Horizon | Installed | Development | Utilities | Multiple VDI Users | VDI- Horizon-RDS-APPRO | VDI- Horizon-RDS-APPRO |  | Development | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05056 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 251581 | 154544 | 10.30.82.14 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA05057 | [5 empty] | VDI- Horizon-RDS-APPRO-02 | VDI Horizon | Installed | Development | Utilities | Multiple VDI Users | VDI- Horizon-RDS-APPRO-02 | VDI- Horizon-RDS-APPRO-02 |  | Development | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA05057 |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 220473 | 142066 | 10.30.82.75 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA05058 |  |  |  | Part of VMware Horizon VDI infrastructure and no migration - jdeltoro 7/24 |  | VDI Horizon EDGE | VDI Horizon EDGE | Installed | Production | Utilities | Multiple VDI Users |  |  | STAGING |  |  | TBD | [7 empty] | Juan Espinoza |  | Rafael Perez/Carlos Castillo |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Red Hat Enterprise Linux 6 |  |  |  |  | 10.30.180.24 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA06006 |  |  |  | Check if on obsolete list |  | VM Server 2008 R2 para Develop - replaced by fba02276 | VM008 R2 para develop - replaced by fba02276 | Disposed/Retired | OFF | Utilities | N/A | VM Server 2008 R2 para Develop | VM Server 2008 R2 para Develop | Decommissioned | Development | Yes | Pending |  |  |  | Yes | FBA06006 | Yes |  | N/A |  | N/A | FBA06006 | FBA06006.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2008R2 6.1.7601 | 2 | 4096 | 362578 | 354816 | 10.30.140.34 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA06007 | Yes |  |  |  |  | VM Server 2003 para Develop | VM003 para develop | Available | OFF | Utilities | N/A | VM Server 2003 para Develop | VM Server 2003 para Develop |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA06009 | Yes |  |  |  |  | VM Suse 11.4 para Develop | VM Suse 11.4 para develop | Available | OFF | Applications | N/A | VM Suse 11.4 para Develop | VM Suse 11.4 para Develop |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA06011 | Yes |  |  | Decommissioned per Angel - jdeltoro 5/7 |  | VM Suse 11.4 para Develop - UIT | VM Suse 11.4 para develop | Disposed/Retired | OFF | Applications | N/A | VM Suse 11.4 para Develop - UIT | VM Suse 11.4 para Develop - UIT | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06011 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA06025 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Security | N/A | Proxy Mbanking | 0 | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06025 | No |  | N/A |  | N/A |  | fba02257.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 4096 | 20679 | 18638 | 10.30.140.155 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6
FBA06029 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Recon Batch Server | Recon Batch | Disposed/Retired | OFF | Applications | N/A | Recon Batch Server | Recon Batch Server | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06029 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA06040 | Yes |  |  |  |  | Recon Batch Server (UAT) | Recon Batch | Disposed/Retired | OFF | Applications | N/A | Recon Batch Server (UAT) | Recon Batch Server (UAT) |  | OFF | Yes | TBD |  |  |  | No | FBA06040 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [7 empty] | 10.30.140.169 | [10 empty] | No CPU/RAM Info Found
FBA06048 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | SharePoint ¦ Active Directory ¦ DMZ | SharePoint ¦ Active Directory ¦ DMZ | Disposed/Retired | OFF | Applications | N/A | SharePoint ¦ Active Directory ¦ DMZ | SharePoint ¦ Active Directory ¦ DMZ | Decommissioned | OFF | No | Pending |  |  |  | No | FBA06048 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA06093 |  |  |  | Per Edgardo - This needs follow up with Eric; this is Xpress and should be going to FIS - jdeltoro 5/13 |  | XESP1 zLinux Migration (Xpress) | Xpress | Installed | Production | Applications | TSA | XESP1 zLinux Migration | XESP1 zLinux Migration |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 18432 | 264311 | 139494 | 10.30.134.171 | 255.255.255.0 |  |  | 10.100.134.171 | [6 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | [8 empty] | No
FBA06093temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBA06093temp | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.2.el8uek.x86_64) | 4 | 8192 | 254074 | 128901 | 10.30.134.135 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA06094 |  |  |  | Per Edgardo - This needs follow up with Eric; this is Xpress and should be going to FIS - jdeltoro 5/13 |  | XESP2 zLinux Migration (Xpress) | Xpress | Installed | Production | Applications | TSA | XESP2 zLinux Migration | XESP2 zLinux Migration |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 18432 | 264339 | 138113 | 10.30.134.172 | 255.255.255.0 |  |  | 10.100.134.172 | [16 empty] | No
FBA06094temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBA06094temp | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.2.el8uek.x86_64) |  |  |  |  | 10.30.134.136
FBA06095 |  |  |  | Shannon to follow up with Mike on Group Obsolete; Marked as Milestone 2, but non-prod servers are marked as Group Obsolete - needs follow up with Omar - jdeltoro 5/7; also follow up on D1 question |  | OLSPRD1 zLinux Migration | OLS | Installed | Production | Applications | TSA | OLSPRD1 zLinux Migration | OLSPRD1 zLinux Migration |  | Production | No | Pending |  | Yes |  | No |  | Yes |  | Sharon Gutierrez |  | Eric Lopez |  |  |  | OLS | MR1130 | Cloud | Milestone 2 | Group 5 | D1 | Virtual Server | poweredOn |  | 2 | 4096 | 24657 | 24657 | 10.30.134.173 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA06096 |  |  |  | Shannon to follow up with Mike on Group Obsolete; Marked as Milestone 2, but non-prod servers are marked as Group Obsolete - needs follow up with Omar - jdeltoro 5/7; also follow up on D1 question |  | OLSPRD2 zLinux Migration | OLS | Installed | Production | Applications | TSA | OLSPRD2 zLinux Migration | OLSPRD2 zLinux Migration |  | Production | No | Pending |  |  |  | No |  | Yes |  | Sharon Gutierrez |  | Eric Lopez |  |  |  | OLS | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn |  | 2 | 4096 | 24657 | 24657 | 10.30.134.174 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA06102 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | LOGICP2 zLinux Migration | LOGICP2 zLinux Migration | Disposed/Retired | OFF | Applications | N/A | LOGICP2 zLinux Migration | LOGICP2 zLinux Migration | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06102 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06108 |  |  |  | There may be a new NDM server; Edgardo to follow up with Eric - jdeltoro 5/13 |  | MSPTEST zLinux Migration ( MSP NDM Production Server )- Connected with Digital Banking | MSP | Installed | Production | Applications | N/A | MSPTEST zLinux Migration ( MSP NDM Production Server ) | MSPTEST zLinux Migration ( MSP NDM Production Server ) |  | Production | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn |  | 2 | 4096 | 40019 | 40019 | 10.30.134.186 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA06111 |  |  |  | Follow up with Omar - Dependency on FB65030 MSSQL server; ; Waiting on FBA06120 and FBA06122 refresh |  | OLSUAT1 zLinux Migration | OLS | Installed | UAT | Applications | TSA | OLSUAT1 zLinux Migration | OLSUAT1 zLinux Migration |  | UAT | No | Pending |  |  |  | No |  | Yes |  | Sharon Gutierrez |  | Eric Lopez | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group Obsolete | TBD | Virtual Server | poweredOn |  | 2 | 4096 | 24659 | 24659 | 10.30.140.172 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA06112 |  |  |  | Follow up with Omar - Dependency on FB65030 MSSQL server; Waiting on FBA06120 and FBA06122 refresh |  | OLSUAT2 zLinux Migration | OLS | Installed | UAT | Applications | TSA | OLSUAT2 zLinux Migration | OLSUAT2 zLinux Migration |  | UAT | No | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Eric Lopez | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group Obsolete | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) | 4 | 4096 | 157789 | 20464 | 10.30.140.173 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA06120 |  |  |  | On obsolete list; waiting for refresh 6/9/25 Part of BeB with thousands of file transfers. Derek is requesting bank PM to coordinate the move. Strategy is likely to build new shell in Azure and then migrate activity over time. |  | FBPRTEST zLinux Migration | FBPR zLinux Migration | Installed | UAT | Applications | TBD | FBPRTEST zLinux Migration | FBPRTEST zLinux Migration |  | UAT | No | Pending |  |  |  | No |  | Yes |  | Juan Espinoza |  | Edgardo Santiago | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group Obsolete | TBD | Virtual Server | poweredOn |  | 2 | 4096 | 34899 | 34899 | 10.30.140.183 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA06122 |  |  |  | Decommissioned per ticket CH25000181963 - jdeltoro 9/18 |  | OLSTST zLinux Migration - UIT | OLS | Installed | Development | Applications | TSA | OLSTST zLinux Migration - UIT | OLSTST zLinux Migration - UIT | Decommissioned | Development | No | Completed |  |  |  | No |  | Yes |  | Sharon Gutierrez |  | Eric Lopez | Linux |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 4096 | 24658 | 24658 | 10.30.140.185 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA06123 |  |  |  | Decommissioned per Edgardo - 1/27 jdeltoro |  | MQTST zLinux Migration - UIT | MQTST zLinux Migration | Disposed/Retired | OFF | Applications | N/A | MQTST zLinux Migration - UIT | MQTST zLinux Migration - UIT | Decommissioned | Development | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 4096 | 40018 | 40018 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA06127 |  |  |  | No concerns no follow needed - jdeltoro 5/9; New MQ UAT; See traffic from FEIS log server; Per Eric, 6127 and 2441 will both be needed as one is UIT and the other is UAT. Requires ASP connectivity. Vince Manso is an FIS resource who has helped with MQ and the ASP project. Per Edgardo this may be decommissioned. Edgardo will follow up with Eric. jdeltoro 5/13 | Eric | MQUAT zLinux Migration | MQ | Installed | UAT | Applications | FIS / Open System | MQUAT zLinux Migration | MQUAT zLinux Migration |  | UAT | No | TBD | ? |  |  | No |  | Yes |  | Irma Ramos |  | Ana Cruz | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Linux 8 | 1 | 1024 | 21585 | 21219 | 10.30.140.190 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
fba06134 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6; updated Application name per Angel - jdeltoro 10/21 |  | Archiva Maven (Java) Repository | Archiva Maven (Java) Repository | Installed | Development | Applications | N/A | redhat archive | redhat archive |  | Development | No | Pending |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  | Redhat archive | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 57428 | 54128 | 10.30.140.192 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
fba06135 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 | Eric | Business Rules Tomcat - UIT | Business Rules Tomcat | Disposed/Retired | OFF | Applications | FIS Open System | Linux Red Hat Enterprise Server 7.0 (3.10.0-123.9.2.el7.x86_64) - UIT | Linux Red Hat Enterprise Server 7.0 (3.10.0-123.9.2.el7.x86_64) - UIT | Decommissioned | UIT | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | Linux |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 1 | 4096 | 90032 | 40532 | 10.30.140.193 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA06141 |  |  |  | Edgardo and Wilson to follow up on if this is a no migrate - jdeltoro 5/13 |  | Microsoft RAP Active Directory | Microsoft RAP Active Directory | Installed | Production | Security | N/A | Microsoft RAP Active Directory | Microsoft RAP Active Directory |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06141 | FBA06141.firstbank.local |  | N/A | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 170385 | 170385 | 10.30.137.210 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA06143 |  |  |  | Per Eric this is good to move in Milestone 2 - jdeltoro 5/9 |  | Account Resolution Portal | Account Resolution | Installed | OFF | Applications | FIS Open System | Mobile Banking | Mobile Banking |  | Production | No | Review |  |  |  | No |  | Yes |  | FIS |  | Eric Lopez |  |  |  | Account Resolution | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn |  | 2 | 4096 | 24658 | 23584 | 10.30.134.187 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA06144 | [5 empty] | Xpress 3 | Xpress | Installed | Production | Database | TSA | Xpress 3 | Xpress 3 |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 18432 | 264343 | 138870 | 10.30.134.188 | 255.255.255.0 |  |  | 10.100.134.188 | [6 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | [8 empty] | No
FBA06144temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBA06144temp | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.2.el8uek.x86_64) |  |  |  |  | 10.30.134.137 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FBA06145 | [5 empty] | Xpress | Xpress | Installed | Production | Database | TSA | Xpress | Xpress |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | FIS | Milestone 3 |  | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 4096 | 249948 | 121282 | 10.30.134.189 | 255.255.255.0 |  |  | 10.100.134.189 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA06145temp |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.329.3.2.el8uek.x86_64) |  |  |  |  | 10.30.134.138 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA06148 | [5 empty] | TPSS | TPSS | Installed | Production | Applications | TSA | TPSS | TPSS |  | Production | No | Pending |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Nieves |  |  |  | TPSS | MR1130 | FIS | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 4 | 16384 | 57428 | 57428 | 10.30.134.192 | 255.255.255.0 |  |  | 10.100.134.192 | [6 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | Yes
FBA06157 |  |  |  | Confirmed with German no migrate - jdeltoro 5/8 |  | Nessus Scan Server | Nessus Scan | Installed | Production | Monitoring | CSO | Nessus Scan Server | Nessus Scan Server |  | Production | No | Pending |  |  |  | Yes |  | Yes |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.30.136.56 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [9 empty] | No
FBA06159 |  |  |  | This will move to West3 for DR per JT - jdeltoro 5/13; per Eric this can be moved to non-PCI segment in Azure - jdeltoro 5/15; Server not found in Faddom - jdeltoro 10/30 |  | AAB MQ_COB (related to FEIS) | FEIS | Installed | Contingency | Applications | N/A | AAB MQ_COB | AAB MQ_COB |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn |  | 4 | 8192 | 90196 | 90196 | [11 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06168 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Integration Server - Oracle Cloud Connection | MIT RDS Server - New Bastion Server | Disposed/Retired | OFF | Database | N/A | Integration Server - Oracle Cloud Connection | Integration Server - Oracle Cloud Connection | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06168 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
fba06172 |  |  |  | Dependency on FBA02046 Part of digital banking; Needs to be fully refactored at some point but no firm date; | Eric | IC FEIS - UIT | FEIS | Installed | Development | Applications | TSA | IC FEIS - UIT | IC FEIS - UIT | UIT | Development | No | Pending |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez | Linux |  |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | No Migration; New Build Replacement | Virtual Server | poweredOn | Red Hat Enterprise Linux 7 | 1 | 20480 | 103055 | 62293 | 10.30.140.214 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
fba06173 |  |  |  | Part of digital banking; this will go away but no defined date; data on physical SQL 65031 so need to factor in vendor reconfiguring application. There is a current project that will finish in August.; needs application map created, follow up on next call - jdeltoro 6/4; dependency on 10.30.134.64 VRU test on port 21 that needs follow; has port 443 dependency on fba06135 goes through load balancer - jdeltoro 6/12 | Edgardo, Eric | IC FEIS - UIT | FEIS | Installed | Development | Applications | TSA | IC FEIS - UIT | IC FEIS - UIT | UIT | Development | No | Pending |  |  |  | No |  | Yes |  | Juan Espinoza |  | Eric Lopez |  |  |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | No Migration; New Build Replacement | Virtual Server | poweredOn |  | 1 | 20480 | 92854 | 67906 | 10.30.140.213 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA06174 | [5 empty] | AAB PCI DB2 | AAB DB2 | Disposed/Retired | OFF | Applications | N/A | AAB PCI DB2 | AAB PCI DB2 | Decommissioned | STAGING | No | Completed | Yes |  |  | No | FBA06174 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA06175 |  |  |  | This will move to East2 for prod per JT - jdeltoro 5/13; per Eric this can be moved to non-PCI segment in Azure - jdeltoro 5/15; |  | AAB PCI MQ (related to FEIS) | FEIS | Installed | Production | Applications | N/A | AAB PCI MQ | AAB PCI MQ |  | Production | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | No Migration; New Build Replacement | Virtual Server | poweredOn |  | 4 | 8192 | 90198 | 90198 | 10.30.148.5 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06177 | [5 empty] | AAB PCI DB2 | AAB DB2 | Disposed/Retired | OFF | Applications | N/A | AAB PCI DB2 | AAB PCI DB2 | Decommissioned | OFF | No | Decommissioned | Yes |  |  | No | FBA06177 | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
fba06178 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Jira &Confluence PROD (Open Source) | Jira &Confluence (Open Source) | Disposed/Retired | OFF | Applications | N/A | Jira &Confluence PROD (Open Source) | Jira &Confluence PROD (Open Source) | Decommissioned | OFF | No | Decommissioned |  |  |  | Yes | FBA06178 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration |  | poweredOff | Linux Oracle Enterprise Server 7.9 (4.1.12-124.60.1.el7uek.x86_64) |  |  |  |  | 10.30.134.70, 192.168.122.1 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
fba06179 | [5 empty] | Jira &Confluence PROD (Open Source) | Jira &Confluence (Open Source) | Installed | UAT | Applications | N/A | Jira &Confluence PROD (Open Source) | Jira &Confluence PROD (Open Source) |  | UAT | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.321.4.1.el7uek.x86_64) | 4 | 6144 | 282709 | 282709 | 10.30.134.225 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA06189 | [5 empty] | IBM Spectrum Control V5.2.7.1 | IBM Spectrum Control V5.2.7.1 | Installed | Production | Monitoring | N/A | IBM Spectrum Control V5.2.7.1 | IBM Spectrum Control V5.2.7.1 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06189 | FBA06189.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 32768 | 770819 | 365697 | 10.30.129.16 | 255.255.255.0 | [19 empty] | Yes
FBA06192 | [5 empty] | UIP AQM Primary | UIP AQM | Installed | Production | Applications | N/A | UIP AQM Primary | UIP AQM Primary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06192 | FBA06192.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 312348 | 312348 | 10.30.71.10 | [20 empty] | Yes
FBA06193 | [5 empty] | UIP AQM Database | UIP AQM Database | Installed | Production | Applications | N/A | UIP AQM Database | UIP AQM Database |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06193 | FBA06193.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 6144 | 1594380 | 1594380 | 10.30.71.11 | [20 empty] | Yes
FBA06194 | [5 empty] | UIP AQM Web Services | UIP AQM Web Services | Installed | Production | Applications | N/A | UIP AQM Web Services | UIP AQM Web Services |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06194 | FBA06194.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 209933 | 209933 | 10.30.71.12 | [20 empty] | Yes
FBA06195 | [5 empty] | UIP AQM Pri(R)/Web/Media | UIP AQM Pri(R)/Web/Media | Installed | Production | Applications | N/A | UIP AQM Pri(R)/Web/Media | UIP AQM Pri(R)/Web/Media |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06195 | fba06195.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 26733948 | 26733948 | 10.30.71.13 | [20 empty] | Yes
FBA06196 | [5 empty] | UIP AQM WFO UI Server | UIP AQM WFO UI | Installed | Production | Applications | N/A | UIP AQM WFO UI Server | UIP AQM WFO UI Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06196 | FBA06196.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 209932 | 209932 | 10.30.71.14 | [20 empty] | Yes
FBA06197 | [5 empty] | UIP AQM Media Server | UIP AQM Media | Installed | Production | Applications | N/A | UIP AQM Media Server | UIP AQM Media Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06197 | FBA06197.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 209933 | 209933 | 10.30.71.15 | [20 empty] | Yes
fba06198 | [5 empty] | VDI HPE Simplivity Arbiter | VDI HPE Simplivity Arbiter | Installed | UAT | Applications | Multiple VDI Users | VDI HPE Simplivity Arbiter | VDI HPE Simplivity Arbiter |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | fba06198 | fba06198.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 168018 | 168018 | 10.30.142.221 | 255.255.255.0 | [19 empty] | No
FBA06199 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | SharePoint ¦ Active Directory ¦ DMZ | SharePoint ¦ Active Directory ¦ DMZ | Disposed/Retired | OFF | Applications | N/A | SharePoint ¦ Active Directory ¦ DMZ | SharePoint ¦ Active Directory ¦ DMZ | Decommissioned | OFF | No | Pending |  |  |  | No | FBA06199 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA06200 | [5 empty] | NEW NetIQ DRA Server - PRIMARY | NEW NetIQ DRA | Disposed/Retired | OFF | Applications | N/A | NEW NetIQ DRA Server - PRIMARY | NEW NetIQ DRA Server - PRIMARY | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06200 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06201 | [5 empty] | NEW NetIQ DRA Server - SECONDARY | NEW NetIQ DRA | Disposed/Retired | OFF | Applications | N/A | NEW NetIQ DRA Server - SECONDARY | NEW NetIQ DRA Server - SECONDARY | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06201 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06202 | [5 empty] | NEW NetIQ GPA Server | NEW NetIQ GPA | Installed | Production | Applications | N/A | NEW NetIQ GPA Server | NEW NetIQ GPA Server | Decommissioned | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06202 | FBA06202.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 157784 | 157784 | 10.30.137.247 | 255.255.255.0 | [19 empty] | No
FBA06203 |  |  | x | Confirmed with German no migrate - jdeltoro 5/8 |  | Nessus 7 | Nessus 7 | Installed | Production | Applications | CSO | Nessus Server | Nessus 7 |  | Production | No | Pending |  |  |  | Yes |  | No |  | Maria Ripepi |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.87.2.el7uek.x86_64) | 4 | 4096 | 301140 | 301140 | 10.30.136.51 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06204 | [5 empty] | UIP 7.4 Datamart - Primary | UIP 7.4 Datamart | Installed | Production | Applications | N/A | UIP 7.4 Datamart - Primary | UIP 7.4 Datamart - Primary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06204 | FBA06204.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 858966 | 858966 | 10.30.71.16 | [20 empty] | No
fba06205 | [5 empty] | UIP 7.4 Datamart - Secondary | UIP 7.4 Datamart | Installed | Production | Applications | N/A | UIP 7.4 Datamart - Secondary | UIP 7.4 Datamart - Secondary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06205 | fba06205.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 859045 | 859045 | 10.30.71.17 | [20 empty] | No
FBA06206 | [5 empty] | UIP 7.4 Core - Primary | UIP 7.4 Core | Installed | Production | Applications | N/A | UIP 7.4 Core - Primary | UIP 7.4 Core - Primary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06206 | fba06206.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 273390 | 273390 | 10.30.71.18 | [20 empty] | No
FBA06207 | [5 empty] | UIP 7.4 Core - Secondary | UIP 7.4 Core | Installed | Production | Applications | N/A | UIP 7.4 Core - Secondary | UIP 7.4 Core - Secondary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06207 | FBA06207.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 273352 | 273352 | 10.30.71.19 | [20 empty] | No
FBA06208 | [5 empty] | UIP 7.4 Agent M3 Arbiter | UIP 7.4 Agent M3 Arbiter | Installed | Production | Applications | N/A | UIP 7.4 Agent M3 Arbiter | UIP 7.4 Agent M3 Arbiter |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06208 | FBA06208.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 6144 | 186394 | 186394 | 10.30.71.20 | [20 empty] | Yes
FBA06209 | [5 empty] | UIP 7.4 Agent M3 Expansion | UIP 7.4 Agent M3 Expansion | Installed | Production | Applications | N/A | UIP 7.4 Agent M3 Expansion | UIP 7.4 Agent M3 Expansion |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06209 | FBA06209.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 6144 | 186306 | 186306 | 10.30.71.21 | [20 empty] | No
FBA06210 | [5 empty] | UIP 7.4 UCC Admin | UIP 7.4 UCC Admin | Installed | Production | Applications | N/A | UIP 7.4 UCC Admin | UIP 7.4 UCC Admin |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06210 | FBA06210.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 6144 | 186308 | 186308 | 10.30.71.22 | [20 empty] | No
FBA06211 | [5 empty] | UIP 7.4 UCC Admin Redundant | UIP 7.4 UCC Admin Redundant | Installed | Production | Applications | N/A | UIP 7.4 UCC Admin Redundant | UIP 7.4 UCC Admin Redundant |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06211 | FBA06211.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6897 (1607) | 2 | 6144 | 186312 | 186312 | 10.30.71.23 | [20 empty] | No
FBA06212 | [5 empty] | UIP AIC 7.4 Core | UIP AIC 7.4 Core | Installed | Production | Applications | N/A | UIP AIC 7.4 Core | UIP AIC 7.4 Core |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06212 | FBA06212.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 8 | 12288 | 269181 | 269181 | 10.30.71.24 | [20 empty] | Yes
FBA06213 | [5 empty] | UIP AIC 7.4 DataMart | UIP AIC 7.4 DataMart | Installed | Production | Applications | N/A | UIP AIC 7.4 DataMart | UIP AIC 7.4 DataMart |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06213 | FBA06213.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 4 | 6144 | 539686 | 539686 | 10.30.71.25 | [20 empty] | Yes
FBA06214 | [5 empty] | Bancware UIP 7.4 ALM BOE | Bancware | Installed | Production | Applications | Financial Planning | UIP 7.4 ALM BOE | UIP 7.4 ALM BOE |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA06214 | FBA06214.firstbank.local |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 222225 | 222225 | 10.30.71.26 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA06215 | [5 empty] | Bancware UIP 7.4 ALM Primary | Bancware | Installed | Production | Applications | Financial Planning | UIP 7.4 ALM Primary | UIP 7.4 ALM Primary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA06215 |  |  | Bancware |  | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 94208 | 657302 | 657302 | 192.168.1.1 | [10 empty] | Standard Esv6 Family vCPUs | Standard E16-4s_v6 | 4 | 128 | [6 empty] | No
FBA06216 | [5 empty] | Bancware UIP 7.4 ALM Secondary | Bancware | Installed | Production | Applications | Financial Planning | UIP 7.4 ALM Secondary | UIP 7.4 ALM Secondary |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA06216 |  |  | Bancware |  | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 94208 | 657331 | 657331 | 192.168.1.2 | [10 empty] | Standard Esv6 Family vCPUs | Standard E16-4s_v6 | 4 | 128 | [6 empty] | No
FBA06217 | [5 empty] | UIP 7.4 Support Server | UIP 7.4 Support | Installed | Production | Applications | N/A | UIP 7.4 Support Server | UIP 7.4 Support Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06217 | FBA06217.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 2 | 4096 | 235474 | 235474 | 10.30.71.29 | [20 empty] | No
FBA06218 | [5 empty] | UIP AIC 7.4 Support Server | UIP AIC 7.4 Support | Installed | Production | Applications | N/A | UIP AIC 7.4 Support Server | UIP AIC 7.4 Support Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06218 | FBA06218.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 2 | 4096 | 235367 | 235367 | 10.30.71.30 | [20 empty] | No
FBA06221 | [5 empty] | Network Node Manager (NNM) Reporting | Network Node Manager (NNM) Reporting | Installed | STAGING | Monitoring | N/A | Network Node Manager (NNM) Reporting | Network Node Manager (NNM) Reporting |  | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06221 | FBA06221.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 528491 | 83645 | 10.30.136.37 | 255.255.255.0 | [19 empty] | No
FBA06222 |  |  |  | This server is staying on-prem |  | FBPRTEST Oracle 8 server (NDM) - Connected with Digital Banking | FBPR Oracle 8(NDM) - Connected with Digital Banking | Installed | Development | Applications | N/A | FBPRTEST Oracle 8 server (NDM) | FBPRTEST Oracle 8 server (NDM) | Staging | STAGING | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.7 (4.18.0-425.19.2.el8_7.x86_64) | 1 | 4096 | 70754 | 40613 | 10.30.140.50 | [20 empty] | Yes
FBA06223 |  |  | x | Validate No Migrate |  | Aspec Support PC 1 | Aspec Support PC 1 | Installed | Contingency | Applications | N/A | Aspec Support PC 1 | Aspec Support PC 1 |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06223 | FBA06223.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 8 | 6144 | 424217 | 206834 | 10.20.16.15 | [20 empty] | No
FBA06224 |  |  | x | Validate No Migrate |  | UIP DR 7.4 Datamart - Primary | UIP DR 7.4 Datamart | Installed | Contingency | Applications | N/A | UIP DR 7.4 Datamart - Primary | UIP DR 7.4 Datamart - Primary |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06224 | FBA06224.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 2 | 8192 | 1646710 | 855370 | 10.20.16.16 | [20 empty] | No
FBA06225 |  |  | x | Validate No Migrate |  | UIP DR 7.4 Datamart - Secondary | UIP DR 7.4 Datamart | Installed | Contingency | Applications | N/A | UIP DR 7.4 Datamart - Secondary | UIP DR 7.4 Datamart - Secondary |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06225 | FBA06225.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 2 | 8192 | 1646712 | 855849 | 10.20.16.17 | [20 empty] | No
FBA06226 |  |  | x | Validate No Migrate |  | UIP DR 7.4 UCC Admin | UIP DR 7.4 UCC Admin | Installed | Contingency | Applications | N/A | UIP DR 7.4 UCC Admin | UIP DR 7.4 UCC Admin |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06226 | FBA06226.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 2 | 6144 | 364663 | 203595 | 10.20.16.18 | [20 empty] | No
FBA06227 |  |  | x | Validate No Migrate |  | UIP DR 7.4 UCC Admin Redundant | UIP DR 7.4 UCC Admin Redundant | Installed | Contingency | Applications | N/A | UIP DR 7.4 UCC Admin Redundant | UIP DR 7.4 UCC Admin Redundant |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06227 | FBA06227.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 2 | 6144 | 364662 | 207125 | 10.20.16.19 | [20 empty] | No
FBA06228 |  |  | x | Validate No Migrate |  | UIP DR 7.4 UCC Core - Primary | UIP DR 7.4 UCC Core | Installed | Contingency | Applications | N/A | UIP DR 7.4 UCC Core - Primary | UIP DR 7.4 UCC Core - Primary |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06228 | FBA06228.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 528504 | 300794 | 10.20.16.20 | [20 empty] | No
FBA06229 |  |  | x | Validate No Migrate |  | UIP DR 7.4 UCC Core - Secondary | UIP DR 7.4 UCC Core | Installed | Contingency | Applications | N/A | UIP DR 7.4 UCC Core - Secondary | UIP DR 7.4 UCC Core - Secondary |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06229 | FBA06229.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 528516 | 303963 | 10.20.16.21 | [20 empty] | No
FBA06230 |  |  | x | Validate No Migrate |  | UIP DR 7.4 Agent M3 Expansion | UIP DR 7.4 Agent M3 Expansion | Installed | Contingency | Applications | N/A | UIP DR 7.4 Agent M3 Expansion | UIP DR 7.4 Agent M3 Expansion |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06230 | FBA06230.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 6144 | 364676 | 199076 | 10.20.16.22 | [20 empty] | No
FBA06231 |  |  | x | Validate No Migrate |  | UIP DR 7.4 Agent M3 Expansion Arbiter | UIP DR 7.4 Agent M3 Expansion Arbiter | Installed | Contingency | Applications | N/A | UIP DR 7.4 Agent M3 Expansion Arbiter | UIP DR 7.4 Agent M3 Expansion Arbiter |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06231 | FBA06231.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 6144 | 364665 | 199762 | 10.20.16.23 | [20 empty] | No
FBA06232 |  |  | x | Validate No Migrate |  | Bancware UIP 7.4 ALM BOE COB | Bancware | Installed | Contingency | Applications | Financial Planning | UIP 7.4 ALM BOE COB | UIP 7.4 ALM BOE COB |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA06232 | FBA06232.firstbank.local |  | Bancware | Arterial | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 16384 | 630904 | 334829 | 10.20.16.24 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA06233 |  |  | x | Validate No Migrate |  | Bancware UIP 7.4 ALM Reporting/DR COB | Bancware | Installed | Contingency | Applications | Financial Planning | UIP 7.4 ALM Reporting/DR COB | UIP 7.4 ALM Reporting/DR COB |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA06233 | FBA06233.firstbank.local |  | Bancware | Arterial | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 94208 | 1220726 | 711056 | 10.20.16.25 | [10 empty] | Standard Esv6 Family vCPUs | Standard E16-4s_v6 | 4 | 128 | [6 empty] | No
fba06234 |  |  | x | Validate No Migrate |  | UIP DR 7.4 AQM Primary | UIP DR 7.4 AQM | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM Primary | UIP DR 7.4 AQM Primary |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06234 | fba06234.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 618616 | 319529 | 10.20.16.26 | [20 empty] | No
fba06235 | [5 empty] | UIP DR 7.4 AQM Database | UIP DR 7.4 AQM Database | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM Database | UIP DR 7.4 AQM Database |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06235 | fba06235.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6897 (1607) | 4 | 4096 | 1847418 | 951716 | 10.20.16.27 | [20 empty] | No
fba06236 |  |  | x | Validate No Migrate |  | UIP DR 7.4 AQM Recording Server | UIP DR 7.4 AQM Recording | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM Recording Server | UIP DR 7.4 AQM Recording Server |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06236 | fba06236.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6897 (1607) | 4 | 4096 | 413816 | 221758 | 10.20.16.28 | [20 empty] | No
fba06237 |  |  | x | Validate No Migrate |  | UIP DR 7.4 AQM WFO UI Server | UIP DR 7.4 AQM WFO UI | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM WFO UI Server | UIP DR 7.4 AQM WFO UI Server |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06237 | fba06237.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 4 | 4096 | 413816 | 222420 | 10.20.16.29 | [20 empty] | No
fba06238 |  |  | x | Validate No Migrate |  | UIP DR 7.4 AQM Pri(R) - Web - Media | UIP DR 7.4 AQM Pri(R) - Web - Media | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM Pri(R) - Web - Media | UIP DR 7.4 AQM Pri(R) - Web - Media |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06238 | fba06238.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 11728607 | 5877218 | 10.20.16.30 | [20 empty] | No
fba06239 |  |  | x | Validate No Migrate |  | UIP DR 7.4 AQM Quality Web Services | UIP DR 7.4 AQM Quality Web Services | Installed | Contingency | Applications | N/A | UIP DR 7.4 AQM Quality Web Services | UIP DR 7.4 AQM Quality Web Services |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fba06239 | fba06239.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 4 | 4096 | 413816 | 222267 | 10.20.16.31 | [20 empty] | No
FBA06240 | [5 empty] | UIP 7.4 WFM Application | UIP 7.4 WFM Application | Installed | Production | Applications | N/A | UIP 7.4 WFM Application | UIP 7.4 WFM Application |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06240 | FBA06240.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6897 (1607) | 8 | 16384 | 283539 | 283539 | 10.30.71.32 | [20 empty] | No
FBA06241 | [5 empty] | UIP 7.4 WFM JumpServer | UIP 7.4 WFM Jump | Installed | Production | Applications | N/A | UIP 7.4 WFM JumpServer | UIP 7.4 WFM JumpServer |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06241 | FBA06241.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6897 (1607) | 2 | 4096 | 291820 | 291820 | 10.30.71.33 | [20 empty] | No
fba06242 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | COB VDI HPE Simplivity Arbiter | COB VDI HPE Simplivity Arbiter | Disposed/Retired | OFF | Applications | N/A | COB VDI HPE Simplivity Arbiter | COB VDI HPE Simplivity Arbiter | Decommissioned | OFF | No | Decommissioned |  |  |  | No | fba06242 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06244 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | FBNB AQM WFO (BsprAQMwfo1) | FBNB AQM WFO (BsprAQMwfo1) | Disposed/Retired | OFF | Applications | N/A | FBNB AQM WFO (BsprAQMwfo1) | FBNB AQM WFO (BsprAQMwfo1) | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06244 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06245 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | FBNB AQM Primary (BsprAQM1n) | FBNB AQM (BsprAQM1n) | Disposed/Retired | OFF | Applications | N/A | FBNB AQM Primary (BsprAQM1n) | FBNB AQM Primary (BsprAQM1n) | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06245 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06246 | [5 empty] | FBNB AQM Pri/Web/Media (BsprAQMMedia1n) | FBNB AQM Pri/Web/Media (BsprAQMMedia1n) | Installed | Production | Applications | N/A | FBNB AQM Pri/Web/Media (BsprAQMMedia1n) | FBNB AQM Pri/Web/Media (BsprAQMMedia1n) |  | Production | Yes | Review |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06246 | FBA06246.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 4096 | 8101754 | 8101754 | 10.30.71.182 | [20 empty] | No
FBA06247 | [5 empty] | FBNB AQM DB (BsprAQMdb4) | FBNB AQM DB (BsprAQMdb4) | Installed | Production | Applications | N/A | FBNB AQM DB (BsprAQMdb4) |  |  | Production | Yes | Review |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA06247 | FBA06247.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 4096 | 516987 | 516987 | 10.30.71.183 | [20 empty] | No
FBA06248 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | FBNB AQM Web Services (BsprAQMServices) | FBNB AQM Web Services (BsprAQMServices) | Disposed/Retired | OFF | Applications | N/A | FBNB AQM Web Services (BsprAQMServices) | FBNB AQM Web Services (BsprAQMServices) | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06248 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06258 |  |  |  | Follow up with John and Adam - jdeltoro 5/8; No migration per Adam - jdeltoro 5/16 |  | Pronet Rapid7 Nexpose Scan | Pronet Rapid7 Nexpose Scan | Installed | Production | Applications | N/A | Pronet Rapid7 Nexpose Scan | Pronet Rapid7 Nexpose Scan |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06258 | FBA06258.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 90198 | 90198 | 10.30.136.58 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA06259 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Microsoft Azure Migration POC, temporasy server | Microsoft Azure Migration, temporasy | Disposed/Retired | OFF | Applications | N/A | Microsoft Azure Migration POC, temporasy server | Microsoft Azure Migration POC, temporasy server | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA06259 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA06260 | [5 empty] | Mobisa / SMS PROD - Connected with Digital Banking | Mobisa / SMS | Installed | Production | Applications | N/A | Mobisa / SMS PROD | Mobisa / SMS PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06260 | FBA06260.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 265062 | 265062 | 10.30.71.178 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06261 |  |  | x | This server needs to possibly go to West3 in Azure; possible test and dr - jdeltoro 5/8 |  | Mobisa / SMS UAT - Connected with Digital Banking | Mobisa / SMS | Installed | UAT | Applications | N/A | Mobisa / SMS UAT | Mobisa / SMS UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA06261 | FBA06261.firstbank.local |  |  | Arterial | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 296192 | 47975 | 10.20.16.178 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06262 | [5 empty] | Mobisa / SMS DMZ - Connected with Digital Banking | Mobisa / SMS | Installed | Production | Applications | N/A | Mobisa / SMS DMZ | Mobisa / SMS DMZ |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 8192 | 264279 | 264279 | 10.30.192.173 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06263 |  |  |  | Server will remain on-site per Angel - jdeltoro 7/3 | N/A | Teramind Master Server - Appliance | Teramind Master- Appliance | Installed | STAGING | Security | Eliezer Mendez | Teramind Master Server - Appliance | Teramind Master Server - Appliance |  | STAGING | No | Pending |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | [5 empty] | 10.30.137.46 | 255.255.255.0 | [19 empty] | No
FBA06264 | [5 empty] | NetIQ DRA Administration WEB | NetIQ | Installed | Production | Applications | CSO | NetIQ DRA Administration WEB |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Maria Ripepi |  | Omar Cuadrado | FBA06264 | FBA06264.firstbank.local |  | DRA | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2031 (21H2) | 4 | 8192 | 161882 | 111974 | 10.30.137.253 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA06265 | [5 empty] | NetIQ DRA Administration WEB | NetIQ | Installed | Production | Applications | CSO | NetIQ DRA Administration WEB |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | Maria Ripepi |  | Omar Cuadrado | FBA06265 | FBA06265.firstbank.local |  | DRA | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2022 10.0.20348.2527 (21H2) | 4 | 8192 | 161877 | 53233 | 10.30.137.254 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA06266 |  |  |  | 10/22/25 This server has a NIC in the PCI segment. Need to discuss in more details about possibly changing the migration method to New Build. Either way, we need to better understand the requirements for this application. Added to Milestone 1; Group 1 per Angel on 4/14 - jdeltoro; Updated to no migration/new build per Angel Lopez - jdeltoro 10/24 | N/A | SafeBreach Host Simulator PCI | SafeBreach | Installed | STAGING | Applications | CSO | SafeBreach Host Simulator PCI |  | Staging | STAGING | Yes | TBD | Yes |  |  | Yes |  | No |  | Maria Ripepi |  | Teddy Quiñones | FBA06266 |  |  |  | MR1130 | Cloud | Milestone 1 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 208998 | 208998 | 10.30.148.156 | 255.255.255.0 | 10.30.148.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA06267 |  |  |  | Updated to no migrate/new build per Angel Lopez - jdeltoro 10/24 |  | SafeBreach Host Simulator PROD | SafeBreach | Installed | STAGING | Applications | CSO | SafeBreach Host Simulator PROD |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | Maria Ripepi |  | Teddy Quiñones | FBA06267 | FBA06267.firstbank.local |  | SafeBreach | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 4096 | 208990 | 208990 | 10.30.137.155 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06268 |  |  | x | Updated to no migrate/new build per Angel Lopez - jdeltoro 10/24 |  | SafeBRidge Host Simulator DMZ | SafeBreach | Installed | STAGING | Applications | CSO | SafeBreach Host Simulator DMZ | SafeBRidge Host Simulator DMZ |  | STAGING | No | TBD |  |  |  | Yes |  | No |  | Maria Ripepi |  | Teddy Quiñones |  |  |  | SafeBreach | MR1130 | Cloud | Milestone 2 | Group 5 | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.8 (4.18.0-477.15.1.el8_8.x86_64) | 4 | 8192 | 161933 | 161933 | 10.30.134.137 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA06269 |  |  | x | Updated to no migrate/new build per Angel Lopez - jdeltoro 10/24 |  | SafeBRidge Collector Virtual Appliance | SafeBreach | Installed | Development | Applications | CSO | SafeBreach Collector Virtual Appliance | SafeBRidge Collector Virtual Appliance |  | STAGING | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Teddy Quiñones |  |  |  | SafeBridge | MR1130 | Cloud | Milestone 2 | Group 5 | No Migration; New Build Replacement | Virtual Server | poweredOn |  | 4 | 32768 | 135264 | 135264 | 10.30.140.186 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | No
FBA06270 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24; Updated to no migrate/new build per Angel Lopez - jdeltoro 10/24 |  | SafeBreach Collector VA Oracle | SafeBreach | Installed | Production | Applications | CSO |  |  | Prod |  |  | TBD | [7 empty] | Maria Ripepi |  | Teddy Quiñones |  |  |  |  | MR1130 | TBD | TBD | TBD | No Migration; New Build Replacement | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.134.232 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | [8 empty] | No
FBA06271 | [5 empty] | FIS MIT Support Terminal Server | FIS MIT Support Terminal | Installed | Production | Utilities | N/A | FIS MIT Support Terminal Server |  |  | Production | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBA06271 | FBA06271.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | [7 empty] | 10.30.136.96 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | [8 empty] | Yes
FBA06272 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | New MQ Prod Server | MQ | Installed | STAGING |  | TBD |  |  | Staging |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.134.144 | [20 empty] | No
FBA06273 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | FIS MIT Support Terminal Server | FIS MIT Support Terminal | Installed | STAGING | Utilities | N/A |  |  | STAGING |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.97 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA07004 |  |  |  | Decommissioned per Juan Luis - jdeltoro 5/9 |  | MR 1130 FTP | MR 1130 FTP | Installed | Production | Applications | N/A | MR 1130 FTP | MR 1130 FTP | Decommissioned | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA07004 | FBA07004.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2008 6.0.6003 | 4 | 4096 | 116825 | 116825 | 10.30.137.164 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA07006 | [5 empty] | Serv U MFT - SFTP | Serv-U | Installed | Production | Applications | TSA | Serv U MFT - SFTP | Serv U MFT - SFTP |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago (FIS) | FBA07006 | fba07006.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 157778 | 157778 | 10.30.137.96 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA07007 | [5 empty] | Serv U Gateway | Serv-U | Installed | Production | Applications | TSA | Serv U Gateway | Serv U Gateway |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Edgardo Santiago (FIS) |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2012 6.2.9200 | 2 | 4096 | 106578 | 106578 | 10.30.192.167 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA07008 | [5 empty] | PCI PROD SFTP Server OneSumX | OneSumX | Installed | Production | Applications | Compliance | PCI PROD SFTP Server OneSumX | PCI PROD SFTP Server OneSumX |  | Production | Yes | Pending | Yes |  |  | Yes |  | Yes |  | Luana Santos |  | Dennis Hernandez | FBA07008 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012 6.2.9200 | 4 | 8192 | 110760 | 110760 | 10.30.148.18 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA07009 | [5 empty] | PCI-COB SFTP Server OneSumX | OneSumX | No Match | No Match | No Match | Compliance | Not Found | PCI-COB SFTP Server OneSumX |  |  | No | Pending | Yes |  |  | Yes |  | Yes |  | Luana Santos |  | Dennis Hernandez |  |  |  |  | Santurce 1519 | Cloud | Milestone 3 |  | No Migration; New Build Replacement |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.19.148.19 | [10 empty] | No CPU/RAM Info Found
FBA07010 |  |  | x | Edgardo Santiago to follow up on whether this can be included in milestone 2 - jdeltoro 5/13; also related to GFT/Swift |  | SFTP Swift Serv-U | SFTP Swift Serv-U | Installed | Production | File Server | International Services | Swift (Serv-U) SFTP/File Server | SFTP Swift Serv U |  | Production | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Edgardo Santiago (FIS) |  |  |  |  | MR1130 | Onsite | Milestone 3 |  | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 229458 | 229458 | 10.30.155.12 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | [8 empty] | Yes
FBA08005 |  |  |  | Confirmed with German and Fernando no migrate; was used to track internal audits - jdeltoro 5/9 |  | IssueTrack Web Server (Audit tool) | IssueTrack Web(Audit tool) | Installed | Production | Applications | N/A | IssueTrack Web Server | IssueTrack Web Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08005 | FBA08005.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 147544 | 147544 | 10.30.137.53 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA08012 |  |  |  | Obsolete list; New server built; Migration in early 2025 |  | Web Consolidation Test Envrionment (UAT) | Web Consolidation Envrionment | Installed | UAT | Web | N/A | Web Consolidation Test Envrionment | Web Consolidation Test Envrionment |  | UAT | Yes | Ready for Decom |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08012 | FBA08012.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2008R2 6.1.7601 | 4 | 5120 | 210038 | 182627 | 10.30.140.201 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08022 | [5 empty] | LDR(Legal Document) | LDR(Legal Document) | Installed | Production | Applications | N/A | LDR(Legal Document) | LDR(Legal Document) |  | Production | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 2048 | 53330 | 53330 | 10.30.152.73 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA08027 | [5 empty] | Server para LDR | para LDR | Available | OFF | Applications | N/A | Server para LDR | Server para LDR |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | [8 empty] | No
FBA08029 | Yes |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | LDR Web Server UAT | LDR Web | Disposed/Retired | OFF | Applications | N/A | LDR Web Server UAT | LDR Web Server UAT | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA08029 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 2048 | 43090 | 18636 | [11 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6
FBA08030 | [5 empty] | E3 Web Server PROD (Win2008R2 6.1.7601) | E3 Web (Win2008R2 6.1.7601) | Installed | Production | Web | N/A | E3 Web Server PROD (Win2008R2 6.1.7601) |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA08030 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.30.137.136 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | [8 empty] | No
FBA08032 | Yes |  |  |  |  | E3 Web Server UAT | E3 Web | Disposed/Retired | OFF | Web | N/A | E3 Web Server UAT |  |  | OFF | Yes | TBD |  |  |  | No | FBA08032 | No |  | N/A |  | N/A |  | FBA08121.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | [7 empty] | 10.30.140.153 | [10 empty] | No CPU/RAM Info Found
FBA08036 | [5 empty] | GFT Application - PROD (upgrade) | GFT | Installed | Production | Applications | N/A | GFT Application - PROD (upgrade) | GFT Application - PROD (upgrade) |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 315486 | 315486 | 10.30.157.203 | [20 empty] | Yes
FBA08039 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | SharePoint UAT | SharePoint | Disposed/Retired | OFF | Applications | N/A | SharePoint UAT | SharePoint UAT | Decommissioned | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA08039 | FBA08039.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2012 6.2.9200 | 4 | 8192 | 161939 | 126226 | 10.30.140.129
FBA08040 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | SharePoint UAT | SharePoint | Disposed/Retired | OFF | Applications | N/A | SharePoint UAT | SharePoint UAT | Decommissioned | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA08040 | FBA08040.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2012 6.2.9200 | 8 | 8192 | 161911 | 123393 | 10.30.140.130
FBA08042 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | TIME OFF / UCM - Human Resources | TIME OFF / UCM - Human Resources | Disposed/Retired | OFF | Applications | N/A | TIME OFF / UCM - Human Resources | TIME OFF / UCM - Human Resources | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA08042 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA08043 |  |  |  | New server that is replacing FBA08117 - presented in CMC on 8/6 ticket CH25000179444 - jdeltoro 8/6; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | eTrans ISO2022 - EPM | eTrans | Installed | STAGING | Applications | Omar Ramos | eTrans ISO20222 | Tsoft Plus |  | Production | No | Pending |  |  |  | Yes | FBA08043 | Yes |  | Sharon Gutierrez |  | Herbert Cruz / Ana Cruz |  |  |  | eTrans | MR1130 | Cloud | Milestone 2 | Group 3 | TBD |  |  | Win2012 6.2.9200 |  |  |  |  | 10.30.137.16 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found | [9 empty] | No
FBA08045 |  |  | x | Validate No Migrate |  | GFT Application - COB (Upgrade) | GFT | Installed | Contingency | Applications | N/A | GFT Application - COB (Upgrade) | GFT Application - COB (Upgrade) |  | Contingency | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08045 |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 315595 | 315595 | 10.19.157.204 | [20 empty] | No
fba08053 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 |  | WEB APPL (SVN) | SVN | Installed | Development | Web | N/A | WEB APPL (SVN) | WEB APPL (SVN) |  | Development | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  | SVN | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.95.1.0.1.el7.x86_64) | 4 | 8192 | 142967 | 48296 | 10.30.140.238 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08058 |  |  |  | No Migration per Angel - jdeltoro 10/21 |  | CDM - PROD (Upgrade FST to CDM) Cognos | Cognos | Installed | Production | Applications | N/A | CDM - PROD (Upgrade FST to CDM) | CDM - PROD (Upgrade FST to CDM) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Preguntar a Julio Rivas |  | Preguntar a Julio Rivas | FBA08058 | FBA08058.firstbank.local |  | Cognos | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 6 | 16384 | 528514 | 528514 | 10.30.137.51 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | No
FBA08059 |  |  |  | No Migration per Angel - jdeltoro 10/21 | N/A | CDM - UAT (Upgrade FST to CDM) Cognos | CDM (Upgrade FST to CDM) Cognos | Installed | UAT | Applications | Cristina Torres/Kaylene Alamo | CDM - UAT (Upgrade FST to CDM) | CDM - UAT (Upgrade FST to CDM) | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Daphne Andino |  | Cristina Torres | FBA08059 | FBA08059.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7159 (1607) | 2 | 12288 | 650298 | 155782 | 10.30.140.60 | 255.255.255.0 |  | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08060 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 | Edgardo | WEB APPL UAT | WEB APPL | Disposed/Retired | OFF | Web | TBD | WEB APPL UAT | WEB APPL UAT | Decommissioned | UAT | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | Linux |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.92.1.0.1.el7.x86_64) | 4 | 8192 | 105561 | 43192 | 10.30.140.240 | 255.255.255.0 |  | N/A | 10.101.140.240 | 255.255.255.0 | 10.101.4.4, 10.101.4.5 | 10.101.140.1 | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 |  | TBD | TBD | TBD |  | Commvault Cloud |  | N/A
FBA08061 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Share Point UAT 1 | Share Point | Disposed/Retired | OFF | Web | N/A | Share Point UAT 1 | Share Point UAT 1 | Decommissioned | OFF | No | Pending |  |  |  | No | FBA08061 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA08062 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Share Point UAT 2 | Share Point | Disposed/Retired | OFF | Web | N/A | Share Point UAT 2 | Share Point UAT 2 | Decommissioned | OFF | No | Pending |  |  |  | No | FBA08062 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA08063 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | SharePoint DEV 1 | SharePoint | Disposed/Retired | OFF | Applications | N/A | SharePoint DEV 1 | SharePoint DEV 1 | Decommissioned | OFF | No | Completed |  |  |  | No | FBA08063 | Yes |  | Juan Espinoza |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FBA08064 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | SharePoint DEV 2 | SharePoint | Disposed/Retired | OFF | Applications | N/A | SharePoint DEV 2 | SharePoint DEV 2 | Decommissioned | OFF | No | Completed |  |  |  | No | FBA08064 | Yes |  | Juan Espinoza |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FBA08065 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Share Point UIT\DEV 3 | Share Point | Disposed/Retired | OFF | Web | N/A | Share Point UIT\DEV 3 | Share Point UIT\DEV 3 | Decommissioned | OFF | No | Pending |  |  |  | No | FBA08065 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA08066 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Share Point UIT\DEV 4 | Share Point | Disposed/Retired | OFF | Web | N/A | Share Point UIT\DEV 4 | Share Point UIT\DEV 4 | Decommissioned | OFF | No | Pending |  |  |  | No | FBA08066 | Yes |  | Juan Espinoza |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBA08067 |  |  |  | No Migration per Angel - jdeltoro 10/21 |  | CDM - COB Cognos | Cognos | Installed | Contingency | Applications | N/A | CDM - COB | CDM - COB |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | Preguntar a Julio Rivas |  | Preguntar a Julio Rivas |  |  |  | Cognos |  | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found | [9 empty] | No
FBA08068 | [5 empty] | Intranet SharePoint - Web | SharePoint | Installed | Production | Web | N/A | Intranet SharePoint - Web | Intranet SharePoint - Web |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA08068 | FBA08068.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 12288 | 514153 | 514153 | 10.30.137.74 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA08069 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Intranet SharePoint Web UAT | SharePoint | Disposed/Retired | OFF | Web | N/A | Intranet SharePoint Web UAT | Intranet SharePoint Web UAT | Decommissioned | UAT | Yes | Completed |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | N/A | FBA08069 | FBA08069.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2012R2 6.3.9600 | 4 | 10240 | 286833 | 286833 | 10.30.140.241
fba08070 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | Prog Confluence Server | Prog Confluence | Disposed/Retired | OFF | Applications | N/A | Prog Confluence Server | Prog Confluence Server | Decommissioned | Development | No | Decommissioned |  |  |  | Yes | FBA08070 | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.77.2.el7uek.x86_64) | 4 | 6144 | 170069 | 57849 | 10.30.140.249 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8
FBA08071 | [5 empty] | Digital Banking - Front End - UIT | Digital Banking | Installed | Development | Applications | N/A | Digital Banking - Front End - UIT | Digital Banking - Front End - UIT |  | Development | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08071 | FBA08071.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 2 | 8192 | 213114 | 93511 | 10.30.140.54 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA08072 | [5 empty] | Digital Banking - Back Office - UIT | Digital Banking | Installed | Development | Applications | N/A | Digital Banking - Back Office - UIT | Digital Banking - Back Office - UIT |  | Development | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08072 | cmt.firstbankpr.com |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 2 | 8192 | 213110 | 57019 | 10.30.140.55 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA08073 | [5 empty] | Intranet Migration Server | Intranet Migration | Installed | Production | Applications | N/A | Intranet Migration Server | Intranet Migration Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08073 |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 2 | 8192 | 192599 | 192599 | 10.30.154.241 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA08074 | [5 empty] | Digital Banking - Web Front End - UAT | Digital Banking | Installed | UAT | Applications | N/A | Digital Banking - Web Front End - UAT | Digital Banking - Web Front End - UAT |  | UAT | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08074 | FBA08074.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 12288 | 217257 | 98766 | 10.30.140.20 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | No
FBA08075 | [5 empty] | Digital Banking - Web - Back Office - UAT | Digital Banking | Installed | UAT | Applications | N/A | Digital Banking - Web - Back Office - UAT | Digital Banking - Web - Back Office - UAT |  | UAT | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08075 | FBA08075.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 2 | 8192 | 213139 | 54672 | 10.30.140.21 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | No
FBA08076 | [5 empty] | OneSumX WebAppl (SIT) | OneSumX | Installed | UAT | Web | Compliance | OneSumX WebAppl (SIT) | OneSumX WebAppl (SIT) |  | UAT | Yes | In Progress |  |  |  | Yes |  | Yes |  | Luana Santos |  | Dennis Hernandez | FBA08076 | FBA08076.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 4 | 8192 | 213114 | 213114 | 10.30.140.119 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08078 | [5 empty] | OneSumX WebAppl (PROD) | OneSumX | Installed | Production | Web | Compliance | OneSumX WebAppl (PROD) | OneSumX WebAppl (PROD) |  | Production | Yes | In Progress | Yes |  |  | Yes |  | Yes |  | Luana Santos |  | Dennis Hernandez | FBA08078 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 16 | 32768 | 442844 | 442844 | 10.30.148.108 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | Yes
FBA08078W19 | [5 empty] | OneSumX WebAppl (PROD) - Windows 2019 | OneSumX | Installed | STAGING | Web | Compliance | OneSumX WebAppl (PROD) - Windows 2019 |  |  | STAGING | Yes | TBD | Yes |  |  | Yes |  | No |  | Luana Santos |  | Dennis Hernandez | FBA08078W19 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 16 | 32768 | 442878 | 442878 | 10.30.148.118 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | No
FBA08079 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | Digital One OnBase Prototype | Digital One OnBase Prototype | Disposed/Retired | OFF | Applications | N/A | Digital One OnBase Prototype | Digital One OnBase Prototype | Decommissioned | UIT | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08079 | FBA08079.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 12 | 16384 | 405718 | 358109 | 10.30.140.111 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32
FBA08080 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | OnBase Upgrave v 17 | OnBase Upgrave v 17 | Disposed/Retired | OFF | Web | N/A | OnBase Upgrave v 17 | OnBase Upgrave v 17 | Decommissioned | Development | Yes | Decommissioned |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08080 | FBA08080.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 221342 | 165244 | 10.30.140.121 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA08081 | [5 empty] | Digital Banking - Web Back Office PROD | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web Back Office - Pilot | Digital Banking - Web Back Office PROD |  | Production | Yes | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08081 | FBA08081.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 12288 | 217241 | 59343 | 10.30.137.188 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA08082 | [5 empty] | Digital Banking - Web FE 1 - PROD | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 1 - Pilot | Digital Banking - Web FE 1 - PROD |  | Production | No | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 12288 | 312393 | 126652 | 10.30.192.142 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA08083 | [5 empty] | Digital Banking - Web FE 2 - PROD | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 2 - Pilot | Digital Banking - Web FE 2 - PROD |  | Production | No | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 12288 | 217232 | 93173 | 10.30.192.143 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA08084 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Web | N/A | OneSumX WebAppl - Contingency |  | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA08084 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 16 | 32768 | 442588 | 442588 | 10.19.148.108
FBA08085 |  |  |  | Decommissioned per Angel - 3/7/2025 jdeltoro |  | OnBase Upgrave v 17 | OnBase Upgrave v 17 | Disposed/Retired | OFF | Web | N/A | OnBase Upgrave v 17 | OnBase Upgrave v 17 | Decommissioned | Development | Yes | Decommissioned |  |  |  | Yes | FBA08085 | Yes |  | N/A |  | N/A | FBA08085 | FBA08085.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 272502 | 210635 | 10.30.140.39 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA08086 | [5 empty] | Digital Banking - Web FE 3 - PROD | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 3 - PROD - Pilot | Digital Banking - Web FE 3 - PROD |  | Production | No | In Progress |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 12288 | 217285 | 108778 | 10.30.192.146 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA08090 |  |  |  | Follow up with Ana Cruz; FIS Core |  | GFT Application - Test (upgrade) | GFT | Installed | UAT | Applications | N/A | GFT Application - Test Legacy | GFT Application - Test (upgrade) |  | UAT | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08090 |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 315486 | 315486 | 10.30.158.196 | [20 empty] | No
FBA08090-2016 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | GFT Application - Test Legacy | GFT | Disposed/Retired | OFF | Applications | N/A |  |  | Decommissioned |  |  | Decommissioned | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | N/A | N/A | No Migration | Virtual Server | poweredOff | Microsoft Windows Server 2016 |  |  |  |  | 10.30.158.196
FBA08090-2022 |  |  | x | Depends on Fed connectivity at MR1130 |  | GFT Application TEST | GFT | No Match | No Match | No Match | N/A | GFT Application - Test ISO2022 | GFT Application TEST |  | UAT | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 16384 | 661597 | 661597 | 10.30.140.5 | 255.255.255.0
FBA08092 | [5 empty] | Profitability & BDI Risk Reporting - Bancware | Bancware | Installed | Production | Web | Financial Planning | Profitability & BDI Risk Reporting | Profitability & BDI Risk Reporting |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA08092 | FBA08092.firstbank.local |  | Bancware | MR1130 | Cloud | Milestone 2 | Group 4 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.5356 (1607) | 8 | 24576 | 868572 | 479528 | 10.30.137.83 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA08093 | [5 empty] | Profitability & BDI Risk Reporting UAT - Bancware | Bancware | Installed | UAT | Web | Financial Planning | Profitability & BDI Risk Reporting UAT | Profitability & BDI Risk Reporting UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Maria Medina |  | Maria Medina | FBA08093 | FBA08093.firstbank.local |  | Bancware |  | Cloud | Milestone 2 | Group 3 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 12 | 16384 | 426125 | 96141 | 10.30.140.67 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D16ls_v6 | 16 | 32 | [6 empty] | No
FBA08095 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | D1 onbase UAT | Onbase | Disposed/Retired | OFF | Applications | TSA | D1 onbase UAT | D1 onbase UAT | Decommissioned | UAT | Yes | Decommissioned |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBA08095 | FBA08095.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 6 | 8192 | 213107 | 126475 | 10.30.140.36 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
FBA08096 | [5 empty] | AML / Investigations Upgrade - PROD | AML / Investigations Upgrade | Installed | Production | Web | TSA | AML / Investigations Upgrade - PROD | AML / Investigations Upgrade - PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Luana Santos |  | John Huertas | FBA08096 | FBA08096.firstbank.local |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 161903 | 161903 | 10.30.137.168 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | [6 empty] | Yes
FBA08097 | [5 empty] | AML / Investigations Upgrade - Test | AML / Investigations Upgrade | Installed | UAT | Web | TSA | AML / Investigations Upgrade - Test | AML / Investigations Upgrade - Test |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Luana Santos |  | John Huertas | FBA08097 | FBA08097.firstbank.local |  |  |  | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 161897 | 161897 | 10.30.140.171 | [20 empty] | No
FBA08098 |  |  |  | Follow up with Omar - Dependency on FB65030 - MSSQL Server - Need to follow up on web application; Follow-up with Edgardo - jdeltoro 5/7; few applications talk to FEIS; need to follow up on what 10.30.140.57; follow up with Hiram on Load Balancers; Edgardo to follow up on list of IIS applicaitons, but having issues with RDS server, will follow up later - jdeltoro 6/4; FBA02143 - FEIS Application Server UAT; Also is connecting through a UATSALES LB to connect back to itself; 192.168.154.138 is OCI; - jdeltoro 6/19 |  | IIS Web Consolidation Server UAT | IIS Web Consolidation | Installed | UAT | Web | TSA & others (Definir cuales son los aplicativos) | IIS Web Consolidation Server UAT | IIS Web Consolidation Server UAT | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Juan Espinoza |  | Eric Lopez | FBA08098 | FBA08098.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 213103 | 95352 | 10.30.140.103 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08099 |  |  |  | Added to Milestone 1; Group 1 per Angel on 4/14 - jdeltoro | N/A | UCM Human Resources / Time Off Historic / Time Bank ADP- Etime | UCM Human Resources | Installed | STAGING | Applications | Eliezer Mendez | UCM Human Resources / Time Off Historic / Time Bank ADP- Etime | UCM Human Resources / Time Off Historic / Time Bank ADP- Etime | Staging | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | Magalys Camacho |  | Eliezer Ramos | FBA08099 | FBA08099.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 1 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 106591 | 106591 | 10.30.137.163 | 255.255.255.0 | 10.30.137.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08101 |  |  |  | Database dependency on FB65031, FBA03109 for APPRO; Does talk to load balancer; follow up with Hiram - jdeltoro 5/16 | Hiram | ITDG WEB UIT (E-Firstclass/econtracting/NMS/Eloan/Imaps/ADM/OSS/Tsys/CAS | ITDG | Installed | UIT | Web | TSA | ITDG WEB UIT (EFC/econtracting/NMS/Eloan/Imaps/ADM/OSS/Tsys/CAS | ITDG WEB UIT (EFC/econtracting/NMS/Eloan/Imaps/ADM/OSS/Tsys/CAS |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA08101 | FBA08101.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 161888 | 150020 | 10.30.140.31 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08102 |  |  | x | To Be Decommissioned; No Migrate |  | Risk Reporting Contingency Web Server | Risk Reporting Contingency Web | Installed | Contingency | Web | N/A | Risk Reporting Contingency Web Server | Risk Reporting Contingency Web Server |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  | FBA08102.firstbank.local |  |  |  | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 469553 | 67274 | 10.0.151.111 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08103 | [5 empty] | VDI Unified Access Gateway Horizon | VDI Unified Access Gateway Horizon | Installed | Production | Utilities | Multiple VDI Users | VDI Unified Access Gateway Horizon - Appliance | VDI Unified Access Gateway Horizon |  | STAGING | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 4096 | 24658 | 24658 | 10.30.192.52 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBA08104 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | AML / Investigations Upgrade - DR | AML / Investigations Upgrade - DR | Disposed/Retired | OFF | Web | TSA | AML / Investigations Upgrade - DR | AML / Investigations Upgrade - DR | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA08104 | Yes |  | Luana Santos |  | John Huertas | [5 empty] | Onsite | N/A | N/A | No Migration | [18 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6
FBA08105 |  |  |  | Dependency on FB65030 follow up with Omar, Follow up with Carlos Castillo on Edgardo's team - jdeltoro 5/16 | Carlos | eTrans Web Test | eTrans | Installed | UAT | Applications | Omar Ramos | eTrans Web Test | eTrans Web Test |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Herbert Cruz / Ana Cruz | FBA08105 | FBA08105.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 8192 | 213078 | 54264 | 10.30.140.18 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08106 |  |  |  | Follow up with Vendor: InfoCorp; Reviewed with bank and need to follow up on database dependencies on FBA65030 and FBA65031 - jdeltoro 5/15; was unable to determine which databases were needed for this server, will need to follow up on next call - jdeltoro 6/4; Omar to follow up with TSA team to get additional information on which databases are being used - jdeltoro 6/19 | Omar, TSA Team | Business eStatement Viewer Back Office UIT | Business eStatement | Installed | UIT | Web | TSA | Business eStatement Viewer Back Office UIT | Business eStatement Viewer Back Office UIT |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA08106 | FBA08106.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221435 | 221435 | 10.30.140.113 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08107 |  |  |  | Vendor: InfoCorp; Reviewed with bank and no concerns - jdeltoro 5/15 | N/A | Business eStatement Viewer Web Front End UIT | Business eStatement | Installed | Development | Web | TSA | Business eStatement Viewer Web Front End UIT | Business eStatement Viewer Web Front End UIT |  | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA08107 | FBA08107.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213146 | 213146 | 10.30.140.114 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08108 | [5 empty] | Business eStatement Viewer Back Office PROD | ITDG | Installed | Production | Web | TSA | Business eStatement Viewer Back Office PROD | Business eStatement Viewer Back Office PROD |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Alfredo Mercado |  | ITDG/Felix Lafountaine | FBA08108 | FBA08108.firstbank.local |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 16384 | 221420 | 221420 | 10.30.137.223 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA08109 | [5 empty] | Business eStatement Viewer Web Front End 1 PROD | ITDG | Installed | Production | Web | TSA | Business eStatement Viewer Web Front End 1 PROD | Business eStatement Viewer Web Front End 1 PROD |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Alfredo Mercado |  | ITDG/Felix Lafountaine |  |  |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 8 | 32768 | 237981 | 237981 | 10.30.192.151 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA08110 | [5 empty] | Business eStatement Viewer Web Front End 2 PROD | ITDG | Installed | Production | Web | TSA | Business eStatement Viewer Web Front End 2 PROD | Business eStatement Viewer Web Front End 2 PROD |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Alfredo Mercado |  | ITDG/Felix Lafountaine |  |  |  | ITDG Apps | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 8 | 32768 | 237934 | 237934 | 10.30.192.152 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | Yes
FBA08111 | [5 empty] | Imaps E3, Imaps Encompass and ADM | Imaps | Installed | Production | Applications | N/A | Imaps E3, Imaps Encompass and ADM | Imaps E3, Imaps Encompass and ADM |  | Production | Yes | TBD |  |  |  | Yes |  | Yes | Yes | N/A |  | N/A | FBA08111 | FBA08111.firstbank.local |  |  | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 213099 | 213099 | 10.30.137.151 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA08112 |  |  |  | Checked with Edgardo and these are still online; was mentioned as possible decommission but will move in Milestone 1 Group 2 | Edgardo | Development Web 2016 Server 1 | Delopment Web 2016 | Installed | Development | Web | FIS / Open System | Development Web 2016 Server 1 | Development Web 2016 Server 1 | Dev | Development | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | FBA08112 | FBA08112.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 161878 | 48951 | 10.30.140.82 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08113 |  |  |  | Checked with Edgardo and these are still online; was mentioned as possible decommission but will move in Milestone 1 Group 2 | Edgardo | Development Web 2016 Server 2 | Delopment Web 2016 | Installed | Development | Web | FIS / Open System | Development Web 2016 Server 2 | Development Web 2016 Server 2 | Dev | STAGING | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | FBA08113 | FBA08113.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 161880 | 53509 | 10.30.140.83 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08114 | [5 empty] | SAEX Upgrade Project - ITG | SAEX | Installed | Production | Applications | TSA | SAEX Upgrade Project | SAEX Upgrade Project |  | Production | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Karla de Jesus |  | Christian Corazon | FBA08114 | FBA08114.firstbank.local |  | SAEX | MR1130 | Cloud | Milestone 2 | Group 2 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 16384 | 272557 | 272557 | 10.30.137.91 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | [6 empty] | Yes
FBA08115 |  |  |  | Vendor: InfoCorp; Reviewed with bank and no concerns - jdeltoro 5/15 | N/A | Business eStatement BO UAT | Business eStatement | Installed | UAT | Applications | TSA | Business eStatement BO UAT | Business eStatement BO UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA08115 | FBA08115.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213136 | 213136 | 10.30.140.110 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08116 |  |  |  | Vendor: InfoCorp; Reviewed with bank and no concerns - jdeltoro 5/15 | N/A | Business eStatement FE UAT | Business eStatement | Installed | UAT | Applications | TSA | Business eStatement FE UAT | Business eStatement FE UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Irma Ramos |  | Arnold Rivera | FBA08116 | FBA08116.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213140 | 213140 | 10.30.140.107 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08117 | [5 empty] | eTrans Web Prod New | eTrans | Installed | Production | Applications | Omar Ramos | eTrans Web Prod New | eTrans Web Prod New |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Herbert Cruz / Ana Cruz | FBA08117 | FBA08117.firstbank.local |  | eTrans | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 229468 | 229468 | 10.30.137.117 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA08118 | [5 empty] | ReconFrontier Web Combined Server | ReconFrontier | Installed | Production | Web | Karina Valentin | ReconFrontier Web Combined Server | ReconFrontier Web Combined Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Norberto Gonzalez |  | Karina Valentin | FBA08118 | FBA08118.firstbank.local |  | ReconFrontier | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 16384 | 400571 | 400571 | 10.30.137.203 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA08119 |  |  |  | Follow up with Norberto Gonzalez, Karina Valentin and Vendor - Fiserv; dependency on FB65031 follow up with Omar - jdeltoro 5/16 | Omar | Fiserv ReconFrontier WEB Combined UAT | Fiserv ReconFrontier | Installed | UAT | Web | Karina Valentin | ReconFrontier WEB Combined UAT | ReconFrontier WEB Combined UAT |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Norberto Gonzalez |  | Myriam Cintron | FBA08119 | FBA08119.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 5 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 4096 | 388189 | 42102 | 10.30.140.152 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | Yes | N/A
FBA08120 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens Identity and Access Management (XIAM) - Web Server | Xapiens | Installed | UAT |  | TBD |  |  | UAT |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.164.11 | [20 empty] | Yes
FBA08121 |  |  |  | Follow up with Omar - Database Dependency on FB65030 - MSSQL Server - ITG and ITDG vendor dependencies; Would need to move CAS along with this app/database; 3.7GB SAEX, CAS 44GB db's; MSSQL 2017 | Omar | SAEX Upgrade Web UAT - ITG | SAEX | Installed | UAT | Web | TSA | SAEX Upgrade Web UAT | SAEX Upgrade Web UAT | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Santitos Rivas |  | Israel Velez | FBA08121 | FBA08121.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 16384 | 221284 | 64074 | 10.30.140.153 | 255.255.255.0 |  | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08122 | [5 empty] | Digital Banking - Web FE 1 - PROD Upgrade | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 1 - PROD Upgrade | Digital Banking - Web FE 1 - PROD Upgrade |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 32768 | 238155 | 130816 | 10.30.192.125 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | Yes
FBA08123 | [5 empty] | Digital Banking - Web FE 2 - PROD Upgrade | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 2 - PROD Upgrade | Digital Banking - Web FE 2 - PROD Upgrade |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 32768 | 237832 | 148142 | 10.30.192.126 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | Yes
FBA08124 | [5 empty] | Digital Banking - Web FE 3 - PROD Upgrade | Digital Banking | Installed | Production | Web | N/A | Digital Banking - Web FE 3 - PROD Upgrade | Digital Banking - Web FE 3 - PROD Upgrade |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 32768 | 237792 | 137047 | 10.30.192.127 | [10 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | Yes
FBA08125 | [5 empty] | Digital Banking - BackOffice - PROD Upgrade | Digital Banking | Installed | Production | Applications | N/A | Digital Banking - BackOffice - PROD Upgrade | Digital Banking - BackOffice - PROD Upgrade |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08125 | FBA08125.firstbank.local |  |  | MR1130 | Cloud | Milestone 4 |  | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 32768 | 237832 | 88250 | 10.30.137.189 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | Yes
FBA08126 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xapiens Identity and Access Management (XIAM) - Web Server PROD | Xapiens | Installed | Production |  | TBD |  |  | Prod |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Ubuntu 20.04 |  |  |  |  | 10.30.166.4 | [20 empty] | Yes
FBA08127 |  |  |  | Follow up on working session Tuesday 5/13 with Omar and Eric to log into this server and review applications - jdeltoro 5/9 | Omar, Eric | IIS Consolidated UAT (PROD FB57768 - FB57769 upgrade) | IIS Consolidated | Installed | UAT | Applications | TSA & others (Definir cuales son los aplicativos) | IIS Consolidated UAT (FB57768 - FB57769 - FBA06006 upgrade) | IIS Consolidated UAT (FB57768 - FB57769 - FBA06006 upgrade) | UAT | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Eric Lopez | FBA08127 | fba06021.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 2 | Replicate and Re-IP | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 6144 | 211041 | 48911 | 10.30.140.184 | 255.255.255.0 | 10.30.140.1 | TBD | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08128 |  |  |  | No concerns - jdeltoro 5/16 | N/A | OSS Web Server UAT 1 NEW | OSS | Installed | UAT | Applications | TSA | OSS Web Server UAT 1 NEW | OSS Web Server UAT 1 NEW |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Eric Lopez | FBA08128 | FBA08128.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213098 | 43301 | 10.30.140.108 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08129 |  |  |  | No concerns - jdeltoro 5/16 | N/A | OSS Web Server UAT 2 NEW | OSS | Installed | UAT | Applications | TSA | OSS Web Server UAT 2 NEW | OSS Web Server UAT 2 NEW |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | Sharon Gutierrez |  | Eric Lopez | FBA08129 | FBA02225.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 4 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213132 | 41439 | 10.30.140.149 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08130 |  |  |  | No concerns - jdeltoro 5/16 | N/A | OSS Web Server UIT 1 NEW | OSS | Installed | UIT | Applications | TSA | OSS Web Server UIT 1 NEW | OSS Web Server UIT 1 NEW |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Sharon Gutierrez |  | Eric Lopez | FBA08130 | FBA08130.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 12288 | 217227 | 50709 | 10.30.140.48 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08131 |  |  |  | No concerns - jdeltoro 5/16 | N/A | OSS Web Server UIT 1 NEW | OSS | Installed | UIT | Applications | TSA | OSS Web Server UIT 1 NEW | OSS Web Server UIT 1 NEW |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes | Yes | Sharon Gutierrez |  | Eric Lopez | FBA08131 | FBA08131.firstbank.local |  |  | MR1130 | Cloud | Milestone 1 | Group 3 | Replicate and Re-IP | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 12288 | 217241 | 48328 | 10.30.140.49 | 255.255.255.0 |  |  | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud | No | N/A
FBA08132 |  |  | x | ON |  | OSS Web SERVER DMZ 1 | OSS | Installed | Production | Applications | TSA | OSS Web Server DMZ 1 | OSS Web SERVER DMZ 1 |  | Production | No | TBD |  |  |  | Yes |  | No | Yes | Lored Matos |  | Lored Matos |  |  |  | OSS | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 8192 | 213123 | 45457 | 10.30.192.36 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA08133 |  |  | x | ON |  | OSS Web SERVER DMZ 1 | OSS | Installed | Production | Applications | TSA | OSS Web Server DMZ 2 | OSS Web SERVER DMZ 1 |  | Production | No | TBD |  |  |  | Yes |  | No | Yes | Lored Matos |  | Lored Matos |  |  |  | OSS | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5933 (1809) | 4 | 8192 | 213110 | 44375 | 10.30.192.37 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA08134 | [5 empty] | BMS System - Niagara | BMS System - Niagara | Installed | Production | Monitoring | N/A | BMS System - Niagara | BMS System - Niagara |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08134 | FBA08134.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213101 | 213101 | 10.30.137.76 | 255.255.255.0 | [19 empty] | No
FBA08135 |  |  |  | Follow up with Fernando if decommissioned - jdeltoro 5/9 |  | ASSISTck Web Production | Assistck | Installed | Production | Applications | BSA | ASSISTck Web Production | ASSISTck Web Production |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Luana Santos |  | Jose Fonseca/Dennis Hernandez | FBA08135 | FBA08135.firstbank.local |  | Assistck | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 32768 | 237832 | 98872 | 10.30.137.226 | 255.255.255.0 | [9 empty] | Standard Esv6 Family vCPUs | Standard E4s_v6 | 4 | 32 | [6 empty] | Yes
FBA08136 |  |  |  | This server to stay on prem till decommission in 2026 per JT - jdeltoro 5/7 |  | ASSISTck Web DEV | ASSISTck Web | Installed | UAT | Applications | N/A | ASSISTck Web DEV | ASSISTck Web DEV |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA08136 | FBA08136.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 32768 | 237812 | 71717 | 10.30.140.43 | 255.255.255.0 | [19 empty] | No
FBA08137 |  |  |  | Decommissioned per Angel - jdeltoro 5/13 |  | Tsoft Plus 2019 | Tsoft Plus 2019 | Disposed/Retired | OFF | Applications | N/A | Tsoft Plus 2019 | Tsoft Plus 2019 | Decommissioned | OFF | No | Decommissioned |  |  |  | Yes | FBA08137 | Yes |  | N/A |  | N/A |  | FBA02465.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.30.137.17 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBA08138 |  |  |  | Follow up with Compliance Team - Server is being replaced by a new server; Need to coordinate with bank PM (Damaris) on replacement server(s) and plan to move them in a future group. |  | OneSumX WebAppl Test | OneSumX WebAppl | Installed | Development | Web | N/A | OneSumX WebAppl Test |  |  | STAGING | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA08138 | FBA08138.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.6054 (1809) | 4 | 8192 | 213111 | 213111 | 10.30.140.59 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08139 | [5 empty] | IssueTrack Upgrade Auto Audit | IssueTrack Upgrade Auto Audit | Installed | Production | Web | N/A | Issue Tracker Upgrade Auto Audit |  |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBA08139 | FBA08139.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 4 | 8192 | 213122 | 38368 | 10.30.137.227 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA08140 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 6 | 16384 | 170069 | 170069
FBA08143 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | OnBase API Server | Onbase | Installed | UAT | Applications | N/A |  |  | UAT |  |  | TBD | [7 empty] | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.140.174 | [20 empty] | No
FBA08145 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Digital Banking - Web Front End - UAT - DMZ | Digital Banking | Installed | STAGING |  | TBD |  |  | Staging |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2019 |  |  |  |  | 10.30.192.10 | [20 empty] | No
FBA084145 |  |  |  | New VM per ticket CH25000178673 in CMC - jdeltoro 7/30 |  | DigitalBanking Web UAT DMZ Server | DigitalBanking | No Match | No Match | No Match | N/A |  |  | UAT |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | [5 empty] | 10.30.192.10
FBA10004 |  |  |  | Confirmed with Edgardo Santiago no migrate - jdeltoro 5/13 |  | Insight Manager Server | MIT RDS Server/DNS Server | Installed | Production | Applications | N/A | Insight Manager Server | Insight Manager Server |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA10004 | FBA10004.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 12288 | 114806 | 114806 | 10.30.136.4 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4s_v6 | 4 | 16 | [6 empty] | Yes
FBA10005 |  |  |  | Followed up with Eric Lopez and has no info; Follow up with Omar - jdeltoro 5/9; updated Application name per Angel - jdeltoro 10/21 |  | CDO/Business Knowledge DEV SQL Integration Services | CDO/Business Knowledge DEV SQL Integration Services | Installed | Production | Applications | Business Reporting | TSM Reports (Nestor Deliz Area) | TSM Reports (Nestor Deliz Area) |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | Lored Matos |  | Omar Ramos | FBA10005 | FBA10005.firstbank.local |  | TSM Reports | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 469083 | 469083 | 10.30.140.202 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA10008 | [5 empty] | Tivoli Storage Productivity Center | Tivoli Storageuctivity Center | Available | OFF | Applications | N/A | Tivoli Storage Productivity Center | Tivoli Storage Productivity Center |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [28 empty] | No
FBA10009 |  |  |  | Per Omar no issues - jdeltoro 5/13 |  | Ideras DB Performance Monitor | Idera | Installed | Production | Database | N/A | DB Performance Monitor | DB Performance Monitor |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA10009 | fba10009.firstbank.local |  | DB Performance Monitor | MR1130 | Cloud | Milestone 2 | Group 1 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 796763 | 796763 | 10.30.136.16 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | No
FBA10013 | [5 empty] | IBM TEM Server – Relay 1 | BigFix | Installed | Production | Monitoring | N/A | IBM TEM Server – Relay 1 | IBM TEM Server – Relay 1 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot | FBA10013 | FBA10013.firstbank.local |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 208978 | 208978 | 10.30.136.19 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA10014 | [5 empty] | IBM TEM Server – Relay 2 | BigFix | Installed | Production | Utilities | N/A | IBM TEM Server – Relay 2 | IBM TEM Server – Relay 2 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot | FBA10014 | FBA10014.firstbank.local |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 208980 | 208980 | 10.30.136.20 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA10015 | [5 empty] | IBM TEM Server – Relay 3 | BigFix | Installed | Production | Utilities | N/A | IBM TEM Server – Relay 3 | IBM TEM Server – Relay 3 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot | FBA10015 | FBA10015.firstbank.local |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 157778 | 157778 | 10.30.136.21 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA10016 | [5 empty] | IBM TEM Server – Relay 4 | BigFix | Installed | Production | Monitoring | N/A | IBM TEM Server – Relay 4 | IBM TEM Server – Relay 4 |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot | FBA10016 | FBA10016.firstbank.local |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 208978 | 208978 | 10.30.136.22 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA10017 | [5 empty] | IBM TEM Server – Relay 5 | BigFix | Installed | Production | Monitoring | N/A | IBM TEM Server – Relay 5 | IBM TEM Server – Relay 5 |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | FIS |  | Mayra Gascot |  |  |  | BigFix | MR1130 | Cloud | Milestone 2 | Group 1 | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 2 | 4096 | 239698 | 239698 | 10.30.192.23 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA10018 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | HP Data Protector | HP Data Protector | Disposed/Retired | OFF | Applications | N/A | HP Data Protector | HP Data Protector | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA10018 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA10019 | [5 empty] | TEM Relay Server svr5 (DMZ 2) | TEM Relaysvr5 (DMZ 2) | Installed | Production | Applications | N/A | TEM Relay Server svr5 (DMZ 2) | TEM Relay Server svr5 (DMZ 2) |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 208987 | 131392 | 10.30.192.24 | [20 empty] | No
FBA10020 |  |  |  | Confirmed with Edgardo Santiago no migrate - jdeltoro 5/13 |  | HP Insight Remote Support Tool | HP Insight Remote Support Tool | Installed | UAT | Utilities | N/A | HP Insight Remote Support Tool | HP Insight Remote Support Tool |  | UAT | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA10020 | FBA10020.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 110708 | 99835 | 10.30.140.212 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | [6 empty] | Yes
FBA10021 | [5 empty] | Vcenter PCI | Vcenter | Installed | Production | Utilities | N/A | Vcenter PCI | Vcenter PCI |  | Production | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 19456 | 2119360 | 2119360 | 10.30.149.12 | [20 empty] | Yes
FBA10022 |  |  | x | Validate No Migrate |  | Vcenter PCI-COB | Vcenter-COB | Installed | Contingency | Utilities | N/A | Vcenter PCI-COB | Vcenter PCI-COB |  | Contingency | No | TBD | Yes |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 19456 | 4237882 | 2171431 | 10.19.149.12 | [20 empty] | No
fba10023 | [5 empty] | Vcenter MR1130 | Vcenter MR1130 | Installed | Production | Utilities | N/A | Vcenter MR1130 | Vcenter MR1130 |  | Production | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 28672 | 2296325 | 2296325 | 10.30.142.121 | 255.255.255.0 | [19 empty] | Yes
fba10025 |  |  | x | Validate No Migrate |  | Vcenter COB - Appliance | Vcenter COB - Appliance | Installed | Contingency | Monitoring | N/A | Vcenter COB - Appliance | Vcenter COB - Appliance |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 19456 | 4238008 | 2159705 | 10.19.142.121 | [20 empty] | Yes
fba10026 | [5 empty] | OVA Vmware - POC | OVA Vmware | Available | OFF | Applications | N/A | OVA Vmware - POC | OVA Vmware - POC |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration | [28 empty] | No
fba10030 |  |  | x | To Be Decommissioned; No Migrate |  | Vcenter Sungard | Vcenter Sungard | Installed | STAGING | Utilities | N/A | Vcenter Sungard | Vcenter Sungard |  | STAGING | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 19456 | 531472 | 531472 | 10.0.151.80 | [20 empty] | No
FBA10034 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Utilities | N/A | VmWare 6.5 Vsphere Replication COB PCI |  | Decommissioned | OFF | No | Decommissioned |  |  |  | No | fba10034 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 30965 | 30965 | 10.19.149.10
fba10036 | [5 empty] | VDI Vcenter Appliance | VDI Vcenter Appliance | Installed | Production | Applications | Multiple VDI Users | VDI Vcenter Appliance | VDI Vcenter Appliance |  | Production | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 28672 | 965768 | 965768 | 10.30.142.220 | 255.255.255.0 | [19 empty] | Yes
fba10039 | [5 empty] | VDI NSX Appliance | VDI NSX Appliance | Installed | Production | Applications | Multiple VDI Users | VDI NSX Appliance | VDI NSX Appliance |  | Production | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 61509 | 18816 | 10.30.180.50 | [20 empty] | No
fba10040 | [5 empty] | VDI VmWare vRealize Operations Manager | VDI VmWare vRealize Operations Manager | Installed | Production | Applications | Multiple VDI Users | VDI VmWare vRealize Operations Manager - Appliance | VDI VmWare vRealize Operations Manager |  | STAGING | No | TBD |  |  |  | No |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | [5 empty] | Onsite | N/A | N/A | No Migration | [28 empty] | No
fba10041 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | VmWare vRealize Operations Manager POC | VmWare vRealize Operations Manager | Disposed/Retired | OFF | Applications | N/A | VmWare vRealize Operations Manager POC | VmWare vRealize Operations Manager POC | Decommissioned | OFF | No | Decommissioned |  |  |  | No | fba10041 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBA10043 |  |  | x | Validate No Migrate |  | Vcenter 7.0 Arterial | Vcenter 7.0 Arterial | Installed | Contingency | Utilities | N/A | Vcenter 7.0 Arterial | Vcenter 7.0 Arterial |  | Contingency | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 19456 | 1473137 | 825105 | 10.20.114.26 | [20 empty] | Yes
FBA10044 | [5 empty] | Xerox Remote Services | Xerox Remote Services | Installed | Production | Utilities | N/A | Xerox Remote Services | Xerox Remote Services |  | Production | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBA10044 | FBA10044.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 3 | 8192 | 417879 | 45555 | 10.30.137.153 | 255.255.255.0 | [19 empty] | No
FBA12003 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 |  | Mortgage MSP Server - Windows 7 | MSP | OFF | OFF | Applications | N/A | Mortgage MSP Server - Windows 7 | Mortgage MSP Server - Windows 7 |  | Production | No | TBD |  |  |  | Yes |  | Yes |  | Luzmarie Velez |  | Waldemar Velez/Elizabeth Cardona |  |  |  | Mortgage MSP | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.3448 (22H2) | 2 | 4096 | 274515 | 173529 | 10.30.137.66 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | Yes
FBA12004 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 |  | APPRO Reporting PC | APPRO | No Match | No Match | No Match | TSA | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | Lucy Ann Vasquez |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win7 6.1.7601 | 8 | 8192 | 161894 | 161894 | 10.30.137.36 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
FBA12011 | [5 empty] | HurrTrak PC | HurrTrak PC | Available | OFF | Applications | N/A | HurrTrak PC | HurrTrak PC |  | OFF | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff |  | 2 | 4096 | 107082 | 68662 | 10.30.137.92 | [20 empty] | No
FBA12012 | [5 empty] | Test PC - TSA Dept | PC - TSA Dept | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 16384 | 272497 | 72193 | 10.30.140.245 | 255.255.255.0
FBA12013 | [5 empty] | Test PC - TSA Dept | PC - TSA Dept | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 90228 | 79213 | 10.30.140.246 | 255.255.255.0
FBA12019 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 | N/A | Workstation Infra - Jump Workstations for tools | Workstation Infra - Jump Workstations for tools | No Match | No Match | No Match | FIS Server Admin | Not Found |  | Prod |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | Windows 10 | FBA12019.firstbank.local |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 8 | 8192 | 520292 | 312396 | 10.30.137.21 | 255.255.255.0 |  | N/A | 10.101.137.21 | 255.255.255.0 | 10.101.4.4, 10.101.4.5 | 10.101.137.1 | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 |  | TBD | TBD | TBD |  | Commvault Cloud |  | N/A
FBA12021 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 |  | APPRO PCI VPN | APPRO | No Match | No Match | No Match | TSA | Not Found |  |  |  | No | TBD | Yes |  |  | Yes |  | No |  | N/A |  | Lucy Ann Vasquez |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 6144 | 108637 | 108637 | 10.30.137.60 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
FBA12022 |  |  | x | To Be Decommissioned; No Migrate |  |  |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4651 (22H2) | 4 | 4096 | 117089 | 117089 | 10.0.151.91
FBA12024 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6 | N/A | Workstation Infra - Jump Workstations for tools | Workstation Infra - Jump Workstations for tools | No Match | No Match | No Match | FIS Server Admin | Not Found |  | Prod |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | Windows 10 |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 264294 | 264294 | 10.30.137.52 | 255.255.255.0 |  | N/A | 10.101.137.52 | 255.255.255.0 | 10.101.4.4, 10.101.4.5 | 10.101.137.1 | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 |  | TBD | TBD | TBD |  | Commvault Cloud |  | N/A
FBA12025 | Yes |  |  |  |  | Workstation - Jump Workstations - ATM Monitoring | Workstation - Jump Workstations - ATM Monitoring | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 10240 | 112744 | 112744 | 10.30.137.139 | 255.255.255.0
FBA12026 |  |  |  | Follow up with Juan - Possible Decommission |  | Workstation - Jump Workstations - Mobius - Vendor Jump Box | Workstation - Jump Workstations - Mobius - Vendor Jump Box | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 4096 | 106583 | 106583 | 10.30.137.159 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA12027 |  |  |  | Follow up with Juan - Possible Decommission |  | Workstation - Jump Workstations - Mobius - Vendor Jump Box | Workstation - Jump Workstations - Mobius - Vendor Jump Box | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 4096 | 106578 | 106578 | 10.30.137.90 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA12028 |  |  |  | No Migrate |  | ATM WIN10 Test Upgrade | ATM WIN10 Upgrade | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  | FBA12028.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 4096 | 106578 | 106578 | 10.30.137.160 | [20 empty] | Yes
FBA12029 |  |  | x | To Be Decommissioned; No Migrate |  |  |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 111144 | 59862 | 10.0.151.93
FBA12032 |  |  |  | No Migrate |  | Alvaria Call Center - UIP 7.4 | UIP | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 4096 | 301929 | 301929 | 10.30.71.31
FBA12033 |  |  | x | Validate No Migrate - Arterial |  | DR | DR | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 6 | 8192 | 469126 | 249518 | 10.20.16.32
FBA12034 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found | 0 | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 14 | 8192 | 161896 | 161896 | fe80::553e:96ed:c7cc:61fd
FBA12037 |  |  |  | No Migrate |  | First Bank Credit Union | First Bank Credit Union | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 315486 | 315486 | 10.30.137.27
FBA12040 | [5 empty] | Win10 32Bit Payroll | Win10 32Bit Payroll | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 4096 | 106578 | 106578 | 10.30.137.233 | 255.255.255.0
FBA12041 |  |  |  | Follow up with Rafi - Does this system need to be migrated; Do we need to contact MasterCard |  | Workstation - Jump Workstations | Workstation - Jump Workstations | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD | Yes |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 4096 | 208981 | 208981 | 10.30.148.86 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4
FBA12042 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found | 0 | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 8 | 8192 | 323684 | 201303 | 10.30.137.40
FBA12043 | [5 empty] | MonEx Workstation | MonEx Workstation | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 5120 | 291924 | 291924 | 10.30.137.24 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
FBA12044 | [5 empty] | MonEx Workstation | MonEx Workstation | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 2 | 5120 | 291922 | 291922 | 10.30.137.28 | 255.255.255.0 | [9 empty] | Standard Dsv6 Family vCPUs | Standard D2s_v6 | 2 | 8
FBA12045 |  |  | x | Validate No Migrate - Arterial |  | DR | DR | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win11 10.0.22631.3737 (23H2) | 4 | 8192 | 315525 | 174080 | 10.20.16.33
FBA12046 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6; added back to migration per Angel - jdeltoro 10/21 | N/A | RPA - Bot Automation - Dev | RPA | No Match | No Match | No Match | Alberto Jimenez | Not Found |  | Dev |  | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Jesus Sanchez | Windows 10 |  |  |  | MR1130 | Cloud | Milestone 1 | Group 1 | Replicate and Re-IP | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 110680 | 110680 | 10.30.75.13 | 255.255.255.0 | 10.30.75.1 | N/A | TBD | TBD | 10.101.4.4, 10.101.4.5 | TBD | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 | TBD | TBD | TBD | TBD | TBD | Commvault Cloud |  | N/A
FBA12047 |  |  |  | Updated to "No Migration" per Angel Lopez - jdeltoro 10/6; added back to migration per Angel - jdeltoro 10/21 | N/A | RPA - Bot Automation - Prod | RPA | No Match | No Match | No Match | Alberto Jimenez | Not Found |  | Prod |  | No | TBD |  |  |  | Yes |  | No |  | Juan Espinoza |  | Jesus Sanchez | Windows 10 |  |  |  | MR1130 | Cloud | Milestone 2 | Group 1 | Replicate and Re-IP | Virtual Server | poweredOn | Win10 10.0.19045.4529 (22H2) | 4 | 8192 | 110681 | 110681 | 10.30.75.14 | 255.255.255.0 |  | N/A | 10.101.75.14 | 255.255.255.0 | 10.101.4.4, 10.101.4.5 | 10.101.75.1 | N/A | N/A | N/A | Standard Dlsv6 Family vCPUs | Standard D4ls_v6 | 4 | 8 |  | TBD | TBD | TBD |  | Commvault Cloud |  | N/A
FBA13001 | Yes |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Orace Integration Test Server | Orace Integration | Disposed/Retired | OFF | Database | N/A | Orace Integration Test Server | Orace Integration Test Server | Decommissioned | STAGING | No | Completed |  |  |  | No |  | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FBA13003 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud FDMEE Production DB Server | Oracle Cloud FDMEEuction DB | Disposed/Retired | OFF | Database | N/A | Oracle Cloud FDMEE Production DB Server | Oracle Cloud FDMEE Production DB Server | Decommissioned | OFF | No | Decommissioned |  |  |  | No | FBA13003 | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FBA14001 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | OpenShift_Bastion_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | Yes | FBA14001 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.9 (4.18.0-513.18.1.el8_9.x86_64) | 4 | 8192 | 323711 | 203422 | 10.30.150.71
fba14003 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master01_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14003 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174277 | 171103 | 10.130.0.2
fba14004 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master02_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14004 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174305 | 174133 | 10.128.0.2
fba14005 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master03_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14005 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174295 | 174123 | 10.129.0.2
fba14006 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra01_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14006 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 416269 | 311318 | 10.131.0.2
fba14007 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra02_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14007 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 606981 | 486041 | 10.128.2.2
fba14008 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra03_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14008 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 276583 | 128123 | 10.129.2.2
fba14009 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker01_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14009 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 174262 | 89253 | 10.130.2.2
fba14010 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker02_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14010 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 170180 | 88309 | 10.131.2.2
fba14011 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker03_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14011 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 170180 | 85758 | 10.128.4.2
fba14012 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker04_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14012 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 174311 | 93190 | 10.129.4.2
fba14013 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker05_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14013 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 170235 | 110399 | 10.130.4.2
fba14014 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker06_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14014 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 172263 | 121501 | 10.131.4.2
fba14015 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker07_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14015 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 170166 | 123997 | 10.128.6.2
fba14016 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker08_Non_PROD |  | Decommissioned | UAT | No | Decommissioned |  |  |  | No | FBA14016 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 170181 | 118172 | 10.129.6.2
FBA14017 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | OpenShift_Bastion_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | Yes | FBA14017 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Red Hat Enterprise 8.8 (4.18.0-477.15.1.el8_8.x86_64) | 4 | 8192 | 161894 | 161894 | 10.30.150.171
fba14019 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master01_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14019 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174328 | 174156 | 10.128.0.2
fba14020 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master02_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14020 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174311 | 173154 | 10.129.0.2
fba14021 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Master03_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14021 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 174311 | 174141 | 10.130.0.2
fba14022 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra01_PRD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14022 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 276733 | 90218 | 10.129.2.2
fba14023 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra02_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14023 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 606981 | 449443 | 10.128.2.2
fba14024 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Infra03_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14024 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 20480 | 416307 | 307474 | 10.131.0.2
fba14025 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker01_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14025 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219387 | 124273 | 10.130.2.2
fba14026 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker02_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14026 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219431 | 127342 | 10.131.2.2
fba14027 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker03_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14027 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219245 | 122692 | 10.130.4.2
fba14028 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker04_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14028 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219389 | 117298 | 10.129.4.2
fba14029 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker05_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14029 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219307 | 121733 | 10.128.4.2
fba14030 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker06_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14030 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219390 | 117133 | 10.128.6.2
fba14031 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker07_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14031 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219432 | 122066 | 10.131.4.2
fba14032 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Openshift_Worker08_PROD |  | Decommissioned | STAGING | No | Decommissioned |  |  |  | No | FBA14032 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219281 | 121099 | 10.129.6.2
fba14033 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 65536 | 219255 | 121596 | 10.130.6.2
FBA15001 |  |  |  | Faddom is FIS tool and no migrate - jdeltoro 7/24 |  | FIS MIT Faddom Application and Windows Proxy | FIS MIT Faddom Application and Windows Proxy | Installed | Production | Monitoring | N/A |  |  | Prod |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | N/A | N/A | N/A | No Migration | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.190 | [20 empty] | Yes
FBA15064 |  |  |  | Azure Migrate is FIS tool and no migrate - jdeltoro 7/24 |  | FIS MIT Azure Migrate Application | FIS MIT Azure Migrate Application | Installed | Production | Monitoring | N/A |  |  | Prod |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | N/A | N/A | N/A | No Migration | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.235 | [20 empty] | Yes
FBA15065 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | FIS MIT FLEXERA Server Appliance | Flexera | Installed | STAGING |  | TBD |  |  | Staging |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Debian GNU/Linux 11 |  |  |  |  | 10.30.136.236 | [20 empty] | No
FBA15066 |  |  |  | New VM reported by Angel Lopez - jdeltoro 7/24 |  | FIS MIT Flexera Beacon | Flexera | Installed | Production | Monitoring | N/A |  |  | Prod |  |  | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Microsoft Windows Server 2022 |  |  |  |  | 10.30.136.237 | [20 empty] | Yes
FBA2478 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | Xpress UAT Server | Xpress | Installed | STAGING |  | TBD |  |  | Staging |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.207 | [20 empty] | No
FBA2480 |  |  |  | New server commission per Angel - jdeltoro 10/21 |  | LINUX NDM UAT | IBM NDM | Installed | STAGING |  | TBD |  |  | Staging |  |  | N/A | [7 empty] | TBD |  | TBD |  |  |  |  | MR1130 | TBD | TBD | TBD | TBD | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 |  |  |  |  | 10.30.140.61 | [20 empty] | No
FBA-APPRODR011 |  |  | x | Validate No Migrate - Arterial |  | DR | DR | Disposed/Retired | Contingency | Applications | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | No | FBA-APPRODR011 | No |  | N/A |  | N/A | FBA-APPRODR011 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 32768 | 203464 | 104071 | 10.20.13.15
FBA-APPROPRDS01 | [5 empty] | VDI Horizon APPRO-RDS-01 | VDI Horizon | Installed | Production | Applications | Multiple VDI Users | VDI Horizon APPRO-RDS-01 | VDI Horizon APPRO-RDS-01 |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-APPROPRDS01 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 203609 | 159357 | 10.30.82.76 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA-APPROPRDS02 | [5 empty] | VDI Horizon APPRO-RDS-02 | VDI Horizon | Installed | Production | Applications | Multiple VDI Users | VDI Horizon APPRO-RDS-02 | VDI Horizon APPRO-RDS-02 |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-APPROPRDS02 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 33792 | 203608 | 161645 | 10.30.82.77 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA-APPROPRDS03 | [5 empty] | VDI Horizon APPRO-RDS-03 | VDI Horizon | Installed | Production | Applications | Multiple VDI Users | VDI Horizon APPRO-RDS-03 | VDI Horizon APPRO-RDS-03 |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-APPROPRDS03 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 276709 | 216947 | 10.30.82.38 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA-APPROPRDS04 | [5 empty] | VDI Horizon APPRO-RDS-04 | VDI Horizon | Installed | Production | Applications | Multiple VDI Users | VDI Horizon APPRO-RDS-04 | VDI Horizon APPRO-RDS-04 |  | Production | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-APPROPRDS04 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 33792 | 203608 | 162308 | 10.30.82.11 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBA-APPRO-RDS01 | [5 empty] | VDI Horizon APPRO-RDS-01 | VDI Horizon | Installed | UAT | Applications | Multiple VDI Users | VDI Horizon APPRO-RDS-01 | VDI Horizon APPRO-RDS-01 |  | UAT | Yes | Pending |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-APPRO-RDS01 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2012R2 6.3.9600 | 8 | 32768 | 214852 | 148726 | 10.30.82.15 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBADR01013 |  |  | x | Validate No Migrate |  | File Server Alterial | FileAlterial | Installed | Contingency | File Server | N/A | File Server Alterial |  |  | Contingency | Yes | TBD |  |  |  | No |  | No |  | N/A |  | N/A | FBADR01013 | 10.20.120.48 |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 16384 | 733445 | 557285 | 10.20.120.48 | [20 empty] | No
FBADR02031 |  |  | x | Validate No Migrate |  | OnBase File Transfer Report Appl Server Aretrial | OnBase File Transfer Report ApplAretrial | Installed | Contingency | Applications | N/A | OnBase File Transfer Report Appl Server Aretrial |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBADR02031 | FBADR02031.firstbank.local |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 10240 | 1443945 | 957725 | 10.20.120.200 | [20 empty] | No
FBADR02235 |  |  | x | Validate No Migrate |  | D1 Onbase WKSOBDocComp 1 - Arterial | Onbase | Installed | Contingency | Applications | TSA | D1 Onbase WKSOBDocComp 1 - Arterial |  |  | Contingency | Yes | TBD |  | Yes |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBADR02235 |  |  |  | Arterial |  | Milestone 3 |  | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 20480 | 328095 | 296812 | 10.20.109.22 | [20 empty] | No
FBADR02237 |  |  | x | Validate No Migrate |  | D1 Onbase WKSOBDocComp 1 - Arterial | Onbase | Installed | Contingency | Applications | TSA | D1 Onbase WKSOBDocComp 1 - Arterial |  |  | Contingency | Yes | TBD |  | Yes |  | Yes |  | No |  | Sharon Gutierrez |  | Angel Ocasio / Kevin Cruz, TSA - Wilfredo Ruiz | FBADR02237 |  |  |  | Arterial |  | Milestone 3 |  | D1 | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 8192 | 223641 | 144035 | 10.20.109.95 | [20 empty] | No
FBADR02239 |  |  | x | Validate No Migrate |  | Onbase Report Web Server Prod 1 - Arterial | Onbase Report Web 1 - Arterial | Installed | Contingency | Applications | N/A | Onbase Report Web Server Prod 1 - Arterial |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBADR02239 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 32768 | 289177 | 194641 | 10.20.109.50 | [20 empty] | No
FBADR02329 |  |  | x | Validate No Migrate |  | Onbase temp Document Conversion Server - Arterial | Onbase temp Document Conversion- Arterial | Installed | Contingency | Applications | N/A | Onbase temp Document Conversion Server - Arterial |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBADR02329 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.6709 (1607) | 4 | 16384 | 119194 | 105999 | 10.20.109.232 | [20 empty] | No
FBADR02362 |  |  | x | Decommissioned |  |  |  | Installed | Contingency | Applications | N/A | Onbase Econtracting DMZ 1 - Arterial |  | Decommissioned | Contingency | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 8192 | 213414 | 132293 | 10.20.99.177 | [20 empty] | No
FBADR02379 |  |  | x | Validate No Migrate |  | Onbase Econtracting app server - Arterial | Onbase Econtracting app- Arterial | Installed | Contingency | Applications | N/A | Onbase Econtracting app server - Arterial |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBADR02379 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 8 | 16384 | 170396 | 101276 | 10.20.109.67 | [20 empty] | No
FBADR02397 |  |  | x | Decommissioned |  |  |  | Installed | Contingency | Applications | N/A | Onbase Econtracting DMZ2 - Arterial |  | Decommissioned | Contingency | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 8192 | 213422 | 126723 | 10.20.99.178 | [20 empty] | No
FBADR07009 |  |  | x | Validate No Migrate |  | PCI-COB SFTP Server OneSumX | No Match | Installed | Contingency | Applications | N/A | PCI-COB SFTP Server OneSumX |  |  | Contingency | Yes | TBD | Yes |  |  | No |  | No |  | N/A |  | N/A | FBADR07009 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 248299 | 160671 | 10.20.120.18 | [20 empty] | No
FBADR65367 |  |  | x | Validate No Migrate |  | HR, CTB< Comercial | HR, CTB< Comercial | Installed | Contingency | Applications | N/A | HR, CTB< Comercial |  |  | Contingency | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBADR65367 |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 8192 | 294496 | 294496 | 10.20.109.146 | [20 empty] | No
FBAMDC1 |  |  | x |  |  | Branch Server - File/Print | Branch- File/Print | Installed | Production | File Server | N/A | Mayaguez Server | Branch Server - File/Print |  | Production | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBAMDC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.148.4
FBA-VDI-RDS-01 |  |  |  | updated CMDB status and environment per Angel - jdeltoro 11/10 |  | VDI Horizon-RDS-01 | VDI Horizon | Disposed/Retired | OFF | Applications | Multiple VDI Users | VDI Horizon-RDS-01 | VDI Horizon-RDS-01 |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-VDI-RDS-01 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 8 | 32768 | 205347 | 129255 | 10.30.82.169 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32
FBA-VDI-RDS-02 | [5 empty] | VDI Horizon-RDS-02 | VDI Horizon | Installed | Production | Applications | Multiple VDI Users | VDI Horizon-RDS-02 | VDI Horizon-RDS-02 |  | UIT | Yes | TBD |  |  |  | Yes |  | Yes |  | Juan Espinoza |  | Rafael Perez/Carlos Castillo | FBA-VDI-RDS-02 |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2016 10.0.14393.6981 (1607) | 8 | 32768 | 192429 | 119566 | 10.30.82.46 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32 | [6 empty] | No
FBBR000MOA |  |  |  | No Migrate |  | TSA Branch Server Mosaic - Test/Dev | TSA BranchMosaic | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR000MOA | FBBR000MOA.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 280660 | 280660 | 10.30.137.55 | [20 empty] | No
fbbr001fs |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | fbbr001fs | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.9.12
FBBR002FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR002FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.4.12
FBBR003FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR003FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.8.12
FBBR004FS |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBBR004FS | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.10.11
FBBR009FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR009FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.5.11
FBBR011FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR011FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.6.12
FBBR014FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR014FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.18.12
FBBR015FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR015FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.19.12
FBBR016FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR016FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.20.12
fbbr019fs |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | fbbr019fs | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.0.23.11
FBBR020FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR020FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.24.12
FBBR025FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR025FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.27.12
FBBR030FS |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | fbbr030fs | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.31.11
FBBR031FS |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | PR_Forest_Hill_File_Server | PR_Forest_Hill_File_ | Disposed/Retired | OFF | File Server | N/A | Not Found | PR_Forest_Hill_File_Server | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBBR031FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.32.12
FBBR032FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR032FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.33.11
fbbr033fs |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | fbbr033fs | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.0.34.11
FBBR035FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR035FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.36.12
FBBR036FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR036FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.37.12
FBBR039FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR039FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.40.12
FBBR040FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR040FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.41.12
FBBR041FS |  |  |  | No Migrate |  | Branch Server - File/Print - Mosaic | Branch- File/Print - Mosaic | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR041FS | FBBR041FS.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 280661 | 280661 | 10.30.137.134 | [20 empty] | Yes
FBBR042FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR042FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.42.12
FBBR044FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR044FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.44.12
FBBR045FS |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print - Mosaic | Branch- File/Print - Mosaic | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR045FS | FBBR045FS.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Virtual Server | poweredOff | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 280662 | 280662 | 10.30.137.187
FBBR046FS |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | fbbr046fs | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.45.11
FBBR053FS | [5 empty] | Mosaico Money Counting - Is a virtual server | Mosaico Money Counting - Is a virtual | Installed | Production | Applications | N/A | Not Found | Mosaico Money Counting - Is a virtual server | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBBR053FS | FBBR053FS.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 280668 | 280668 | 10.30.137.70 | 255.255.255.0 | [19 empty] | No
FBBR061FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR061FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.67.12
FBBR062FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR062FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.71.12
FBBR063FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR063FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.35.12
fbbr065fs |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | fbbr065fs | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.0.72.11
FBBR067FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR067FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.48.12
FBBR068FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR068FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.43.12
FBBR710FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR710FS | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.12.6
FBBR712FS |  |  | x |  |  | Branch Server - File/Print | Branch- File/Print | Installed | Production | File Server | N/A | Not Found | Branch Server - File/Print |  |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR712FS | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.62.6
FBBR719FS |  |  | x |  |  | Branch Server - File/Print | Branch- File/Print | Installed | Production | File Server | N/A | Not Found | Branch Server - File/Print |  |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR719FS | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.15.0.2
FBBR721FS |  |  | x |  |  | Branch Server - File/Print | Branch- File/Print | Installed | Production | File Server | N/A | Not Found | Branch Server - File/Print |  |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR721FS | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.1.152.9
FBBR722FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR722FS | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.63.6
FBBR724FS |  |  | x |  |  | Branch Server - File/Print | Branch- File/Print | Installed | Production | File Server | N/A | Not Found | Branch Server - File/Print |  |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR724FS | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.60.6
FBBR733FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR733FS | [5 empty] | N/A | N/A | No Migration |  | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.79.6
FBBR801FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR801FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.160.12
FBBR802FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes | FBBR802FS | No |  | N/A |  | N/A | FBBR802FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.167.12
FBBR803FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR803FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.168.12
FBBR804FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | Disposed\Retired | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes | FBBR804FS | No |  | N/A |  | N/A | FBBR804FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.165.12
FBBR805FS |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBBR805FS | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.164.11
FBBR806FS |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Dolphin-Humacao File Server | Dolphin-Humacao File | Disposed/Retired | OFF | File Server | N/A | Not Found | Dolphin-Humacao File Server | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBBR806FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.163.12
FBBR807FS |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | FBBR807FS | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.166.11
FBBR808FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR808FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.162.12
FBBR809FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR809FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.161.12
FBBR810FS |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Branch Server - File/Print | Branch- File/Print | Disposed/Retired | OFF | File Server | N/A | Not Found | Branch Server - File/Print | Decommissioned |  | Yes | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A | FBBR810FS | [5 empty] | N/A | N/A | No Migration | Physical Server | poweredOff | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.0.169.12
FBBRUAT2FS | [5 empty] | UAT Mosaico - Is a virtual server | Mosaico | Installed | UAT | Applications | N/A | Not Found | UAT Mosaico - Is a virtual server |  |  | Yes | Pending |  |  |  | Yes |  | Yes |  | N/A |  | N/A | FBBRUAT2FS | patchlinkproxy.firstbank.local |  |  |  |  | N/A | N/A | No Migration | Physical Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 4 | 4096 | 290910 | 124000 | 10.30.140.234 | [20 empty] | No
FBCCRMRPTS | [5 empty] | CRM REPORTS | CRM REPORTS | Disposed/Retired | OFF | Applications | N/A | Not Found | CRM REPORTS | Decommissioned |  | No | Pending |  |  |  | No | FBCCRMRPTS | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FB-DIRECTOR |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.16 | [20 empty] | No
FBDR02115 |  |  | x | Validate No Migrate - Arterial; updated CMDB status and environment per Angel - jdeltoro 11/10 |  | DR B2Bi | DR B2Bi | Disposed/Retired | OFF | Applications | N/A | Not Found |  |  |  | No | Completed |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (3.10.0-1160.105.1.0.1.el7.x86_64) | 2 | 10240 | 881321 | 626718 | 10.20.106.15
FBDR02197 |  |  | x | Validate No Migrate |  | Alterial D1 Glass Server 1 | D1 | Installed | STAGING | Applications | TSA | Not Found | Alterial D1 Glass Server 1 |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | Arterial | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.326.6.el7uek.x86_64) | 4 | 12288 | 191819 | 100705 | 10.20.120.21 |  |  |  | 10.100.120.21 | [16 empty] | No
FBDR02198 |  |  | x | Validate No Migrate |  | Alterial D1 Glass Server 2 | D1 | Installed | STAGING | Applications | TSA | Not Found | Alterial D1 Glass Server 2 |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | Arterial | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.326.6.el7uek.x86_64) | 4 | 12288 | 191759 | 100379 | 10.20.120.22 |  |  |  | 10.100.120.22 | [16 empty] | No
FBDR02201 |  |  | x | Validate No Migrate |  | Alterial D1 Coonect 1 | D1 | Installed | STAGING | Applications | TSA | Not Found | Alterial D1 Coonect 1 |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | Arterial | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.326.6.el7uek.x86_64) | 8 | 16384 | 190768 | 98716 | 10.20.120.25 |  |  |  | 10.100.120.25 | [16 empty] | No
FBDR02202 |  |  | x | Validate No Migrate |  | Alterial D1 Connect Server 2 | D1 | Installed | STAGING | Applications | TSA | Not Found | Alterial D1 Connect Server 2 |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | Arterial | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.326.6.el7uek.x86_64) | 8 | 16384 | 190717 | 98076 | 10.20.120.26 |  |  |  | 10.100.120.26 | [16 empty] | No
FBDR02205 |  |  | x | Validate No Migrate |  | Alterial D1 Connect 5 | D1 | Installed | STAGING | Applications | TSA | Not Found | Alterial D1 Connect 5 |  |  | No | Pending |  | Yes |  | Yes |  | Yes |  | Sharon Gutierrez |  | John Huertas |  |  |  |  | Arterial | FIS | N/A | N/A | D1 | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.326.6.el7uek.x86_64) | 8 | 16384 | 139531 | 48735 | 10.20.120.29 |  |  |  | 10.100.120.29 | [16 empty] | No
FBDR02339 |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 6144 | 165469 | 111808 | 10.20.99.183
FBDR03062 |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | DR B2Bi | DR B2Bi | Disposed/Retired | OFF | Database | N/A | Not Found |  | Decommissioned |  | No | Completed |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOff |  | 2 | 6144 | 416350 | 155171 | 10.20.106.17
FBDR06108 |  |  | x | Validate No Migrate - Arterial |  | DR MSP NDM | DR MSP NDM | Installed | Contingency | Applications | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | Arterial | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 6.10 (2.6.32-754.35.1.0.2.el6.x86_64) | 2 | 4096 | 40018 | 31734 | 10.20.106.186 | [20 empty] | No
FBE3CTXUAT |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | fbe3ctxuat | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 2048 | 41051 | 21753 | 10.30.141.97
FBFL-BIGFIX-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFL-BIGFIX-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.199.12 | [20 empty] | No
FBFLBSA-VS |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | FBFLBSA-VS | No |  | N/A |  | N/A | FBFLBSA-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.201
FBFLDEPCON-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFLDEPCON-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.22 | [20 empty] | No
FBFL-ENCOMPASS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFL-ENCOMPASS | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.46 | [20 empty] | No
FBFLINTRANET-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFLINTRANET-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.199.30 | [20 empty] | No
FBFLNEXPHUB-VS |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | FBFLNEXPHUB-VS | No |  | N/A |  | N/A | FBFLNEXPHUB-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.4
FBFLRPT-01-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFLRPT-01-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2008R2 6.1.7601 |  |  |  |  | 10.87.199.156 | [20 empty] | No
FBFLSYNERGY-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | Out of Scope |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFLSYNERGY-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.157 | [20 empty] | No
FBFLTRACKIT-VS |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFLTRACKIT-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.199.143 | [20 empty] | No
FBFLUMECP-VS |  |  | x | Miami; Out of scope |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Decommissioned |  |  |  | Yes | FBFLUMECP-VS | No |  | N/A |  | N/A | FBFLUMECP-VS | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5820 (1809) |  |  |  |  | 10.87.199.20
FBFL-UNICALL-01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | Out of Scope |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFL-UNICALL-01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.130 | [20 empty] | No
FBFL-UNICALL-02 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | Out of Scope |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFL-UNICALL-02 | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.87.199.131 | [20 empty] | No
FBFL-UNICALL-03 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | Out of Scope |  |  |  | Yes |  | No |  | N/A |  | N/A | FBFL-UNICALL-03 | [5 empty] | N/A | N/A | No Migration |  |  | Win2012R2 6.3.9600 |  |  |  |  | 10.81.238.41 | [20 empty] | No
FBINTEGRATION |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud GL Integration Production DB Server | Oracle Cloud GL Integrationuction DB | Disposed/Retired | OFF | Database | N/A | Not Found | Oracle Cloud GL Integration Production DB Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FBINTEGRATION | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FBISE1130ADM1_ISE | [5 empty] | Servers managed by INTWO per Rafael | INTWO | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | [5 empty] | 10.30.76.15
FBISE1130PSN_ISE | [5 empty] | Servers managed by INTWO per Rafael | INTWO | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | [5 empty] | 10.30.76.16
FBISE1519ADM1 | [5 empty] | Servers managed by INTWO per Rafael | INTWO | No Match | No Match | No Match | N/A |  |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | [5 empty] | 10.19.76.17
FBISE1519PSN1 | [5 empty] | Servers managed by INTWO per Rafael | INTWO | No Match | No Match | No Match | N/A |  |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | Santurce 1519 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | [5 empty] | 10.19.76.18
FBISEAPPLIANCE |  |  |  | No Migrate |  | Cisco NAC Control | Cisco NAC Control | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 86100 | 76254
fbme003dc1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme003dc1 | No |  | N/A |  | N/A | fbme003dc1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.3.4
FBME004DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme004dc1 | No |  | N/A |  | N/A | FBME004DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.4.4
FBME005DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme005dc1 | No |  | N/A |  | N/A | FBME005DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.5.4
FBME006DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme006dc1 | No |  | N/A |  | N/A | FBME006DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.6.4
FBME007DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme007dc1 | No |  | N/A |  | N/A | FBME007DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.7.4
FBME008DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme008dc1 | No |  | N/A |  | N/A | FBME008DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.8.4
FBME009DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme009dc1 | No |  | N/A |  | N/A | FBME009DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.9.4
FBME010DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme010dc1 | No |  | N/A |  | N/A | FBME010DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.10.4
FBME011DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | Fbme011dc1 | No |  | N/A |  | N/A | FBME011DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.11.4
FBME013DC1 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | Yes | fbme013dc1 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.13.4
FBME015DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme015dc1 | No |  | N/A |  | N/A | FBME015DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.15.4
FBME016DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme016dc1 | No |  | N/A |  | N/A | FBME016DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.16.4
fbme017dc1 |  |  | x | Decommissioned |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | fbme017dc1 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Physical Server | [6 empty] | 10.9.17.4
FBME018DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme018dc1 | No |  | N/A |  | N/A | FBME018DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.18.4
FBME019DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme019dc1 | No |  | N/A |  | N/A | FBME019DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.19.4
FBME023DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme023dc1 | No |  | N/A |  | N/A | FBME023DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.23.4
FBME024DC1 |  |  | x | Not in scope; No Migrate |  | Risk Reporting Contingency Web Server | Risk Reporting Contingency Web | Disposed/Retired | OFF | File Server | N/A | Not Found | Risk Reporting Contingency Web Server | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme024dc1 | Yes |  | N/A |  | N/A | FBME024DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.24.4
FBME030DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme030dc1 | No |  | N/A |  | N/A | FBME030DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.30.4
FBME034DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme034dc1 | No |  | N/A |  | N/A | FBME034DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.34.4
fbme035dc1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme035dc1 | No |  | N/A |  | N/A | fbme035dc1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.35.4
FBME037DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme037dc1 | No |  | N/A |  | N/A | FBME037DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.37.4
FBME038DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | FBME038DC1 | No |  | N/A |  | N/A | FBME038DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.38.4
FBME039DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | fbme039dc1 | No |  | N/A |  | N/A | FBME039DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.39.4
FBME044DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | Applications | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | FBME044DC1 | No |  | N/A |  | N/A | FBME044DC1 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.44.4
FBME045DC1 |  |  | x | Not in scope; No Migrate |  |  |  | Disposed/Retired | OFF | File Server | N/A | Not Found |  | Decommissioned |  | Yes | Completed |  |  |  | Yes | FBME045DC1 | No |  | N/A |  | N/A | FBME045DC1 | [5 empty] | N/A | N/A | No Migration | Physical Server |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.9.45.4
FBMEFS01 | [5 empty] | File Server MonEx | FileMonEx | Installed | Production | Applications | N/A | Not Found |  |  |  | Yes | Pending |  |  |  | Yes | FBMEFS01 | No |  | N/A |  | N/A | FBMEFS01 | FBMEFS01.firstbank.local |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Physical Server | poweredOn | Win2019 10.0.17763.5936 (1809) | 8 | 8192 | 1441882 | 1441882 | 10.30.137.30 | 255.255.255.0 | [19 empty] | Yes
FBMOSAICO |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Mosaico | Mosaico | Disposed/Retired | OFF | Applications | N/A | Not Found | Mosaico | Decommissioned |  | No | Completed |  |  |  | No | FBMOSAICO | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff
FBMOSAICOSQL |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | MOSAICO SQL | MOSAICO SQL | Disposed/Retired | OFF | Database | N/A | Not Found | MOSAICO SQL | Decommissioned |  | No | Decommissioned |  |  |  | No | FBMOSAICOSQL | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  | poweredOff
fbmrrepoappl |  |  |  | Follow up with Rafael Ramirez and Derek Kirkman - jdeltoro 5/9 |  | REPO APPL SERVER | REPO | Installed | Production | Applications | N/A | Not Found | REPO APPL SERVER |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | No Migration; New Build Replacement | Virtual Server | poweredOn | Win2003 5.2.3790 | 2 | 2048 | 84918 | 84918 | 10.30.141.86 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D2ls_v6 | 2 | 4 | [6 empty] | No
FBNDMMR | [5 empty] | VM Server / NDM - DEBTManager - Connected with Digital Banking | DebtManager | Installed | Production | Applications | Sheila Ponte | Not Found | VM Server / NDM - DEBTManager |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | Santitos Rivas |  | Geraldo Reyes | FBNDMMR | FBNDMMR.firstbank.local |  | DebtManager | MR1130 | Cloud | Milestone 2 | Group 6 | TBD | Virtual Server | poweredOn | Win2016 10.0.14393.7070 (1607) | 6 | 8192 | 264292 | 264292 | 10.30.137.240 | 255.255.255.0 | [9 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16 | [6 empty] | Yes
fbopconsqluat |  |  |  | No migrate |  | DB2 UAT | DB2 | Installed | UAT | Database | N/A | Not Found | DB2 UAT |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | fbopconsqluat |  |  |  | MR1130 | Cloud | N/A | N/A | No Migration | Physical Server |  | Win2008R2 6.1.7601 |  |  |  |  | 10.30.130.67 | 255.255.255.0 | [9 empty] | No CPU/RAM Info Found
FBOPTAMPROD | [5 empty] | Direct CD | Direct CD | Available | OFF | Database | N/A | Not Found | Direct CD |  |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBPR_MP |  |  |  | Will move from Gen1 to Gen2; dependent on obsolete refresh project; IP changes would require work to adjust agents on FBPR side |  | MIT MSS Server - SIEM | MIT - SIEM | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Jay Randolph | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | CentOS 4/5/6 | 2 | 2 | 60 | 5 | 172.31.0.102 | 255.255.255.240 | 172.31.0.97 | 100.121.143.102 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
FBPRMAC201 |  |  |  | Will move from Gen1 to Gen2; FBPR internal (German) project to move to bitlocker; will be active till April 2025; No issues with moving to MIT.local domain; prestage server for domain migration on night of cut; |  | MIT MSS Server - Disk Encryption Project | MIT - Disk Encryption Project | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Chris Evans | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows Server 2016 | 4 | 16 | 350 | 194 | 172.31.0.106 | 255.255.255.240 | 172.31.0.97 | 100.121.143.106 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
fbpr-xiam-prod-db |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 6 | 32768 | 295474 | 157054 | 10.30.167.5 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D8s_v6 | 8 | 32
fbpr-xiam-prod-prov |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 2 | 16384 | 278682 | 91242 | 10.30.167.4 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16
fbpr-xiam-prod-web |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  |  | MR1130 | Cloud | Milestone 3 |  | TBD | Virtual Server | poweredOn |  | 6 | 16384 | 278618 | 32907 | 10.30.166.4 | [10 empty] | Standard Dlsv6 Family vCPUs | Standard D8ls_v6 | 8 | 16
fbpr-xiam-test-db |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  | Xapiens | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn |  | 4 | 16384 | 278651 | 40258 | 10.30.165.11 | [10 empty] | Standard Dsv6 Family vCPUs | Standard D4s_v6 | 4 | 16
fbpr-xiam-test-prov |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  | Xapiens | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn |  | 2 | 16384 | 278647 | 37742 | 10.30.165.12 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16
fbpr-xiam-test-web |  |  | x | ON |  | Xapiens | Xapiens | No Match | No Match | No Match | Access Management | Not Found | Xapiens |  |  | No | TBD |  |  |  | No |  | No |  | Maria Ripepi |  | Luis Adames/Omar Cuadrado |  |  |  | Xapiens | MR1130 | Cloud | Milestone 2 | Group 5 | TBD | Virtual Server | poweredOn |  | 2 | 16384 | 278627 | 28271 | 10.30.164.11 | [10 empty] | Standard Esv6 Family vCPUs | Standard E2s_v6 | 2 | 16
FBREFERRALS |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | OSS | OSS | Disposed/Retired | OFF | Applications | TSA | Not Found | OSS | Decommissioned |  | No | Pending |  |  |  | No | FBREFERRALS | Yes |  | Sharon Gutierrez |  | Eric Lopez |  |  |  | OSS |  | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBSAOMNIBAKCOB | [5 empty] | Omniback | Omniback | Disposed/Retired | OFF | Utilities | N/A | Not Found | Omniback | Decommissioned |  | No | Decommissioned |  |  |  | No | FBSAOMNIBAKCOB | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
FBSUNWEBBUDG |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | Bancware ALM Compute Server | Bancware | Disposed/Retired | OFF | Applications | Financial Planning | Not Found | ALM Compute Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FBSUNWEBBUDG | Yes |  | Maria Medina |  | Maria Medina |  |  |  | Bancware |  | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
FBWEBGATEWAY |  |  | x | Decommissioned |  |  |  | No Match | No Match | No Match | N/A | Not Found |  | Decommissioned |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4128 | 260212 | 48996 | 10.30.140.58
FDMEE-PROD-APP |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud FDMEE Production Application Server | Oracle Cloud FDMEEuction Application | Disposed/Retired | OFF | Applications | N/A | Not Found | Oracle Cloud FDMEE Production Application Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FDMEE-PROD-APP | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FDMEE-TEST-APP |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud FDMEE TEST Application Server | Oracle Cloud FDMEE Application | Disposed/Retired | OFF | Applications | N/A | Not Found | Oracle Cloud FDMEE TEST Application Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FDMEE-TEST-APP | Yes |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff
FDMEE-TEST-DB |  |  |  | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud FDMEE TEST DB Server | Oracle Cloud FDMEE DB | Disposed/Retired | OFF | Database | N/A | Not Found | Oracle Cloud FDMEE TEST DB Server | Decommissioned |  | No | Decommissioned |  |  |  | No | FDMEE-TEST-DB | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  | poweredOff | [16 empty] | No CPU/RAM Info Found
FMG-VM64 |  |  |  | No Migrate |  | FortiManager | FortiManager | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 8192 | 215123 | 215123 | 10.30.136.31
HIHHPSVR01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | HIHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.83.217.15
intech-mr1130-scanner01 | [7 empty] | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 92247 | 92247 | 10.30.136.67
intech-tenable-sc | [7 empty] | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 8192 | 264278 | 264278 | 10.30.136.66
INTRA-SQLSRV |  |  |  | Decommissioned |  |  |  | Disposed/Retired | Production | Database | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | INTRA-SQLSRV | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration
JAXFBPRZABPRX01 |  |  |  | Will move from Gen1 to Gen2; Zabbix |  | MIT Zabbix Server | MIT - Zabbix | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Andrew Harris | N/A |  |  |  |  | FIS JAX | FIS - UCE | N/A | N/A | Replicate and Re-IP | Virtual Server | poweredOn | Red Hat Enterprise Linux 8 | 2 | 4 | 120 | 18 | 172.31.0.110 | 255.255.255.240 | 172.31.0.97 |  | 100.113.33.232 | 255.255.255.240 | 172.31.0.99 | 100.113.33.225 | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦CORE_AP¦UCE-100.113.33.224_28_EPG | [9 empty] | VADP
JAXMITFBPRTSC01 |  |  |  | Will move from Gen1 to Gen2; replacement server to TSC11 - jdeltoro 5/16 |  | MIT RDS Server - New Bastion Server | MIT RDS Server - Bastion Server | No Match | No Match | No Match | N/A | [5 empty] | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows 2022 |  |  |  |  | 172.31.0.109 | 255.255.255.240 | 172.31.0.97 | 100.121.143.109 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
JAXMITWFPRDLP01 |  |  |  | Will move from Gen1 to Gen2; replacement server to COL Server - jdeltoro 5/16 |  | MIT MSS Server - New BigFix Reporting and DLP | MIT - BigFix Reporting and DLP | No Match | No Match | No Match | N/A | [5 empty] | TBD | [7 empty] | N/A |  | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows 2022 |  |  |  |  | 172.31.0.105 | 255.255.255.240 | 172.31.0.97 | 100.121.143.105 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
JAXPNFBPREPP01 |  |  |  | Will move from Gen1 to Gen2; database will be moved from SQL01 to EPP01 within a few weeks of 1/30; No issues with moving to MIT.local domain; prestage server for domain migration on night of cut |  | Replacement SQL Server for SQL01 | Replacement SQLfor SQL01 | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Chris Evans | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows 2022 | 4 | 12 | 320 | 320 | 172.31.0.100 | 255.255.255.240 | 172.31.0.97 | 100.121.143.100 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
JAXVNMSFBPRCOL |  |  |  | Will move from Gen1 to Gen2; BigFix Reporting |  | MIT MSS Server - BigFix Reporting | MIT - BigFix Reporting | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Dean Hanna/Tim K./Daniel | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows Server 2019 | 4 | 16 | 620 | 420 | 172.31.0.98 | 255.255.255.240 | 172.31.0.97 | 100.121.143.98 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
KEHHPSVR01 |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | KEHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.87.203.15
linuxtemplate |  |  | x | ON |  | Linux Template 8 | Linux Template 8 | No Match | No Match | No Match | N/A | Not Found | Linux Template 8 |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 7.9 (4.1.12-124.63.3.1.el7uek.x86_64) | 2 | 4096 | 75880 | 17711 | 10.30.140.207 | 255.255.255.0
LinuxTemplate8 |  |  |  | Validate No Migrate |  | Linux Template 8 | Linux Template 8 | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn | Linux Oracle Enterprise Server 8.10 (5.4.17-2136.331.7.el8uek.x86_64) | 4 | 4096 | 106595 | 24537 | 10.30.140.128 | 255.255.255.0
LoadMaster VLM |  |  |  | No Migrate |  |  |  | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 1024 | 33874 | 33874
MICROSTRATEGYAP |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | MicroStrategyAppProd | MicroStrategyApp | Disposed/Retired | OFF | Applications | N/A | Not Found | MicroStrategyAppProd | Decommissioned |  | No | Completed |  |  |  | Yes | microstrategyap | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  | poweredOff | Win2012R2 6.3.9600 |  |  |  |  | 10.179.4.66 | [10 empty] | No CPU/RAM Info Found
microstrdev |  |  | x | Oracle Cloud |  | Microstrategy Dev | Microstrategy | Installed | Development | Applications | N/A | Not Found | Microstrategy Dev |  |  | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 8.9 (5.4.17-2136.326.6.el8uek.x86_64) |  |  |  |  | 10.179.4.246, 192.168.16.18 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
MR1130-FAuth-1 |  |  |  | No Migrate |  | FortiAuthenticator | FortiAuthenticator | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 8192 | 214127 | 185791 | 10.30.128.105
MR1130-Foti-Analyzer-VM |  |  |  | No Migrate |  | FortiAnalyzer | FortiAnalyzer | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 16384 | 1579104 | 1559681 | 10.30.136.30
MSTRAAPDEV |  |  | x | Decommissioned per Angel Lopez - jdeltoro 9/18 |  | Oracle Cloud | Oracle Cloud | Disposed/Retired | OFF | Applications | N/A | Not Found | Oracle Cloud | Decommissioned |  | No | Decommissioned |  |  |  | Yes | MStraApDEV | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  | poweredOff | Win2012R2 6.3.9600 |  |  |  |  | 10.179.4.210
MXQ9510312 |  |  |  | Decommissioned per Angel Lopez - jdeltoro 7/2 |  | HPE Proliant Solutions Server Proliant DL360 Gen 10 | HPE Proliant SolutionsProliant DL360 Gen 10 | Disposed/Retired | Production | Database | N/A | Not Found | HPE Proliant Solutions Server Proliant DL360 Gen 10 | Decommissioned |  | No | Decommissioned |  |  |  | No | MXQ9510312 | Yes |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
ONDEMANDPRD |  |  | x | Oracle Cloud |  | OnDemand - Tutel | OnDemand - Tutel | Installed | Production | Applications | N/A | Not Found | OnDemand - Tutel |  |  | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.179.4.123 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
PEHHPSVR01 |  |  |  | FL; Out of Scope |  | N/A | N/A | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | PEHHPSVR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.88.10.5
PLATFORM-SRV |  |  | x | Miami; Out of scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | PLATFORM-SRV | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.87.199.25 | [20 empty] | No
procctrldev |  |  | x | Oracle Cloud |  | Tutela Oracle Cloud ProcessControl Dev | Tutela Oracle Cloud ProcessControl | Installed | Development | Applications | N/A | Not Found | Tutela Oracle Cloud ProcessControl Dev |  |  | No | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.324.5.3.el7uek.x86_64) |  |  |  |  | 10.179.4.226 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
procctrlprd |  |  | x | ON |  | Proccess Control | Proccess Control | Installed | Production | Applications | N/A | Not Found | Proccess Control |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (5.4.17-2136.329.3.1.el7uek.x86_64) |  |  |  |  | 10.179.4.82 | [20 empty] | No
RedhatTemplate8 |  |  | x | ON |  | Template Linux Template | Template Linux Template | No Match | No Match | No Match | N/A | Not Found | Template Linux Template |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A |  |  |  |  | MR1130 | Onsite | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 4096 | 106604 | 6738 | 10.30.140.80 | 255.255.255.0
sbc01 |  |  | x | ON |  | SBC For TEAM | SBC For TEAM | No Match | No Match | No Match | N/A | Not Found | SBC For TEAM |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [5 empty] | Onsite | N/A | N/A | No Migration
SEGPHY | [5 empty] | Access Control | Access Control | Disposed/Retired | OFF | Security | N/A | Not Found | Access Control | Decommissioned |  | No | Decommissioned |  |  |  | No | SEGPHY | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found
teraappliance9 |  |  |  | Not in scope; No Migrate |  | N/A | N/A | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 8 | 16384 | 246930 | 246930 | 172.17.0.1
tutela |  |  | x | Oracle Cloud |  | TUTELA DB PROD | TUTELA DB | Installed | Production | Applications | N/A | Not Found | TUTELA DB PROD |  |  | No | Completed |  |  |  | Yes |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration |  |  | Linux Oracle Enterprise Server 7.9 (4.1.12-124.81.2.el7uek.x86_64) |  |  |  |  | 10.179.4.252, 192.168.16.18 | [10 empty] | No CPU/RAM Info Found | [9 empty] | No
VirtualSW01 |  |  |  | Not in scope; No Migrate |  | N/A | N/A | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 1 | 256 | 8529 | 8529
VMLAP64209 |  |  |  | Not in scope; No Migrate |  | Laptop that ended up in Server List; Might need follow up | Laptop that ended up inList; Might need follow up | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration |  |  | <not reported> |  |  |  |  | 172.20.120.63
VNMSFBPRSQL01 |  |  |  | Decommissioned |  | MIT MSS SQL Server | MIT MSS SQL | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Chris Evans | N/A |  |  |  |  | FIS JAX | N/A | N/A | N/A | No Migration | Virtual Server | poweredOff | Microsoft Windows Server 2012 R2 | 2 | 10 | 600 | 216 | 172.31.0.101 | 255.255.255.240 | 172.31.0.97 | 100.121.143.101 | [6 empty] | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG
VNMSFBPRTSC11 |  |  |  | Will move from Gen1 to Gen2; RDS Bastion Jump Server and DNS Server |  | MIT RDS Server/DNS Server | MIT RDS Server/DNS Server | No Match | No Match | No Match | N/A |  |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A | Diallo | N/A |  |  |  |  | FIS JAX | FIS - Bastion | N/A | N/A | Replicate and Move Network | Virtual Server | poweredOn | Microsoft Windows Server 2019 | 4 | 16 | 120 | 83 | 172.31.0.99 | 255.255.255.240 | 172.31.0.97 | 100.121.143.99 |  |  |  |  | JAX_PROD_Cloud | JAX_FBPR_12121_UCE_001 | FBPR-12121¦VNMS_AP¦FBPR-VNMS-172.31.0.96_28_EPG | [9 empty] | VADP
WAPVMGT01 |  |  | x | FL; Out of Scope |  | Veeam Backup Gateway Server | Veeam Backup Gateway | Installed | Production | Database | N/A | Not Found | Veeam Backup Gateway Server |  |  | Yes | TBD |  |  |  | Yes |  | Yes |  | N/A |  | N/A | WAPVMGT01 |  |  |  |  | Onsite | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5936 (1809) |  |  |  |  | 10.81.239.21
WAVBKUP01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | WAVBKUP01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5458 (1809) |  |  |  |  | 10.81.239.20 | [20 empty] | No
WAVCYAR01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | Security | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | WAVCYAR01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2022 10.0.20348.2527 (21H2) |  |  |  |  | 10.81.239.32 | [20 empty] | No
WAVDC01 | [5 empty] | Domain Controller | Domain Controller | Disposed/Retired | Production | Domain Controller | FIS Infra | Not Found | Domain Controller | Decommissioned |  | No | Decommissioned |  |  |  | No | WAVDC01 | Yes |  | Juan Espinoza |  | Edgardo Santiago | [5 empty] | Onsite | N/A | N/A | No Migration
WAVFILE01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | WAVFILE01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.81.238.54 | [20 empty] | No
WAVMT01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Development | File Server | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | WAVMT01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2019 10.0.17763.5458 (1809) |  |  |  |  | 10.81.239.22 | [20 empty] | No
WAVPS01 |  |  | x | FL; Out of Scope |  |  |  | Installed | Production | Utilities | N/A | Not Found |  |  |  | Yes | TBD |  |  |  | Yes |  | No |  | N/A |  | N/A | WAVPS01 | [5 empty] | N/A | N/A | No Migration |  |  | Win2016 10.0.14393.7070 (1607) |  |  |  |  | 10.81.238.51 | [20 empty] | No
Web Based |  |  |  | Confirmed decommissioned - jdeltoro 5/9 |  | Web Based | Web Based | Installed | Production | Web | N/A | Not Found | Web Based | Decommissioned |  | No | TBD |  |  |  | No |  | Yes |  | N/A |  | N/A | [5 empty] | Cloud | N/A | N/A | No Migration | [18 empty] | No CPU/RAM Info Found | [9 empty] | No
WIN-CUQ4H8PLUN9 |  |  |  | Decommissioned |  |  |  | Disposed/Retired | Production | Applications | N/A | Not Found |  | Decommissioned |  | No | Decommissioned |  |  |  | No | win-cuq4h8plun9 | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 4 | 6144 | 303197 | 220197
WIN-DVEPI8OHOG7 |  |  |  | Not in scope; No Migrate |  | N/A | N/A | No Match | No Match | No Match | N/A | Not Found |  |  |  | No | TBD |  |  |  | No |  | No |  | N/A |  | N/A | [6 empty] | N/A | N/A | No Migration | Virtual Server | poweredOn |  | 2 | 8192 | 90197 | 90197 | fe80::2c6f:7d67:d4c1:3399
FBA01016 |  | Success |  | File Server Cluster Virtual IP |  | File Server | File Server | TBD | TBD |  | TBD |  |  | Prod | [10 empty] | TBD |  | TBD |  |  |  |  | MR1130 | Cloud | TBD | TBD | No Migration
150 | [39 empty] | 758 | 2364964 | 64879917 | 47455081 | [13 empty] | 750 | 2504 | [6 empty] | 150
Note on R2: tc={AFD85333-25D7-44AD-95F6-E6AC1F00A0A8}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Yes / No / Remediated Track if old server is upgraded in place, new server is built and will need to be migrated, etc.
Note on S2: tc={AB689111-78D4-4865-9452-5AAAB5BB3C63}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Systems with PCI related data cannot come into JAX/PHX data centers
Note on T2: tc={FB2BACDA-C7AB-47C0-AAE8-FD8733F01E46}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Systems that are related to D1 Project. Project start Dec 1st - June 2025
Note on AI2: Deltoro, Jose: Milestone 1 Milestone 2 Milestone 3 Milestone 4
Note on AL260: tc={AF158FC2-FE72-46DC-9673-373755CCFEF5}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on AL261: tc={674F27B6-F540-4603-BE96-C69999C8E51F}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on AL263: tc={86A167A0-B253-4549-A64E-D197A93B56BC}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on AL264: tc={B66C4D5E-F75D-4508-9395-C589956220BA}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on E1003: tc={1138DA21-815C-477E-8EE5-8D9E821A7354}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Perez, Javier create a new map to determine all ingress database connections for physical servers.
Note on AL1156: tc={D94F815A-C129-47D7-8997-87F89F1482DB}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on AL1180: tc={0BE9C4ED-1439-43F5-8912-8605C287C5C8}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM
Note on AL1237: tc={04FCFEEE-0DB6-488B-B263-D4DC5A200B7E}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This server also exists as a LAB VM